## Slide 1: P802.11ax Report to EC on Conditional Approval to go to SA Ballot
Date: 2019-11-11
Authors:

## Slide 2: Introduction
This document contains the report to the IEEE 802 Executive Committee in support of a request for conditional approval to send IEEE P802.11ax Draft 6.0 to Sponsor Ballot.
This document was approved during the plenary session of the 802.11 working group on xx November 2019.
  Passed in the Working Group xx yes, xx no , xx abstain

## Slide 3: Status Summary
The TGax Draft went through Five WG Letter Ballots. Draft 3.0 was the first to achiever > 75% needed for an approved draft
The TG has so far resolved over 15000 comments received on drafts 1.0 to 5.0.
The TG is now resolving comments received on draft 5.0 (558 comments) and is expected to complete resolutions of these comments by January 2020.
The plan is to recirculate draft 6.0 unchanged in January and proceed to SA ballot shortly after.

## Slide 4: 802.11 WG Letter Ballot Results – P802.11ax
Ballot ID | Ballot Close Date | Title | Ballot Type | Pool | Return | %Return | Abstain | %Abstain | Approve | Disapprove | %Approve
233 | 01 July 2018 | Technical Letter Ballot for TGax Draft 3.0 | Technical | 303 | 248 | 82 | 4 | 1.3 | 211 | 33 | 86
238 | 25 Feb 2019 | First Recirculation Ballot for TGax draft 4.0 | Recirculation | 303 | 278 | 91 | 3 | 1 | 253 | 22 | 92
244 | 24 Oct 2019 | Second Recirculation Ballot for TGax draft 5.0 | Recirculation | 303 | 279 | 91 | 4 | 1.3 | 258 | 17 | 93.8
244.1 |  | LB 191 Post-Ballot vote change |  | 303 | 279 | 91 | 4 | 1.3 | 260 | 15 | 94.5

## Slide 5: 802.11 WG Letter Ballot Comments – P802.11ax
Ballot ID | Ballot Close Date | Title | Total Number of Comments received (Yes and No votes)
233 | 01 July 2018 | Technical Letter Ballot for TGax draft 3.0 | 2154 (1234 T, 845 E, 45 G)
238 | 25 Feb 2019 | First Recirculation Ballot for TGax draft 4.0 | 1619 (1194 T, 394 E, 31 G)
244 | 24 Oct 2019 | Second Recirculation Ballot for TGax draft 5.0 | 558 (385 T, 166 E, 7 G)

## Slide 6: Unsatisfied Technical comments by commenter
Voter | LB233 | LB238 | LB244 | Total | 
Mark Rison (Samsung) | 0 | 0 | 295 | 295 | 
Yongho Seok (Mediatek) | 0 | 0 | 35 | 35 | 
Song-Haur An (Independent) | 0 | 0 | 16 | 16 | 
Yongang Fang (ZTE) | 0 | 0 | 13 | 13 | 
Youhan Kim (Qualcomm) | 0 | 0 | 6 | 6 | 
Kaiying Lv (Mediatek) | 0 | 0 | 3 | 3 | 
Andrew Myles | 0 | 0 | 1 | 1 | 
Tomoko Adachi (Toshiba) | 0 | 0 | 1 | 1 | 
Yusuke Tanaka | 0 | 0 | 1 | 1 | 
Total | 0 | 0 | 371 | 371 | 

## Slide 7: Unsatisfied Technical comments by commenter
Voter | LB233 | LB238 | LB244 | Total | 
Carlos Aldana (Intel) | 3 | 0 | 0 | 3 | 
Graham Smith (SR Technologies) | 6 | 0 | 0 | 6 | 
Ahmed Reza Hedayat (InterDigital) | 1 | 0 | 0 | 1 | 
Mark Hamilton (Rukus Wireless) | 0 | 40 | 0 | 40 | 
Alfred Asterjadhi (Qualcomm) | 0 | 34 | 0 | 34 | 
Joseph Levy (InterDigital) | 0 | 6 | 0 | 6 | 
Total | 10 | 80 | 0 | 90 | 

## Slide 8: Unsatisfied Technical Comments – Topics
Voter | PHY | MAC | MAC Frames | General | 
Mark Rison (Samsung) | 33 | 122 | 48 | 92 | 295
Yongho Seok (Mediatek) | 0 | 33 | 2 | 0 | 35
Song-Haur An (Independent) | 16 | 0 | 0 | 0 | 16
Yongang Fang (ZTE) | 0 | 8 | 5 | 0 | 13
Youhan Kim (Qualcomm) | 3 | 1 | 2 | 0 | 6
Kaiying Lv (Mediatek) | 0 | 2 | 1 |  | 3
Andrew Myles | 1 | 0 | 0 | 0 | 1
Tomoko Adachi (Toshiba) | 0 | 0 | 1 | 0 | 1
Yusuke Tanaka | 0 | 0 | 0 | 1 | 1
Total | 53 | 166 | 59 | 93 | 371

## Slide 9: Unsatisfied Technical Comments – Topics
Voter | PHY | MAC | MAC Frames | General | 
Carlos Aldana (Intel) | 3 | 0 | 0 | 3 | 
Graham Smith (SR Technologies) | 0 | 6 | 0 | 6 | 
Ahmed Reza Hedayat (InterDigital) | 1 | 0 | 0 | 1 | 
Mark Hamilton (Rukus Wireless) | 1 | 15 | 7 | 23 | 
Alfred Asterjadhi (Qualcomm) |  |  |  |  | 
Joseph Levy (InterDigital) | 1 | 3 | 2 | 6 | 
Total | 6 | 24 | 9 | 39 | 

## Slide 10: Unsatisfied comments
The composite of all unsatisfied comments and the resolutions approved by the comment resolution committee received during working group ballot may be found in the embedded document on the right:
  Double click on the icon to the right to open this.

## Slide 11: TGax Timeline
 | Open | Close
Third recirculation (TGac D6.0) | 20-Jan-20 | 05-Feb-20
First sponsor ballot | 01-March-20 | 30-March-20
Second sponsor ballot | 01-July-20 | 16-July-20
Third sponsor ballot | 30-Sept-20 | 14-Oct-13
Fourth sponsor ballot | 19-Oct-13 | 3-Nov-13
Fifth sponsor ballot | 3-Dec-13 | 18-Dec-13
EC to RevCom Nov-20 |  | 
RevCom to SB Dec-20 |  | 

## Slide 12: References