## Slide 1: Adopting a release framework to meet 802.11be timeline
Date: 2019-12-16
Authors:
Name | Affiliations | Address | Phone | email
Laurent Cariou | Intel |  |  | Laurent.cariou@intel.com
Robert Stacey |  |  |  | 
Carlos Cordeiro |  |  |  | 

## Slide 2: Introduction
Based on [1], 802.11be TG agreed on a timeline for 11be with the following key dates:
  D0.1 Sept 2020
  D1.0 Letter Ballot March/May 2021
  D2.0 LB Mar 2022
The market is already building an expectation around these dates [5][6], and this will only become more important over time
We believe it is critical to agree now on a development process that increases the chances this timeline can be met
In this contribution, we re-iterate the importance to respect this timeline, evaluate how to achieve this and propose possible next steps.

## Slide 3: 802.11be process and timeline [1]
The term EM in this slide captures all the TG documents except the SFD and draft
SFD
EM
D0.1–D1.0
EHT SG
TGbe
SB: D5.0–Pub
5 years
December 2019
December 2019
July 2018
May 2024
December 2019
Sept 2020
~1 year
2018
2019
2020
2021
2022
2023
2024
Nov 2020
March/May 2021
7-8 months
Nov 2022
2.5 years
May 2024
6 months
D1.0–D3.0
D4.0–D5.0
Nov2023
11ac Pub
Dec 2013
expected
Laurent Cariou, Intel

## Slide 4: Need to meet the agreed timeline (1/2)
Importance to establish predictable release dates and feature set early on [2]:
  industry needs a stable and predictable release date and feature set to plan expensive development effort
  OEMs benefit from a predictable and regular upgrade cycle
It is critically important for 11be and the Wi-Fi industry to respect this timeline, as it has major implications on:
  Competitive standing against competing technologies and their evolution cycles and marketing messaging
  Market expectations for new usages
  Product launch dates
Identifying the feature set early to meet the approved timeline is critical – more critical than the exact content of the feature set

## Slide 5: Need to meet the agreed timeline (2/2)
We just have 5 meetings (Jan, March, May, July, September 2020) before creating the first D0.1 draft.
With current pace and with current scope, and based on learnings from prior amendments, achieving this is nearly impossible
Here we present possible approaches to meet this timeline, and request members to constructively work to find a workable solutions to this problem

## Slide 6: Different time constraints depending on features
Similarly to previous PHY/MAC programs, it is expected that not all the features defined in 11be will be implemented in the first release of products
  Features show up in products based on releases (release 1, release 2, etc.), which are launched a few years apart
  This is true for both Wi-Fi and 3GPP markets
The most stringent constraint to meet the timeline really is for features that are candidate to be included in the first release
The specification of release 1 features needs to be ready and stable in 11be D1.0/D2.0 at the target dates.
On the other hand, features that are more likely to be in future releases (release 2) of products can enjoy a more relaxed development timeline and become mature at a later stage.

## Slide 7: Prioritization/releases as the way to meet timeline and market expectations
We can overcome the timeline difficulties if we are able to identify as early as now the features that are the most likely to be implemented in first release of 11be products.
We therefore propose to group the current 11be candidate features into 2 categories: a release 1 list and a release 2 list
Defining such lists will allow:
  Prioritization of these topics in the agenda during task group and ad hoc group sessions until D2.0
    Features in the release 2 list can still be discussed, and can be included in SFD. They are just deprioritized in the agenda as long as release 1 presentations are available
  Acceleration of the development of the draft and early draft comment resolutions by focusing on release 1 list

## Slide 8: Release 1 list
The release 1 list corresponds to the list of features that will need to have a mature specification in D1.0
  Contributions on these features would be prioritized in 11be agenda, and the generation of D0.1/D1.0 would be triggered as soon as these features are considered mature and stable through a TG vote
    We could still allocate a small amount of time for R2 features if we see the need
  Only these features would be converted from SFD into spec text in D0.1/1.0
  Comment resolution for D1.0/D2.0 would be focus only on those features

## Slide 9: Release 2 list
The release 2 list corresponds to the list of features that don't need to be mature in D1.0. These features could:
  Be included in 11be D1.0, but with little or no specification text
  Be only introduced in a later draft version (as we did in 11ax for Midamble (D3.0) and 6GHz related features (D4.0))
  Be specified in a newly created and dedicated Release 2 task group
11be SFD could have 2 parts: release 1 and release 2
  Release 1 part would be converted to spec text in D0.1/1.0
  Release 2 part and features from Release 1 part that are immature would be converted to spec text in a later release or within another dedicated TG
PHY design in R1 should consider forward compatibility for future R2 features. (e.g. adding hooks in preamble design)

## Slide 10: Process for release 2 topics – option 1
Release 2 features could be given the same priority as Release 1 features as soon as a major draft (e.g. D3.0/D4.0) is generated (similarly to Midamble and 6 GHz features in 11ax D3.0 and D4.0)
A selection procedure could look like this:

## Slide 11: Process for release 2 topics – option 2
Release 2 features could be specified in a newly created TG, selection procedure could look like this:

## Slide 12: How to select features for release 1
There are many reasons to consider:
  Complexity/gain tradeoff
  Time to standardize
  Time/investment to implement
  Market needs
  Interest in the features

## Slide 13: Candidate Release 1 list
We believe that the 4 following high-level topics should be present in release 1 list, because collectively they offer a major product refresh (i.e., new Wi-Fi generation) and address expected use cases:
  320 MHz bandwidth
  4K QAM
  Multiple RUs to a single STA
  Multi-link operation
Of course, depending on the evolution of a topic like multi-link operation, a second-level of details may be needed to prioritize within this topic
If there is sufficient consensus on this, we could start with this for prioritization

## Slide 14: Conclusion
It is critically important for 11be and the Wi-Fi industry to stick to the approved 11be timeline, as it has major implications on competitive standing against competing technologies, market expectations for new usages, product launch dates
The current 802.11 amendment development process does not cater to how the market works – this is a problem that we need to address
Timeline constraint is uniquely for features that are candidate for the first release of 11be products, as they need to be mature in early drafts
We therefore propose to define a release 1 list of EHT topics and to prioritize in the agenda these topics:
  320MHz, 4K QAM, Multiple RUs per STA, Multi-link operation
For R2 features process, we present here 2 options but this can be discussed/decided later, and we want to focus discussion on R1 at this stage
  For now, all remaining candidate features in PAR are main candidate features for R2

## Slide 15: Straw Poll #1
Do you agree to define releases of features, and to allow the chair and ad hoc chairs of 802.11be to prioritize contributions and decisions related to release in the agenda, starting with release 1?

## Slide 16: Straw Poll #1
Do you agree to define releases of features, and to allow the chair and ad hoc chairs of 802.11be to prioritize contributions and decisions related to release in the agenda, starting with release 1?
  A minimum time per session [~10%] should be allocated for R2 features discussion

## Slide 17: Straw Poll #2
Do you agree to include 320MHz, 4K QAM, Multiple RUs per STA and multi-link operation in 11be release 1 list?

## Slide 18: References
[1] IEEE802.11-19/0787r2, “802.11be Timeline Proposal”
[2] IEEE802.11-19/1259r1, “A cascading process for major amendments” https://mentor.ieee.org/802.11/dcn/18/11-18-1259-01-0000-a-cascading-process-for-major-amendments.pptx
[3] IEEE802.11-14/0649r1, “802.11ax Timeline Scenarios”
[4] IEEE802.11-18/0968r0, “TGax timeline”
[5] https://www.cnet.com/news/wi-fi-6-is-barely-here-but-wi-fi-7-is-already-on-the-way/
[6] https://www.u-blox.com/en/beyond/blog/guest-blogs/wi-fi-7-next-generation-wi-fi-technology