## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-20/145
Venue Date: | June 2020
First Author: | Michael Montemurro, BlackBerry
Subject: | REVmd Working Group Comments for PHY ad-hoc
Full Date: | 2020-06-18
Author(s): | Name(s) | Michael Montemurro
| Company | BlackBerry
Address
Phone:
Fax:
| email: | mmontemurro@blackberry.com
Abstract:
This document contains comments in the "PHY ad hoc" group, submitted on REVmd initial SA Ballot..

## Revision History
Revision | Date | Description
0 | 2020-01-13 | Initial revision
1 | 2020-01-16 | Updated based on initial comment assignments and comment resolution discussions.
2 | 2020-02-04 | Updated based on discussions up to the end of January - all comments assigned.
3 | 2020-02-20 | Updated based on discussions up to the February adhoc
4 | 2020-02-20 | Updated resolutions for 4270 and separate consideration for 4137
5 | 2020-02-21 | Updated based on 11md adhoc completion
6 | 2020-03-16 | Updated based on teleconferences up to and including March 13
7 | 2020-03-19 | Updated based on Mark Rison comments on CID 4326 and CID 4388
8 | 2020-04-16 | Updated based on comments resolved up to and including the April 8 telecon
9 | 2020-04-17 | Updated based on comments resolved and motioned up to and including the April 17 telecon
10 | 2020-05-06 | Updated based on comments resolved up to May 1. Created Review and Insufficient detail tabs.
11 | 2020-05-12 | Updated based on comments resolved up to May 8.
12 | 2020-06-18 | Updated based on comments resolved up to June 17

## PHY Motion F
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4338 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  | 4339 | V | Stephen McCann |  |  | We have both "GAS Query Request" and "GAS Query" but it is not clear how these differ | Throughout, change "GAS Query" not followed by "Request" or "Response" or "Fragment" to "GAS Query Request" | REVISED (PHY: 2020-05-15 15:21:36Z) - Incorporate the changes in document https://mentor.ieee.org/802.11/dcn/20/11-20-0654-03-000m-cid-4100-proposed-resolution.doc which clarify the terminology for specification of GAS query protocol requirements. | PHY | PHY Motion F | Ready for motion | PHY: 2020-05-15 15:26:22Z - status set to: Ready for motion PHY: 2020-01-14 23:00:36Z - status set to: Submission Required |  |  |  | 2020-05-15 15:26 | PHY
4703 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  |  | V | Mark Rison |  |  | There are some places that are poorly worded and suggest the EDCA Parameter Set element is not always provided at association in a QoS BSS | As it says in the comment | REVISED (PHY: 2020-05-20 21:42:22Z) - Incorporate the changes shown under "Discussion" for CIDs 4413 and 4703 in 11-20/0435r3 (https://mentor.ieee.org/802.11/dcn/20/11-20-0435-03-000m-resolutions-for-some-comments-on-11md-d3-0-sb1.docx), which address the issue raised by the commenter. | PHY | PHY Motion F | Ready for motion | PHY: 2020-05-20 21:42:25Z - status set to: Ready for motion PHY: 2020-01-14 19:39:44Z - status set to: Submission Required |  |  |  | 2020-05-20 21:43 | PHY
4462 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  |  | J | Mark Hamilton |  |  | "of all MSDUs and A-MSDUs buffered at the STA". A STA does not buffer A-MSDUs. The things it receives via MA-UNITDATA.request are MSDUs, and those are the things it buffers prior to transmission Change the cited text to "of all MSDUs buffered at the STA" | Delete "or A-MSDUs" in 9.2.4.1.8 More Data subfield (4x), 9.2.4.5.6 Queue Size subfield, 9.2.4.5.8 AP PS Buffer State subfield | REJECTED (PHY: 2020-05-27 21:28:42Z) - As described in the definition of bufferable unit (BU), and Figure 5-1’s flow of action for transmitted frames, aggregation into A-MSDUs occurs before the power buffering stage, and thus A-MSDUs are buffered. | PHY | PHY Motion F | Ready for motion | PHY: 2020-05-27 21:28:46Z - status set to: Ready for motion PHY: 2020-01-14 20:17:35Z - status set to: Submission Required |  |  |  | 2020-05-27 21:29 | PHY
4446 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  |  | A | Assaf Kasher |  |  | "AGC training field" -- no such field; should be "AGC field". Also should be "an AGC" not "a AGC" | As it says in the comment | ACCEPTED (PHY: 2020-05-13 20:51:06Z) Note to Editor: there are 6 instances. | PHY | PHY Motion F | Ready for motion | PHY: 2020-05-13 20:52:01Z - status set to: Ready for motion |  |  |  | 2020-05-13 20:53 | PHY
4445 | RISON, Mark | 1001 | 3 |  | 1011 | 8 | T | Yes | 1011 | 8 |  |  | V | Mark Hamilton |  |  | "For nonmesh STAs, the Channel Switch Count field either is set to the number of TBTTs until the STA sending the Channel Switch Announcement element switches to the new channel or is set to 0. (MDR2)A 1 indicates that the switch occurs immediately before the next TBTT. A 0 indicates that the switch occurs at any time after the frame containing the element is transmitted." is self-contradictory. If it switches before the next TBTT, the number of TBTTs until the switch was 0 | Change to "For nonmesh STAs, the Channel Switch Count field is set to the number of TBTTs until the STA sending the Channel Switch Announcement element switches to the new channel. (MDR2)1 indicates that the switch occurs immediately before the next TBTT. 0 indicates that the switch occurs at any time after the frame containing the element is transmitted." | REVISED (PHY: 2020-05-27 21:27:27Z) - Incorporate the changes for CID 4445 in doc 11-20/338r4 <https://mentor.ieee.org/802.11/dcn/20/11-20-0338-04-000m-revmd-initial-sa-comments-assigned-to-hamilton.docx> which resolves the comment in the direction suggested by the commenter. | PHY | PHY Motion F | Ready for motion | PHY: 2020-05-27 21:27:16Z - status set to: Ready for motion PHY: 2020-02-20 21:44:23Z - status set to: Discuss PHY: 2020-02-20 21:26:20Z - status set to: Ready for motion PHY: 2020-01-14 20:31:43Z - status set to: Discuss PHY: 2020-01-14 20:31:40Z - status set to: Needs submission |  |  |  | 2020-05-27 21:28 | PHY
4341 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  | 4340 | A | Mark Rison |  |  | There are still a lot of "MCS"es. These need to be qualified with the PHY, to avoid confusion, except in generic contexts (e.g. 10.6.6.5.2 Selection of a rate or MCS) | Throughout, change "S1G MCS" to "S1G-MCS", "CMMG MCS" to "CMMG-MCS" | ACCEPTED (PHY: 2020-05-13 21:08:15Z) | PHY | PHY Motion F | Ready for motion | PHY: 2020-05-13 21:08:14Z - status set to: Ready for motion PHY: 2020-01-14 22:57:16Z - status set to: Submission Required |  |  |  | 2020-05-13 21:08 | PHY
4721 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  |  | J | Michael Montemuro |  |  | The whole "field" v. "subfield" thing is just a big inconsistent mess (e.g. in 9.4.2.171 Reduced Neighbor Report element some things in the Neighbor AP Information field are fields and some are subfields, and the TBTT Information Set [sub!]field contains one or more TBTT Information fields). There is no value in trying to make the distinction, because (a) the distinction is not made reliably and (b) it's not possible to make the distinction, because some things are subfields of X but are also the field that contains subfield Y | Change "subfield" to "field" throughout | REJECTED (PHY: 2020-05-22 21:42:39Z) “subfield” is a field and indicates that it is a component of a field. It has its value and shall not globally replaced. The comment cannot be addressed as a single issue, or does not relate to a specific line, paragraph, figure, or equation in the balloted draft. | PHY | PHY Motion F | Ready for motion | PHY: 2020-05-25 12:44:06Z - status set to: Ready for motion PHY: 2020-05-13 21:59:39Z - This was discussed in WG balloting and it was decided that no change would be made. Emily to find the previous CID - Mike will review the prior discussion and see what we want to do. PHY: 2020-01-14 19:25:50Z - status set to: Submission Required |  |  |  | 2020-06-18 14:52 | PHY
4339 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  | 4338 | V | Stephen McCann |  |  | We have both "GAS Query Request" and "GAS Query" but it is not clear how these differ, and they don't seem to be frames anyway | Throughout, change "GAS Query" not followed by "Request" or "Response" or "Fragment" to "GAS query"; change "GAS Query Request" to "GAS query"; change "GAS Query Response" to "GAS query response" | REVISED (PHY: 2020-05-15 15:24:11Z) - Incorporate the changes in document https://mentor.ieee.org/802.11/dcn/20/11-20-0654-03-000m-cid-4100-proposed-resolution.doc which clarify the terminology for specification of GAS query protocol requirements. | PHY | PHY Motion F | Ready for motion | PHY: 2020-05-15 15:24:19Z - status set to: Ready for motion PHY: 2020-01-14 23:00:00Z - status set to: Submission Required |  |  |  | 2020-05-15 15:26 | PHY
4137 | Goodall, David | 1001 | 3 | 23.3.8.2.2.5 | 3370 | 6 | T | Yes | 3370 | 6 | 23.3.8.2.2.5 |  | J | Mark Rison | 11-20/244 |  | Why is bit 0 of the SIG-1 symbol of the short preamble reserved and set to 1 rather than 0? Is it reserved for future use or is it reserved for some other reason? If it will always be the value 1 then we can use it to further verify the short preamble signal field, which is protected by a weak CRC4. | Add a note saying why b0 of the S1G-1 symbol of the short preamble is reserved. | REJECTED (PHY: 2020-02-14 15:27:30Z) - To be specific, the Reserved SIG Indication is used as one of criteria in PHY receive procedure whether the PHY shall issue the error condition PHY-RXEND.indication(FormatViolation) in different amendments (e.g. 11ac, 11ah and 11ax) when its reserved bit set to 0. However, not to add the note - a proposed note is not necessary because 1) weak CRC4 is not a technical approach 2) when CRC8 is supported in 11ac, the bits are set to 1. | PHY | PHY Motion F | Ready for motion | PHY: 2020-06-18 15:00:10Z - status set to: Ready for motion PHY: 2020-02-20 20:40:20Z - status set to: Discuss PHY: 2020-02-14 15:27:50Z - status set to: Ready for motion Rejected. To be specific, the Reserved SIG Indication is used as one of criteria in PHY receive procedure whether the PHY shall issue the error condition PHY-RXEND.indication(FormatViolation) in different amendments (e.g. 11ac, 11ah and 11ax) when its reserved bit set to 0. However, not to add the note - a proposed note is not necessary because 1) weak CRC4 is not a technical approach 2) when CRC8 is supported in 11ac, reserved bits are still setting to 1. |  |  |  | 2020-06-18 15:01 | PHY
4325 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  |  | V | Mark Hamilton |  |  | "AC parameters" is not a defined thing; should be "EDCA parameters" (5x) | As it says in the comment | REVISED (PHY: 2020-05-27 21:31:11Z) - Incorporate the changes for CID 4325 in doc 11-20/338r4 <https://mentor.ieee.org/802.11/dcn/20/11-20-0338-04-000m-revmd-initial-sa-comments-assigned-to-hamilton.docx>which changes the 5 locations of AC parameters to announced EDCA. | PHY | PHY Motion F | Ready for motion | PHY: 2020-05-27 21:31:02Z - status set to: Ready for motion PHY: 2020-05-13 21:11:23Z - Mark Hamilton will prepare a submission. Rejection reason will be created if no submission is forthcoming. PHY: 2020-02-18 21:07:19Z - status set to: Submission Required More work required. |  |  |  | 2020-05-27 21:32 | PHY
4314 | RISON, Mark | 1001 | 3 | 12 |  |  | T | Yes |  |  | 12 |  | V | Mark Rison |  |  | "gives the current message number" (4x) -- the "message number" is not defined | Change "message number" to "TSC or PN" in each case | REVISED (PHY: 2020-06-10 22:05:18Z) - Incorporate the changes under “Proposed Changes:” for CID 4314 in https://mentor.ieee.org/802.11/dcn/20/11-20-0435-04-000m-resolutions-for-some-comments-on-11md-d3-0-sb1.docx | PHY | PHY Motion F | Ready for motion | PHY: 2020-06-10 22:05:21Z - status set to: Ready for motion PHY: 2020-05-13 21:15:52Z - Mark Rison to email Jouni and Dan with the proposed changes for their review. Mark will bring back a proposed resolution. PHY: 2020-01-14 23:03:27Z - status set to: Submission Required |  |  |  | 2020-06-10 22:06 | PHY
4301 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  |  | V | Mark Rison |  |  | "When MAX-ACCESS is read-only, the MIB attribute value may be updated by the PLME and read from the MIB attribute by management entities. When MAX-ACCESS is read-write, the MIB attribute may be read and written by management entities but shall not be updated by the PLME." has some odd numerology; specifically it only appears for PHYs in odd-numbered clauses above 20 | Add the cited text to the end of the PHY MIB subclause of the other PHYs | REVISED (PHY: 2020-05-20 21:19:33Z) - Relative to draft 3.2, add the following paragraph at 2868.34, 2896.35 [also fix the font size at 2896.30], 2954.20, 2966.62, 3124.21, and 3478.60: "When MAX-ACCESS is read-only, the MIB attribute value may be updated by the PLME and read from the MIB attribute by management entities. When MAX-ACCESS is read-write, the MIB attribute may be read and written by management entities but shall not be updated by the PLME." | PHY | PHY Motion F | Ready for motion | PHY: 2020-05-20 21:19:18Z - status set to: Ready for motion PHY: 2020-05-13 21:19:38Z - Mark Rison to provide a submission with detailed editing instructions with page and line numbers. PHY: 2020-01-14 23:06:58Z - status set to: Submission Required |  |  |  | 2020-05-20 21:22 | PHY
4224 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  |  | V | Ganesh Venkatesan |  |  | The units of MULTICHANNEL_SAMPLING_RATE are unclear. Sometimes it's sample/s, sometimes unitless. Since Annex P says the sampling rate is MULTICHANNEL_SAMPLING_RATE sample/s, MULTICHANNEL_SAMPLING_RATE itself should be unitless | Delete " sample/s" in 15.4.5.11 Time of Departure accuracy, 16.3.7.10 Time of Departure accuracy, 17.3.9.9 Time of Departure accuracy, 19.3.18.8 Time of Departure accuracy, 20.5.4.1.2 Time of Departure accuracy, 21.3.17.5 Time of Departure accuracy, 23.3.16.5 Time of Departure accuracy, 24.5.4.1.2 Time of departure accuracy, 25.5.7.1.3 Time of Departure accuracy, 25.6.9.2.3 Time of Departure accuracy | REVISED (PHY: 2020-05-20 20:37:02Z) - Change in Annex-P as shown in the paragraph at P4590L12-21 in D3.2. "The minimum sampling rate is MULTICHANNEL_SAMPLING_RATE sample/s respectively." to "The minimum sampling rate is MULTICHANNEL_SAMPLING_RATE expressed in sample/s." | PHY | PHY Motion F | Ready for motion | PHY: 2020-05-20 20:37:49Z - status set to: Ready for motion PHY: 2020-01-22 14:43:14Z - status set to: Submission Required |  |  |  | 2020-05-20 21:16 | PHY
4179 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  | 4178 | A | Mark Rison |  |  | A BSSID is a characteristic of a BSS, not of an AP/STA. So "BSSID of" should not refer to an an AP/STA | Change "BSSID of the target AP" to "BSSID of the target AP's BSS" throughout | ACCEPTED (PHY: 2020-05-13 21:48:54Z) Note to Editor: there are 19 instances. | PHY | PHY Motion F | Ready for motion | PHY: 2020-05-13 21:48:58Z - status set to: Ready for motion PHY: 2020-01-14 23:29:12Z - status set to: Submission Required |  |  |  | 2020-05-13 21:53 | PHY
4178 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  | 4179 | V | Mark Rison |  |  | A BSSID is a characteristic of a BSS, not of an AP/STA. So "BSSID of" should not refer to an an AP/STA | As it says in the comment | REVISED (PHY: 2020-06-18 14:48:06Z) Change "BSSID of the target AP" to "BSSID of the target AP's BSS" throughout. Note to Editor: there are 19 instances and this resolution is the same as CID 4179. | PHY | PHY Motion F | Submission Required | PHY: 2020-05-13 21:55:12Z - The comment is the same as CID 4179 but the resolution will be distinct. PHY: 2020-01-14 23:29:24Z - status set to: Submission Required |  |  |  | 2020-06-18 15:08 | PHY
4340 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  | 4341 | V | Mark Rison |  |  | There are still a lot of "MCS"es. These need to be qualified with the PHY, to avoid confusion, except in generic contexts (e.g. 10.6.6.5.2 Selection of a rate or MCS) | As it says in the comment | REVISED (PHY: 2020-06-18 14:50:55Z) Throughout, change "S1G MCS" to "S1G-MCS", "CMMG MCS" to "CMMG-MCS" Note to editor. The resolution to this CID is the same as CID 4341 | PHY | PHY Motion F | Submission Required | PHY: 2020-01-14 22:57:42Z - status set to: Submission Required |  |  |  | 2020-06-18 15:08 | PHY

## Review
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4286 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | It is not clear what the difference between 802.1X authentication and EAP authentication is. Jouni said "In the context of IEEE 802.11 standard, 802.1X authentication is really referring to EAP authentication, so these would also be interchangeable here" | Change "EAP authentication" to "802.1X authentication" throughout, except in the definition of IEEE 802.1X authentication and Extensible Authentication Protocol (EAP) reauthentication protocol (EAP-RP) and in the arrow label in Figure 4-31--IEEE 802.1X EAP authentication and Figure 4-37--Example using IEEE 802.1X authentication. Delete "EAP" in the caption of Figure 4-31--IEEE 802.1X EAP authentication and in Table 9-198--Transition and Transition Query reasons and in last para of 12.6.10.3 Cached PMKSAs and RSNA key management. Change "Successful completion of EAP authentication over IEEE Std 802.1X" to "Successful completion of IEEE Std 802.1X authentication" and "full EAP authentication via IEEE 802.1X authentication." to "full IEEE 802.1X authentication." |  | PHY | Review | Submission Required | PHY: 2020-05-13 21:25:24Z - Mark Rison to prepare a submission with the detailed changes. PHY: 2020-01-14 23:12:12Z - status set to: Submission Required |  |  |  | 2020-05-13 21:37 | PHY
4395 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  | 4394 |  | Mark Rison |  |  | There are ~11 instances of "current ESS", but this is not defined | Change each to "ESS of which the STA is a member" (if you accept STAs can be members of an ESS, not just of a BSS) |  | PHY | Review | Submission Required | PHY: 2020-05-13 21:03:06Z - Mark R to prepare a submission with the detailed changes and their rationale. If no submission, the comment will be rejected. PHY: 2020-01-14 22:48:59Z - status set to: Submission Required |  |  |  | 2020-05-13 21:05 | PHY
4423 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | How does a "duration time" or "time duration" differ from a "duration" | Change "duration time" and "time duration" to "duration" throughout |  | PHY | Review | Submission Required | PHY: 2020-05-13 20:56:25Z - Mark R to create a submission. If no submission is contributed, the comment will be rejected for the change suggested cannot be applied uniformly (or something similar). PHY: 2020-01-14 22:44:04Z - status set to: Submission Required |  |  |  | 2020-05-13 20:58 | PHY
4569 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Youhan Kim |  |  | The concept of a "normal control" has sprouted but is not well-defined | Change "Link Adaptation Per Normal Control Response Capable" to "Link Adaptation Without NDP CMAC PPDU Capable" throughout (5x) |  | PHY | Review | Submission Required | PHY: 2020-05-13 20:46:46Z - Assign to Youhan PHY: 2020-01-09 21:53:55Z - status set to: Submission |  |  |  | 2020-05-13 20:47 | PHY
4629 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  | 4630 |  | Mark Rison |  |  | "The RCPI encoding is defined in 15" should be referring directly to Clause 9, as in 16.3.8.6 Received Channel Power Indicator Measurement | Fix in 17.3.10.7 Received Channel Power Indicator Measurement and 20.3.10 Received channel power indicator (RCPI) measurement |  | PHY | Review | Submission Required | PHY: 2020-05-13 20:41:44Z - Mark Rison to provide detailed set of changes. If detailed changes are not submitted, this comment will be rejected for insufficient detail. CID 4630 is a related comment. PHY: 2020-01-14 19:55:51Z - status set to: Submission Required |  |  |  | 2020-05-13 20:43 | PHY
4710 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Youhan Kim |  |  | There are various references to "NDP frames" and "non-NDP frames". The first is a misnomer because NDPs are NDPs not frames; the second is pleonastic since all frames (MPDUs) are not NDPs | This appears to be some 11ah horror, so change all instances of "non-NDP frame" to "non-NDP-CMAC frame", all instances of "sounding NDP frame" to "sounding NDP", and all remainng instances of "NDP frame" to "NDP CMAC frame". Dieu reconnaitra les siens |  | PHY | Review | Submission Required | PHY: 2020-01-14 19:32:19Z - status set to: Submission Required |  |  |  | 2020-05-13 20:41 | PHY
4712 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | There are approximately 100 instances of "relay STA", of which approximately 58 are "S1G relay STA". This seems to falsely suggest that the others are or can be non-S1G relay STAs | Change all instances of "relay STA" and "Relay STA" that are not preceded by "S1G" or "DMG" to "S1G relay STA" throughout, adjusting the preceding indefinite article "a" if present to "an". Change all instances of "relay AP" and "Relay AP" that are not preceded by "S1G" or "DMG" to "S1G relay AP" throughout, adjusting the preceding indefinite article "a" if present to "an" |  | PHY | Review | Submission Required | PHY: 2020-05-13 20:30:55Z - Mark will provide a contribution with the page and line numbers indicated for the changes. If no submission is given, will craft a rejection reason. No specification for where the changes need to be made or their context. PHY: 2020-01-14 19:30:17Z - status set to: Submission Required |  |  |  | 2020-05-13 20:38 | PHY
4720 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | CID 1505 follow-up. There are still references to short/long retry count(er) in 10.3.3: "The SSRC shall be incremented when any short retry count (SRC)" "The SLRC shall be incremented when any long retry count (LRC)" and in 11.8.3 "The short retry counter and long retry counter for the MSDU or A-MSDU are not affected." Also "A STA shall maintain a SRC and an LRC for each MSDU or MMPDU awaiting transmission." "The SRC for an MPDU [...]. This SRC and the SSRC shall be reset when [...]. The LRC for an MPDU [...]. This LRC and the SLRC shall be reset when" "Retries for failed transmission attempts shall continue until the SRC for the MPDU [...] or until the LRC for the MPDU [...]" in 10.3.4.4. Note: DCF is not deprecated | Delete all references to short/long retry count(er)s throughout |  | PHY | Review | Submission Required | PHY: 2020-05-13 20:26:56Z - Assigned to Mark Rison. Submission required. If no submission is created, the CID will be rejected for insufficient details. PHY: 2020-05-08 15:06:18Z - Possible Rejection reason: 4719 - Rejected - It might be possible to delete words from the draft, but the result would not necessarily be consistent. The comment provides insufficient detail to make a complete change. PHY: 2020-02-20 22:08:19Z - status set to: Submission Required |  |  |  | 2020-05-13 20:28 | PHY
4756 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | There seem to be at least three flavours of awake window: mesh, TDLS and DMG (and there has been a suggestion in TGmd that there are also IBSS awake windows, though the term does not appear). The first seems to be so denoted, but the others not | Add "TDLS" or "DMG" before "awake window" where "mesh" is not present there |  | PHY | Review | Submission Required | PHY: 2020-05-13 20:22:12Z - Mark Rison to send Solomon an email to help get guidance on DMG. If there is no submission will be rejected for insufficient detail. PHY: 2020-01-14 18:51:51Z - status set to: Submission Required |  |  |  | 2020-05-13 20:23 | PHY

## Privacy
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4040 | Montemurro, Michael | 1001 | 3 | 12.6.10.3 | 2635 | 9 | T | Yes | 2635 | 9 | 12.6.10.3 |  |  | Michael Montemuro |  |  | During the development of REVmd, there was a proposal to allow PMKSA caching while a STA was changing its MAC address (see https://mentor.ieee.org/802.11/dcn/19/11-19-0586-07-000m-pmksa-caching-and-mac-randomization.docx). This proposal was not finalized. It would be desirable for this proposal to be completed in REVmd. | Submitter will create a contribution to define how PMKSA caching works while a STA is changing its MAC address. |  | PHY | Privacy | Submission Required | PHY: 2020-01-15 00:26:07Z - status set to: Submission Required |  |  |  | 2020-01-15 00:27 | PHY
4731 | RISON, Mark | 1001 | 3 | 9.4.2.216 |  |  | G | Yes |  |  | 9.4.2.216 |  |  | Dan Harkins | 11-20/0543r0 |  | The Password Identifier element is included in the unprotected authentication frame. It may violate the privacy of users (household). For example, it exposes a group of devices and number of devices that are sharing the same password. Particularly, when these devices belongs to the same household (apartment) in an apartment building, it violates the privacy of users/residents. | Delete the referenced subclause | The BRC could not come to consensus on technical changes to the draft that would address the privacy concerns stated by the commenter. | PHY | Privacy | Submission Required | PHY: 2020-05-29 15:52:59Z - status set to: Submission Required Reject reason (in case the motion fails). The BRC could not come to consensus on technical changes to the draft that would address the privacy concerns stated by the commenter. REVISED (PHY: 2020-05-06 21:55:49Z) Incorporate the changes in https://mentor.ieee.org/802.11/dcn/20/11-20-0543-02-000m-privacy-for-password-identifiers.doc which address the privacy issues with password identifiers. PHY: 2020-05-06 21:55:52Z - status set to: Ready for motion https://mentor.ieee.org/802.11/dcn/20/11-20-0543-01-000m-privacy-for-password-identifiers.docx GEN: 2020-03-28 15:38:57Z - status set to: Submission Required GEN: 2020-01-14 06:47:24Z - status set to: Discuss |  |  |  | 2020-06-18 15:05 | PHY

## Insufficient Details
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4739 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | Some work was done in TGmc to make the description of all the flavours and interactions of CS clearer, but this didn't come to fruition. It should be attempted again | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 19:15:03Z - status set to: Submission Required |  |  |  | 2020-04-30 21:00 | PHY
4818 | Torab, Payam | 1001 | 3 |  | 3824 | 27 | T | Yes | 3824 | 27 |  |  |  | Payam Torab |  |  | dot11Spectrum Mangement Required operation for DMG is incomplete. | Add DMG-specific missing pieces |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-09 21:40:07Z - status set to: Submission Link to 4817 |  |  |  | 2020-04-30 20:45 | PHY
4633 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | CID 2712 follow-up. Other things in the PHY clauses are stated "is identical" -- do these need fixing too? | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 19:54:08Z - status set to: Submission Required |  |  |  | 2020-04-30 21:19 | PHY
4635 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | Many places that refer to Action frames should also refer to Action No Ack frames (e.g. AC setting) | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 19:53:40Z - status set to: Submission Required |  |  |  | 2020-04-30 21:19 | PHY
4646 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | It seems possible "beacon interval" has multiple meanings. This needs to be clarified | See 19/0856 discussion and |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 19:53:13Z - status set to: Submission Required |  |  |  | 2020-05-06 14:16 | PHY
4686 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | There are multiple references to "the virtual CS mechanism", but there are multiple virtual CS mechanisms for S1G STAs (and maybe also DMG STAs), so which is intended is not clear | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 19:45:09Z - status set to: Submission Required |  |  |  | 2020-04-30 21:15 | PHY
4697 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | CID 2316 follow-up. Re "beacon interval", need to distinguish "from one TBTT to the next" and "from one beacon to the next TBTT" from "a duration equal to the time between TBTTs, that may start at any time" | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 19:41:31Z - status set to: Submission Required |  |  |  | 2020-04-30 21:11 | PHY
4699 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Menzo Wentink |  |  | "remaining TXOP duration" is not well-defined. Maybe it's just TXNAV? | As it says in the comment | The term "remaining TXOP duration" is used in several locations, and the meaning seems clear. It is the time remaining in the TXOP. The time remaining is not necessarily the TXNAV, which might cover only the response frame. | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 19:40:14Z - status set to: Submission Required |  |  |  | 2020-05-08 14:50 | PHY
4706 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | According to 18/1636r0, "There is no reference to dot11STACivicLocation in main body of the standard. The same thing apply to dot11STACivicLocationType. Furthermore, it seems that dot11STACivicLocationConfigTable is poorly defined and probably does not pass MIB compilation. In description of "dot11RMCivicConfigured", there is a reference to dot11STACivicLocationEntry. However, dot11STACivicLocationEntry is not defined anywhere." | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 19:36:06Z - status set to: Submission Required |  |  |  | 2020-05-06 14:16 | PHY
4630 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  | 4629 |  | Mark Rison |  |  | Actually, the PHY doesn't have to have any particular encoding for the RCPI. It should pass the RCPI in dB to the MAC, and let the MAC worry about how to encode it over the air | In all the PHY Received Channel Power Indicator Measurement subclauses, delete the reference to how the RCPI is encoded. In all the PHY TX/RXVECTOR tables, say that the RCPI is returned with 0.5 dB precision |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 19:55:07Z - status set to: Submission Required |  |  |  | 2020-06-18 14:56 | PHY
4714 | RISON, Mark | 1001 | 3 | 25.3.9.1 | 3504 | 5 | T | Yes | 3504 | 5 | 25.3.9.1 |  |  | Assaf Kasher |  |  | Table 25-7---Fields in the CMMG SIG field needs the same changes as made under CID 1351. However Assaf reports that it "requires (a lot of) more work because the scrambling is not mentioned in the encoding process." | Ask Assaf to kindly to the more work |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 19:29:31Z - status set to: Submission Required |  |  |  | 2020-04-30 21:02 | PHY
4613 | RISON, Mark | 1001 | 3 | 12.5.3.3.1 | 2602 | 22 | T | Yes | 2602 | 22 | 12.5.3.3.1 |  |  | Matthew Fischer |  |  | Significant differences remain between the encryption descriptions for PV0 under a) and PV1 under b). The asterisks below highlight them: 1) Increment the PN***, to obtain a fresh PN for each MPDU,*** so that the PN never repeats for the same temporal key. Note that retransmitted MPDUs are not modified on retransmission. v. 1) When the (Ed)sequence number of the MPDU is less than the previous (Ed)sequence number and satisfies the BPN update conditions in 12.5.3.3.6 (Construct CCMP header for PV1 MPDUs(11ah)) for that TID/ACI, increment the ***base*** PN so that the PN never repeats for the same temporal key ***and TID/ACI***. Note that retransmitted MPDUs are not modified on retransmission. 2) Use the fields in the MPDU header to construct the ***additional authentication data (AAD)*** for CCM. The CCM algorithm provides integrity protection for the fields included in the AAD. MPDU header fields that ***may*** change when retransmitted are muted by being masked to 0 when calculating the AAD. v. 2) Use the fields in the MPDU header to construct the AAD for CCM. The CCM algorithm provides integrity protection for the fields included in the AAD. MPDU header fields that ***might*** change when retransmitted are muted by being masked to 0 when calculating the AAD. 3) Construct the CCM nonce block from the PN, A2, and the priority value of the MPDU where A2 is MPDU Address 2. If the Type field of the Frame Control field is 10 (Data frame) and there is a QoS Control field present in the MPDU header, the priority value of the MPDU is equal to the value of the QC field TID (bits 0 to 3 of the QC field). If the Type field of the Frame Control field is 00 (Management frame)***,*** and the frame is a QMF, the priority value of the MPDU is equal to the value in the ACI subfield of the Sequence Number field. Otherwise, the priority value of the MPDU is equal to the fixed value 0. 4) Place the new PN and the key identifier into the 8-octet CCMP header. v. 3) Construct the CCMP header as defined in 12.5.3.3.6 (Construct CCMP header for PV1 MPDUs(11ah)). If the Type field of the Frame Control field is 001 (Management frame) and the frame is a QMF, the priority value of the MPDU is equal to the value in the ACI subfield of the Sequence Number field. Otherwise, the priority value of the MPDU is equal to the fixed value 0. 4) Construct the CCM nonce block from the PN, the A2, and the ***Priority field of the MPDU*** where A2 is ***the STA MAC address identified by*** MPDU Address 2. | Align the wording for a) and b), and also align with the wording for GCMP |  | PHY | Insufficient Details | Submission Required |  |  |  |  | 2020-05-06 14:16 | PHY
4743 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | There are references to "physical carrier sense", "virtual carrier sense" and "physical CS" and "virtual CS" but the terms are never defined. Use "CS" rather than "carrier sense" except when defined etc. The terms PHYCS and PHYED are defined but barely used. There is a zoo of inconsistent terminology for "carrier sense", whch makes it hard to understand exactly what is meant where and how the various PHYs compare: CS, CCA, CS/CCA, energy detect, ED, PHYED, CCA-ED, CCA Mode 1-5. "CCA-ED" just confuses everyone, because everyone thinks it means CCA using ED, when in fact it means some wacko mode of operation in wacky regulatory domains/bands. There are also issues of editorial and technical consistency between the PHYs. | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 19:03:30Z - status set to: Submission Required |  |  |  | 2020-04-30 20:59 | PHY
4747 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | It is not clear whether the SME picks the Key ID for transmission of encrypted frames (using the Key ID parameter of the MLME-SETKEYS.request) or whether the MAC does so. Additionally there are various issues with the security pseudocode | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 19:01:48Z - status set to: Submission Required |  |  |  | 2020-05-06 14:16 | PHY
4749 | RISON, Mark | 1001 | 3 | 12 |  |  | T | Yes |  |  | 12 |  |  | Mark Rison |  |  | As a follow-up to CID 7572 in mc, I got the following input from Jouni MALINEN: In 12.9.2.2, MLME-SETPROTECTION.request is supposed to apply to _all_ keys. The only MSDU that this "transmit without protections" case could apply to is an EAPOL frame that is used to carry either EAP authentication of 4-way handshake prior the initial key configuration in an association. There is no group-addressed MSDU that could be sent out unprotected in a BSS that has RSN enabled. That said, clearly the GTK cases are not fully covered in the current standard. Interestingly, IGTK is actually covered in 11.13. The last paragraph of 12.6.14 should really point out that MLME-SETPROTECTION.request is used with GTK. 12.7.11.1 (Authenticator key management state machine) Figure 12-52 has interesting MLME-SETPROTECTION.request(TA, Rx_Tx) use in the REKEYESTABLISHED state for GTK and Figure 12-53 SETKEYSDONE uses MLME-SETPROTECTION.request(Rx_Tx, IGTK), but nothing similar for GTK. This does not really make any sense for GTK. It should also be covered in SETKEYSDONE and there should be no TA in the parameters (the Address parameter within Protectlist is not used for Key Type = Group case) and ProtectType should be Tx for an AP (and actually, also for IBSS, since there is separate Tx key for each STA). That Rx_Tx for IGTK is also incorrect (should be Tx). | Address all the issues raised in the comment in the way described in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 18:58:11Z - status set to: Submission Required |  |  |  | 2020-05-06 14:16 | PHY
4750 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | Discussions related to CID 7592 and 7593 in mc have revealed that the description of legacy PS and U-APSD is hopelessly muddled in terms of things like how PS-Polls operate for U-APSD and duplication of statements and consistency of description | Refactor the wording |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 18:56:22Z - status set to: Submission Required |  |  |  | 2020-04-30 20:51 | PHY
4751 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | The distinctions made in the specification w.r.t. TS/TC/TSID/TID are incomprehensible | Make the definitions comprehensible. E.g. what does "UP for either TC or TS" mean? |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 18:55:45Z - status set to: Submission Required |  |  |  | 2020-04-30 20:51 | PHY
4753 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | The description of the PHYCONFIG_VECTOR is missing for DSSS, HR/DSSS, ERP, DMG and TVHT | Add such a description |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 18:54:50Z - status set to: Submission Required |  |  |  | 2020-04-30 20:51 | PHY
4755 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | There are millions of MIB variables/tables to do with LCIs and civic locations, and it is not clear which are used in which contexts (TVWS, DSE, FTM, neighbour report, etc.) | Add some words to the parent MIB node to disambiguate them all (including the way in which/why an index is used, where an index is used) |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 18:52:23Z - status set to: Submission Required |  |  |  | 2020-04-30 20:51 | PHY
4759 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | It is not clear what a "Receive IGTK SA" is. Such a SA is not described in 12.6.1.1. Jouni has suggested that "Receive IGTK SA" was trying to refer to the IGTKSA used for receiving frames from the specific peer in MBSS. 12.6.1.1 does not define this, but it does have Mesh GTKSA (and Mesh GTKSA description in 12.6.1.1.10 mentions "transmit mesh GTKSA" and "receive mesh GTKSA"). Maybe a Mesh IGTKSA should be defined similarly to this. Or simply talk about IGTKSA (of which there would be zero or more for each peer). It should be noted that the existing sentence is this paragraph talks about "Receive MGTK SA" (which is not described in 12.6.1.1, but is mentioned in its subclause 12.6.1.1.10). The comment proposed language that is similar to that for the "Receive ... SA" part | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 18:50:56Z - status set to: Submission Required |  |  |  | 2020-04-30 20:47 | PHY
4711 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | We should not refer to PPDUs as frames, since this is needlessly confusing. "frame" should be a synonym for "MPDU" only | Change all references to "frame"s that are in fact PPDUs to "PPDU" |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 19:31:43Z - status set to: Submission Required |  |  |  | 2020-05-06 14:16 | PHY
4394 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  | 4395 |  | Mark Rison |  |  | There are ~11 instances of "current ESS", but this is not defined | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 22:49:37Z - status set to: Submission Required |  |  |  | 2020-04-30 21:35 | PHY
4227 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | Mark HAMILTON claims we need a definition of "minimum/receive/receiver sensitivity" | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 23:19:18Z - status set to: Submission Required |  |  |  | 2020-04-30 21:47 | PHY
4260 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | "existing"/"established" is usually otiose when it refers to agreements, BSSes, etc. since behaviour is generally about the present, not the past or future | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 23:15:16Z - status set to: Submission Required |  |  |  | 2020-05-06 14:16 | PHY
4266 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | It should be clearer that it is not possible to change the basic rate/MCS set for the lifetime of the BSS | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-05-13 21:39:45Z - Mark Rison to prepare a submission. Move to Insufficient detail. PHY: 2020-01-14 23:14:45Z - status set to: Submission Required |  |  |  | 2020-05-13 21:40 | PHY
4277 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | We have all of "BA session" (4x), "block ack session" (17x), "BlockAck session" (4x) (and none are defined) | Change all to "block ack session" and define the term |  | PHY | Insufficient Details | Submission Required | PHY: 2020-05-13 21:37:09Z - Mark Rison to prepare a submission. If a submission is not forthcoming, the comment will be tagged for insufficient detail. PHY: 2020-01-14 23:12:45Z - status set to: Submission Required |  |  |  | 2020-05-13 21:39 | PHY
4293 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | Referring to fields in binary is not clear as to the ordering of bits. E.g. it is not clear what PPDU Type = 10 or 01 refers to, but there are other instances | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-05-13 21:22:41Z - Mark R to prepare a submission with editing instructions. Move to Insufficent Details. PHY: 2020-01-14 23:09:32Z - status set to: Submission Required |  |  |  | 2020-05-13 21:23 | PHY
4298 | RISON, Mark | 1001 | 3 | 19 |  |  | T | Yes |  |  | 19 | 4299 |  | Mark Rison |  |  | It is confusing that a non-HT preamble is just STF+LTF while an HT preamble also includes SIG fields | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-05-13 21:21:19Z - Similar to CID 4299. Mark Rison to prepare a submission with a detailed resolution. Move to insufficient details. PHY: 2020-01-14 23:08:16Z - status set to: Submission Required |  |  |  | 2020-05-13 21:22 | PHY
4299 | RISON, Mark | 1001 | 3 | 19 |  |  | T | Yes |  |  | 19 | 4298 |  | Mark Rison |  |  | "preamble" should really only be STF+LTF, but the HT one includes SIG fields. Maybe call the one with SIG fields the "PHY header"? | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 23:07:52Z - status set to: Submission Required |  |  |  | 2020-05-06 14:16 | PHY
4310 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | Cf. 19/0336 on CIDs 2709-2711: it would be better for "preamble" to consistently mean "just the STFs and LTFs, not including SIGNAL", for all PHYs | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 23:05:35Z - status set to: Submission Required |  |  |  | 2020-04-30 21:40 | PHY
4632 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | CID 2177 follow-up. RSSI RXVECTOR param units should be specified. Some but not all PHYs say "RSSI is intended to be used in a relative manner, and it shall be a monotonically increasing function of the received power" but even for those PHYs it is not clear what the use of something that has no units is | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 19:54:30Z - status set to: Submission Required |  |  |  | 2020-05-06 14:16 | PHY
4366 | RISON, Mark | 1001 | 3 | 12.7.6.2 | 2671 | 25 | T | Yes | 2671 | 25 | 12.7.6.2 |  |  | Mark Rison |  |  | Message 1 uses the following values for each of the EAPOL-Key frame fields:" -- "Key Data = PMKID for the PMK being used during PTK generation(#59)" -- Jouni said in Vienna that it can contain other stuff, and that it should be referring to PMKID KDE. Also, should have general statement for all the Key Data = lines to say this is the minimum set of things that need to be included in the message, but other stuff (e.g. VS) may also be included | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-15 00:55:51Z - status set to: Submission Required |  |  |  | 2020-04-30 21:35 | PHY
4220 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | The Timestamp field rule ("value of the STA's TSF timer at the time that the data symbol containing the first bit of the Timestamp field appears at the transmit antenna connector" or similar) is mentioned for S1G beacon (twice), PV1 probe rsp, probe rsp, beacon, DMG beacon, announce, timing advertisement but not for TIM frames | Add something to give the same rule for TIM frames as for (normal) beacons (and also for any other frames with a Timestamp field whose contents are not clearly specified) |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 23:22:53Z - status set to: Submission Required |  |  |  | 2020-04-30 21:49 | PHY
4399 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | Constructs of the form "may do X by doing Y" are ambiguous because the might mean "if you do X, then Y might happen" or "if you do X, then Y will happen" | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 22:48:20Z - status set to: Submission Required |  |  |  | 2020-04-30 21:33 | PHY
4453 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | "The QoS Action field is defined in 9.6.3.1 (General). representing ADDTS Reserve Response. The (#2110)Higher Layer Stream ID element is defined in 9.4.2.124 (Higher Layer Stream ID element). The Status Code field is defined in 9.4.1.9 (Status Code field)." is too vague. Needs to refer to specific contents. Similarly in other locations | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 20:28:59Z - status set to: Submission Required |  |  |  | 2020-04-30 21:30 | PHY
4477 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | PHY-RXEND.ind is defined to be sent after any signal extension (" When a Signal Extension is present, the primitive is generated at the end of the Signal Extension."; "When receiving a signal extended PPDU, the PHY- RXEND.indication primitive shall be emitted a period of aSignalExtension after the end of the last symbol of the PPDU."). So the PHY receive procedures need to show the PHY-RXEND.ind as being after the SE | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-09 22:22:28Z - status set to: Submission |  |  |  | 2020-05-06 14:16 | PHY
4523 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | Text about "channel starting frequency" sometimes does not give the units (e.g. in 20.3.1), and is inconsistent as to case of channel, italicisation (e.g. none in 17.3.8.4.2), and presence of article | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-05-13 20:47:59Z - Mark R to prepare a submission with editing instructions. If no submission, the comment will be rejected for insufficient details. PHY: 2020-05-13 20:47:45Z - PHY: 2020-01-09 22:16:41Z - status set to: Submission |  |  |  | 2020-05-13 20:49 | PHY
4525 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | An ax comment said "W.r.t. dynamic defragmentation, it is mentioned that a recipient STA shall discard incomplete fragments when receiving a BlockAckReq to move the BA window. When the STA receives a DELBA to tear down the BA agreement, the STA should/shall do the same". The requirement to discard incomplete fragments on receiving a BAR that moves the window or a DELBA needs to be captured | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-09 22:15:41Z - status set to: Submission |  |  |  | 2020-05-06 14:16 | PHY
4527 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | The concept of a frame being "protected" is used without being defined | Define a protected frame as a frame that is authenticated and/or encrypted |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-09 22:14:44Z - status set to: Submission |  |  |  | 2020-04-30 21:27 | PHY
4598 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | Do the rules on permissible transmission using optional feature Foo also need conditioning on dot11FooActivated? An example of where this is done is "An HT STA shall not transmit a frame in a PSDU with the TXVECTOR parameter(#2639) FORMAT set to HT_MF or HT_GF and TXVECTOR parameter FEC_CODING set to LDPC_CODING unless the RA of the frame corresponds to an HT STA for which the LDPC Coding Capability subfield of the HT Capabilities element received from that STA contained a value of 1 and dot11LDPCCodingOptionActivated is true (if there is more than one intended receiver, then this requirement applies for each intended receiver)." | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-09 21:47:35Z - status set to: Submission |  |  |  | 2020-05-06 14:16 | PHY
4602 | RISON, Mark | 1001 | 3 | 12 |  |  | T | Yes |  |  | 12 |  |  | Mark Rison |  |  | There is confusion (cf. CID 2137 I think) about the general concept of a temporal key, and the temporal key (TK) in PTKs (Jouni is adamant they are not the same) | As it says in the comment |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-22 15:23:37Z - status set to: Submission Required |  |  |  | 2020-05-06 14:16 | PHY
4363 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Mark Rison |  |  | The use of "or both" (57x) implies that uses of "or" without and "or both" are exclusive, but this is not the case | Delete "or both" throughout |  | PHY | Insufficient Details | Submission Required | PHY: 2020-01-14 22:53:38Z - status set to: Submission Required |  |  |  | 2020-04-30 21:35 | PHY

## DMG
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4238 | RISON, Mark | 1001 | 3 | 20.9.2.2.3 | 3132 | 28 | T | Yes | 3132 | 28 | 20.9.2.2.3 | 4239 |  | Assaf Kasher |  |  | "A value of 0 in the PPDU Type(#1379) field and a value of 0 in the Beam Tracking Request field indicate a BRP-RX PPDU(#1379)." is not clear. It might mean that either condition makes a PPDU into a BRP-RX PPDU, or that both conditions need to be met | Change to "A value of 0 in both the PPDU Type(#1379) field and the Beam Tracking Request field indicates a BRP-RX PPDU(#1379)." |  | PHY | DMG | [5 empty] | 2020-04-30 21:47 | PHY
4239 | RISON, Mark | 1001 | 3 | 20.9.2.2.3 | 3132 | 28 | T | Yes | 3132 | 28 | 20.9.2.2.3 | 4238 |  | Assaf Kasher |  |  | "A value of 0 in the PPDU Type(#1379) field and a value of 0 in the Beam Tracking Request field indicate a BRP-RX PPDU(#1379)." is not clear. It might mean that either condition makes a PPDU into a BRP-RX PPDU, or that both conditions need to be met | Change to "A value of 0 in both the PPDU Type(#1379) field indicates a BRP-RX PPDU(#1379). A value of 0 in the Beam Tracking Request field indicates a BRP-RX PPDU(#1379)." |  | PHY | DMG | [5 empty] | 2020-04-30 21:47 | PHY
4463 | RISON, Mark | 1001 | 3 | 20.3.5.1 | 3097 | 33 | T | Yes | 3097 | 33 | 20.3.5.1 |  |  | Assaf Kasher |  |  | "Tc (SC)" -- the "(SC)" is spurious | Delete the "(SC)". Also at 3462.61 |  | PHY | DMG | Discuss | PHY: 2020-01-14 20:16:49Z - status set to: Discuss |  |  |  | 2020-01-15 22:06 | PHY
4692 | RISON, Mark | 1001 | 3 | 20 |  |  | T | Yes |  |  | 20 |  |  | Assaf Kasher |  |  | CID 2036 follow-up, are the 128s in Figures 20-4/8 correct | As it says in the comment |  | PHY | DMG | [5 empty] | 2020-04-30 22:00 | PHY
4693 | RISON, Mark | 1001 | 3 | 24 |  |  | T | Yes |  |  | 24 |  |  | Assaf Kasher |  |  | CID 2036 follow-up, are the 128s in Figures 24-2/5 correct? | As it says in the comment |  | PHY | DMG | Submission Required | PHY: 2020-01-14 19:44:02Z - status set to: Discuss |  |  |  | 2020-04-30 22:00 | PHY

## HT-VHT
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4296 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Youhan Kim |  |  | There are references to "HT training" and "non-HT training fields" and "HT-Training" and "HT-Training part I". Ditto "VHT training" | At the end of 19.3.9.3.1 add a para "The HT training fields are the HT-STF and HT-LTF fields.". In Figure 19-23 add " Part II" after the middle "HT-Training". In Figure 19-24 add " Part II" after the "HT-Training" at line 20 and change "TX HT Training Symbols" to "TX HT Training". At the end of 21.3.8.3.1 Introduction add a para "The VHT training fields are the VHT-STF and VHT-LTF fields.". In 21.3.19 PHY transmit procedure change first "VHT Training Symbols" to "VHT training" and second to "of symbols for the VHT training". In Figure 21-34--PHY transmit procedure for SU transmission change "VHT Training Symbols" to "VHT-Training". In Figure 21-35--PHY transmit state machine for SU transmission change "TX VHT Training Symbols" to "TX VHT Training". In 21.3.20 PHY receive procedure change "receiving the VHT training symbols" to "receiving the VHT training" |  | PHY | HT-VHT | Discuss | PHY: 2020-04-30 21:42:02Z - status set to: Discuss |  |  |  | 2020-04-30 21:43 | PHY

## Legacy PHY
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4538 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Youhan Kim |  |  | There are references to "data part"s (with various capitalisations) but this term is not defined | Change "data part" (case-insensitively) to "Data field" throughout, except in Clause 17 where it should be "DATA field" |  | PHY | Legacy PHY | Submission Required | PHY: 2020-01-09 22:00:24Z - status set to: Submission |  |  |  | 2020-01-15 23:27 | PHY

## MAC
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4682 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  | 4683 |  | Graham Smith |  |  | The RTT as defined and used is not an RTT, it's a ToF. Calling it an RTT confuses it with a different (less accurate) approach to measuing range, sometimes called 1-sided RTT | Change "RTT" to "ToF" and "round trip time" to "time of flight" throughout. Change "an RTT" to "a ToF" in Figure 11-37 |  | PHY | MAC | Submission Required | PHY: 2020-01-14 19:47:55Z - status set to: Submission Required |  |  |  | 2020-04-30 21:17 | PHY
4683 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  | 4682 |  | Graham Smith |  |  | The RTT as defined and used is not an RTT, it's a ToF. It has been argued that the term RTT is (mis)used in a "popular OS implementation", but there is more than one popular OS implementation, and in any case terminology misuse by an implementation, however popular, is not a justification for perpetuating an error | Change "RTT" to "ToF" and "round trip time" to "time of flight" throughout. Change "an RTT" to "a ToF" in Figure 11-37 |  | PHY | MAC | Submission Required | PHY: 2020-02-20 21:55:30Z - Straw poll the resolution during the March meeting. PHY: 2020-01-14 19:46:14Z - status set to: Submission Required |  |  |  | 2020-04-30 21:17 | PHY
4694 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Graham Smith |  |  | "the BSS with which the STA is associated " (8x) -- STAs are associated with APs, not with BSSes. They are members of BSSes | As it says in the comment |  | PHY | MAC | Discuss | Graham to post updated resolution. Mark and Mark to review. PHY: 2020-01-14 19:42:13Z - status set to: Discuss |  |  |  | 2020-02-20 22:07 | PHY

## Obsolete
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4438 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  | 4439 |  | Graham Smith | 11-20/650 |  | There are no implementations of HT-delayed BA. HT-delayed BA is not useful, as it impairs throughput. Note: hypothetical use of HT-delayed BA by amendments to 802.11-202x is not relevant to REVmd | Delete the HT-delayed BA feature |  | PHY | Obsolete | Submission Required | PHY: 2020-01-16 22:57:24Z - status set to: Needs submission PHY: 2020-01-14 20:33:13Z - status set to: Discuss |  |  |  | 2020-06-05 15:30 | PHY
4439 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes |  |  |  | 4438 |  | Graham Smith | 11-20/650 |  | There are no implementations of HT-delayed BA. HT-delayed BA is not useful, as it impairs throughput. Note: hypothetical use of HT-delayed BA by amendments to 802.11-202x is not relevant to REVmd | Delete 10.25.7 HT-delayed block ack extensions | Incorporate the changes in documeent https://mentor.ieee.org/802.11/dcn/20/11-20-0650-01-000m-cids-4438-4439-delete-ht-delayed-block-ack.docx which resolve the comment in the direction proposed by the commenter. | PHY | Obsolete | Submission Required | PHY: 2020-01-16 22:54:25Z - status set to: Submission Required PHY: 2020-01-14 20:32:10Z - status set to: Discuss |  |  |  | 2020-06-05 15:29 | PHY
4513 | RISON, Mark | 1001 | 3 | 19.3.11.11.5 | 3043 | 25 | T | Yes | 3043 | 25 | 19.3.11.11.5 |  |  | Youhan Kim |  |  | 40 MHz non-HT duplicate and HT-MCS 32 will both achieve 3 dB power gain; typically, non-HT will have better PER performance because the L-LTF density [xxft] | Deprecate HT-MCS 32 |  | PHY | Obsolete | Submission Required | PHY: 2020-01-09 22:19:13Z - status set to: Submission |  |  |  | 2020-01-15 23:23 | PHY

## S1G
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4466 | RISON, Mark | 1001 | 3 | 12.5.3.3.1 | 2603 | 24 | T | Yes | 2603 | 24 | 12.5.3.3.1 |  |  | Matthew Fischer |  |  | "Otherwise, the priority value of the MPDU is equal to the fixed value 0." -- it should be derived from the TID (in the PTID/Subtype subfield field) | As it says in the comment |  | PHY | S1G | Submission Required | PHY: 2020-01-09 22:29:03Z - status set to: Discuss |  |  |  | 2020-01-22 19:36 | PHY
4611 | RISON, Mark | 1001 | 3 | 12 | 2609 | 5 | T | Yes | 2609 | 5 | 12 | 4612 |  | Mark Rison |  |  | "4) The nonce(#1406) value is constructed from the STA MAC Address Identified By A2, PN, and Nonce Flags fields." is just duplication of Figure 12-21--Nonce field. Ditto duplication of Figure 12-28--Nonce field for GCMP | Delete the cited text, and "3) (11ah)The nonce(#1406) value is constructed from the A2, PN, and Nonce Flags fields." in 12.5.3.4.1 and "c) The nonce(#1406) value is constructed from the A2 and PN fields." in 12.5.5.4.1 |  | PHY | S1G | Submission Required |  |  |  |  | 2020-06-03 20:54 | PHY
4614 | RISON, Mark | 1001 | 3 | 12.5.3.3.4 | 2606 | 37 | T | Yes | 2606 | 37 | 12.5.3.3.4 |  |  | Matthew Fischer |  |  | "(11ah)STA MAC Address Identified By A2 field occupies octets 1-6. This shall be encoded with the octets ordered with (11ah)STA MAC Address Identified By A2 octet 0 at octet index 1 and (11ah)STA MAC Address Identified By A2 octet 5 at octet index 6." says nothing of value, but omits the key point of what the field actually contains | Change to "The STA MAC Address Identified By A2 field contains the Address 2 field from the PV0 MPDU or the address derived from the A2 field from the PV1 MPDU (see 9.8.3.2)." |  | PHY | S1G | Submission Required | PHY: 2020-01-14 19:56:43Z - status set to: Discuss |  |  |  | 2020-01-22 19:36 | PHY

## SAE
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4546 | RISON, Mark | 1001 | 3 | 12.4.6 | 2575 | 54 | T | Yes | 2575 | 54 | 12.4.6 |  |  | Dan Harkins |  |  | "Encoding of the Anti-Clogging Token field(#2534) and its placement with respect to the peer-commit-scalar and PEER-COMMIT-ELEMENT is described in 12.4.7.4 (Encoding and decoding of SAE Commit messages)." -- no, the placement is described in Table 9-42--Authentication frame body | As it says in the comment |  | PHY | SAE | Submission Required | PHY: 2020-01-09 21:58:45Z - status set to: Submission PHY: 2020-01-09 21:58:26Z - status set to: Submission |  |  |  | 2020-01-15 23:11 | PHY
4669 | RISON, Mark | 1001 | 3 | 12.4.4.2.3 | 2569 | 30 | T | Yes | 2569 | 30 | 12.4.4.2.3 |  |  | Dan Harkins |  |  | "All operations in the SSWU algorithm shall be done in constant time. " is already stated, so CSEL and CEQ don't have to say it (indeed, this would suggest that maybe other operations such as multiplication do not have to be in constant time) | Delete "operates in constant time and " (2x) |  | PHY | SAE | [5 empty] | 2020-01-15 23:11 | PHY
4671 | RISON, Mark | 1001 | 3 | 12.4.4.3.3 | 2571 | 13 | T | Yes | 2571 | 13 | 12.4.4.3.3 |  |  | Dan Harkins |  |  | "the SAE hash-to-PWE bit" - no such bit, and they're called subfields anyway. And set to what? | Change to "to 1 the SAE hash-to-element subfield". In 12.4.4.2.2/3 change "indicate support for the SAE hash-to-element in its Extended RSN Capabilities field" to "set the SAE hash-to-element subfield in its Extended RSN Capabilities field to 1". In 12.4.4.2.3 change "setting the SAE hash-to-element bit in the Extended RSN Capabilities field" to "setting to 1 the SAE hash-to-element subfield in the Extended RSN Capabilities field" |  | PHY | SAE | [5 empty] | 2020-04-03 15:02 | PHY

## Security
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4049 | Qi, Emily | 1001 | 3 | 12.7.2 | 2660 | 9 | T | No | 2660 | 9 | 12.7.2 |  |  | Emily Qi | 11-20/247 |  | The Key Description Version field is a 2-bits field, which can indicate 3 "old" combinations. However, with the introduction of new AKMs for GCMP-128, GCMP-256, FILS, FILS+FT, there are additional combinations. Suggest using 2 reserved bits (bit 4 and bit 5) to indicate additional combinations. | If the direction is agreed, the commenter will provide a submission for the comment resolution. |  | PHY | Security | Submission Required | Incorporate the changes in https://mentor.ieee.org/802.11/dcn/20/11-20-0247-01-000m-initial-sb-proposed-resolutions-for-bp-comments.doc under Proposed Resolution for CID 4049. PHY: 2020-01-15 00:24:01Z - status set to: Submission Required |  |  |  | 2020-02-14 16:37 | PHY
4050 | Qi, Emily | 1001 | 3 | 11.3.5.3 | 2234 | 16 | T | Yes | 2234 | 16 | 11.3.5.3 |  |  | Emily Qi |  |  | Bullet e (Line 16 to Line 47) describes a procedure of using SA Query to check whether the STA has an active security association with the AP or not. This procedure is within the association process. Starting with SAE, FT and FILS Authentication, the Authentication process has major impact on the current key material and if initiated when not really needed it will cause the real STA to lose sync with the security material, which will result with disconnection, i.e. a very simple DOS attack. A much more efficient approach would have been to start the SA Query mechanism at an earlier stage, i.e. immediately following the SAE Authentication Request, instead of waiting for the (Re)Association-Request. | The commenter will provide a submission for the comment resolution. |  | PHY | Security | Submission Required | PHY: 2019-12-20 16:27:51Z - status set to: Submission Required |  |  |  | 2020-02-03 16:25 | PHY
4087 | Chitrakar, Rojan | 1001 | 3 | 12.5.3.4.1 | 2608 | 25 | T | No | 2608 | 25 | 12.5.3.4.1 |  |  | Mark Rison | 11-20/407 |  | As per 12.5.3.3 (P2607L59), the MIC is also encrypted along with the plaintext MPDU, so it is not possible to obtain the original MIC at this stage. The original MIC can only be obtained after CCM decryption stage. The figure 12-23 is misleading, either it should be clarified that the MIC that is fed into the CCM decryption block is encrypted MIC, or the entire encrypted MPDU (instead of MIC and data) should be passed to the CCM decryption block. | Rectify the Figure 12-23 as per comment. Specifically, the MIC that is fed into the CCM decryption module should be "encrypted MIC" | Incorporate the changes in https://mentor.ieee.org/802.11/dcn/20/11-20-0435-03-000m-resolutions-for-some-comments-on-11md-d3-0-sb1.docx under "Proposed Changes" for CID 4087 which address the comment in the direction proposed by the commenter. | PHY | Security | Submission Required | PHY: 2020-05-29 14:42:15Z Reviewed proposed resolution in https://mentor.ieee.org/802.11/dcn/20/11-20-0435-03-000m-resolutions-for-some-comments-on-11md-d3-0-sb1.docx There is no consensus on the direction or the proposed changes. Potentially add a note with details and map things normatively to the reference specification. |  |  |  | 2020-05-29 15:01 | PHY
4612 | RISON, Mark | 1001 | 3 | 12 | 2609 | 5 | T | Yes | 2609 | 5 | 12 | 4611 |  | Mark Rison |  |  | "4) The nonce(#1406) value is constructed from the STA MAC Address Identified By A2, PN, and Nonce Flags fields." is just duplication of Figure 12-21--Nonce field. Ditto duplication of Figure 12-28--Nonce field for GCMP | Replace the cited text, and "3) (11ah)The nonce(#1406) value is constructed from the A2, PN, and Nonce Flags fields." in 12.5.3.4.1 and "c) The nonce(#1406) value is constructed from the A2 and PN fields." in 12.5.5.4.1, with references to the figures. Also remove the "The Nonce field has an internal structure of Nonce Flags ¦¦ (11ah)STA MAC Address Identified By A2 ¦¦ PN" and "The Nonce field has an internal structure of A2 ¦¦ PN" duplication (of figures immediately above!) |  | PHY | Security | Submission Required | PHY: 2020-05-29 15:22:28Z Discussed resolution in https://mentor.ieee.org/802.11/dcn/20/11-20-0435-03-000m-resolutions-for-some-comments-on-11md-d3-0-sb1.docx. Consensus is that the direction of the resolution is correct. Check the status of management frames for PV1. |  |  |  | 2020-06-03 20:54 | PHY
4728 | RISON, Mark | 1001 | 3 |  |  |  | T | Yes | [5 empty] | Nehru Bhandaru |  |  | "To prevent key reinstallation attacks, a non-AP STA in which dot11WNMSleepModeActivated is true shall maintain a copy of the most recent GTK and most recent IGTK " -- should not quadruplicate this statement, even less so with variant wordings. We did not duplicate the statement for the original KRACK fix (this point was ignored in the resolution of CID 2551) | In 11.2.3.16.1, 12.7.7.4, 12.12.2.1, 13.5.1 delete the para starting (#1321) and replace it with "NOTE---See 6.3.19 regarding prevention of key reinstallation attacks." |  | PHY | Security | Submission Required |  |  |  |  | 2020-02-18 17:51 | PHY