## Slide 1: Status of the comments-on-fcc19-138-nprm-revisiting-use-of-the-5-850-5-925-ghz-band
Date: 2020-02-18
Authors:

## Slide 2: Abstract
This document provides are review of the status of the development of the 802 comments on the fcc19-138 NPRM revisiting the use of the 5.850-5.925 GHz band

## Slide 3: Background
21 November 2019 – the FCC announces the intent to propose a NPRM for the 5.9 GHz band at the December 2019 Open Commission Meeting (12 Dec 2019) [1]
5 December 2019 – A discussion thread was started on the 802.11 TGbd reflector [2]
12 December 2019 – at the Open Commission Meeting, the FCC commissioners unanimously approve the proposed NPRM. [3]
06 February 2020 - Publication of the NPRM in the Federal Register [4]
09 March 2020 - Comments on the NPRM are due on or before [4]
06 April 2020 – Reply comments are due on or before [4]

## Slide 4: 802.11 TGbd Activity
During the January 802.11 TGbd session:
Discussed on the pending publication of the NPRM
Initial draft of comments on the NPRM [5]
Additional proposed text was contributed and editorial changes [6 (r0)-(r7)]
TGbd agreed the following motion:
Approve TGbd to develop comment document responding to FCC NPRM on 5.9 GHz band
  - Joseph Levy leads the developing of comments with 11-20/0104 as the comment document.
and run a WG ballot to approve the completed comment document and for the WG Chair to decide to send to FCC after EC review or forward to 802.18 for LMSC process
Note this motion was not agreed at the closing plenary of the 802.11 January meeting, the WG decided that working with 802.18 to generate comments from 802 was the preferred way to proceed.
Additional contribution and editing continued until the NPRM was published (6 Feb) at which time the draft [7,8] and the work transferred to 802.18 (10 Feb)

## Slide 5: 802.18 Activity/Plan
Prior to the NPRM being published (6 Feb) 802.18 was monitoring and commenting on the 802.11 TGbd draft contribution 11-20/0104
After the NPRM was published (6 Feb) 802.18 transferred 11-20/0104 [7,8] to become 18-20/0020 [9,10] respectively (10 Feb).
802.18 has set up a very aggressive teleconference plan to complete the comments document and allow for 802 EC review/approval prior to the 9 March 2020 submission due date. Meeting dates (past and planned)
  Ad Hoc meetings 11, 14, 18, 19 Feb (2 hours, 15:00-17:00 EST)
  Regular 802.18 weekly meeting 23, 30 Mar; 06, 13, 20 Feb (1 hour, 15:00-16:00 EST)
The goal is to have a completed/approved 802.18 document by 20 Feb, so it can be approved by the 802 EC (10 day ballot) and be submitted to the FCC prior to the 9 Mar due date. (note the document can only be approved by 802.18 in a “Regular” meeting)

## Slide 6: Comment Document – 18-20/0020 [10]– Open Items
Text contributions may be provided to 802.18 (for any part of the document)
There are currently several sections of the document that do not have any content, if content is not provided these sections will be removed and there will be no comment from 802 related to the issues of the section:
  OOB performance/requirements
  Need for compatibility/backwards compatibility
Draft status:
  Sections 1, 2, and 3 have been reviewed, edited, and all 802.18 comments have been resolved
  Sections 4, 5.1, 6, and 7.4 are due to be discussed on the 18 Feb Ad hoc call (15:00-17:00 EST)
  All sections with open comments and the entire document is due to be “finalized” on the 19 Feb Ad hoc call (15:00-17:00 EST)
  Note: The conclusion has not yet been written (this should be done prior to the 19 Feb Ad hoc call
  Final edits/approval of 18-20/0020 is scheduled for the 802.18 call on 20 Feb (15:00-16:00 EST)

## Slide 7: References
[1] – Office of Engineering and Technology Opens ET Docket No. 19-138, and associated FCC “FACT SHEET”, 21 Nov 2019.
[2] – [STDS-802-11-TGBD] Discussion on: FCC NPRM impacting the 5.9 GHz Band, Joseph Levy, 5 Dec 2019
[3] – FCC Seeks to Promote Innovation in the 5.9 GHz Band – News Release, 12 Dec 2019, Bureau of Engineering and Technology
[4] - “FEDERAL COMMUNICATIONS COMMISSION, 47 CFR Parts 2, 15, 90, and 95, [ET Docket No. 19–138; FCC 19–129; FRS 16447], Use of the 5.850–5.925 GHz Band” as published in the Federal Register/ Vol. 85, No. 25/ Thursday, February 6, 2020 / proposed Rules, starting on page 6841. https://www.govinfo.gov/content/pkg/FR-2020-02-06/pdf/2020-02086.pdf
[5] – “Draft TGbd Comments on FCC NPRM Docket 19-138”, 11-20/0104r1
[6] – “Draft TGbd Comments on FCC NPRM Docket 19-138”, 11-20/0104r13
[7] – “Draft TGbd Comments on FCC NPRM Docket 19-138”, 11-20/0104r14
[8] – “Comments on FCC19-138 NPRM Revisiting Use of the 5.850-5.925 GHz Band”, 18-20/0020r0
[9] – “Comments on FCC19-138 NPRM Revisiting Use of the 5.850-5.925 GHz Band”, 18-20/0020r1
[10] – “Comments on FCC19-138 NPRM Revisiting Use of the 5.850-5.925 GHz Band”, 18-20/0020r5