## Slide 1
Date: 2020-10-05
Authors:
P802.11REVmd Report to EC on Approval to forward draft to RevCom

## Slide 2: Introduction
This document contains the report to the IEEE 802 Executive Committee in support of a request for conditional approval to send P802.11REVmd Draft 5.0 to RevCom.
This document was approved by the 802.11 working group on 2020-09-18.
  Passed in the Working Group 88 yes, 0 no , 6 abstain
R1-R3 adds the WG motion results and updated voter, unresolved comments
R4 adds 2nd SA recirculation results

## Slide 3: Standards Association (SA) Ballot Results – P802.11REVmd
Ballot Close Date | Title | Pool | Return | %Return | Abstain | %Abstain | Approve | Disapprove | %Approve
15 Dec 2019 | Initial SA ballot for P802.11REVmd draft 3.0 | 174 | 148 | 85 | 4 | 3 | 119 | 25 | 83
04 Sept 2020 | First Recirculation SA Ballot for P802.11REVmd draft 4.0 | 174 | 154 | 89 | 5 | 3 | 136 | 13 | 91
16 Sept | Post ballot vote changes to Approve* | 174 | 154 |  |  |  | 145 | 4 | 97
04 Oct | Second Recirculation SA Ballot for P802.11REVmd draft 5.0 | 174 | 157 | 90 | 5 | 3 | 148 | 4 | 97
* Myles, Hervieu, Aboul-Magd, Costa, Goodall, Malinen, Kasher, Bims, Seok

## Slide 4: SA Ballot Comments – P802.11REVmd
Ballot Close Date | Title | Total Number of Comments received (Yes and No votes)
15 Dec 2019 | Initial SA ballot for P802.11REVmd draft 3.0 | 820 (519T, 301 E)
04 Sept 2020 | First Recirculation SA Ballot for P802.11REVmd draft 4.0 | 82 (57 T, 25 E)
04 Oct 2020 | Second Recirculation SA Ballot for P802.11REVmd draft 5.0 | 3 (3 T, 0 E)

## Slide 5: Unsatisfied comments by commenter
Voter | Initial | 1st Re | 2nd Re | Comment topic | Total
Matthew Fischer | 2 | 0 | 0 | Additional Block ACK mechanism, Control Response MCS negotiation | 2
Guido Hiertz | 1 | 0 | 0 | TXOP limit parameters | 1
Joseph Levy | 9 | 0 | 0 | Power save, Frame Exchange sequences | 9
Mark Rison | 0 | 1 | 0 | “Many issues in the draft” | 1
TOTAL | 12 | 1 | 0 |  | 13

## Slide 6: Unsatisfied comments
The composite of all unsatisfied comments and the resolutions approved by the comment resolution committee received during SA ballot are in the embedded document on the right:
  Double click on the icon to open the file

## Slide 7: Mandatory Coordination
Coordination Entity | Draft | Date | Status
IEEE-SA Editorial (MEC) | D3.0 | Dec 2019 | “Meets all editorial requirements.”
Quantities, Units and Letter Symbols (SCC14) |  |  | Not required
Terms and Definitions (SCC10) |  |  | Not required
Registration Authority Committee (RAC) | D4.0 | Sept 2020 | Completed

## Slide 8: P802.11md Timeline
Report to EC for conditional approval to proceed to RevCom | 2020-10-06 | 
2nd Recirculation D5.0 | 2020-09-24 to 2020-10-04 | 
Comment Response Notification | 2020-10-10 | 
Post to RevCom by | 2020--10-13 | 
If required: 3rd recirculation | 2020-10-7 to 2020-10-17 |