## Slide 1: TGbc Closing Report
Date: 2021-05-14
Authors:

## Slide 2: Abstract
Closing report for IEEE 802.11 TGbc (Broadcast Services) for May 2021.

## Slide 3: Meeting Goals & Accomplishments of the week
Goal for the week:
Progress with comment resolution
Accomplishments
Group met 4 times this week
Discussion and approval of 135 comment resolutions
Discussion in general direction on how to resolve some Cls. 11 comments
Request to TGbc Editor to produce next version of TGbc Draft
Owning Ad-hoc | Count of CID | 
EDITOR | 382 | 
2021-01-05 - approved | 7 | 
2021-01-12 - approved | 41 | 
2021-01-13 - approved | 7 | 
2021-01-27 - approved | 52 | 
2021-02-02 - approved | 7 | 
2021-02-09 - approved | 37 | 
2021-03-09 - approved | 1 | 
2021-03-10 - approved | 18 | 
2021-03-12 - approved | 60 | 
2021-04-13 - approved | 4 | 
2021-05-04 - approved | 13 | 
2021-05-11 - approved | 17 | 
2021-05-14 - CID 1091 - approved | 1 | 
2021-05-14 - editor - approved | 18 | 
2021-05-14a - approved | 67 | 
2021-05-14b - approved | 32 | 
CHAIR | 261 | 
(Leer) | 261 | 
Gesamtergebnis | 643 | 

## Slide 4: Plans for Next Meeting & Upcoming Telcos
Upcoming meeting
Comment resolution from WG LB
Resolve all comments, produce D2.0, go to WG recirc
Weekly Telcos
  Every Tuesday, 09:30h – 11:30 ET, 2 hours
  Already announced with 10-day notice to WG and TG reflector
  Next telco on May 25th.

## Slide 5: TGbc schedule (changed)
January 2019 First meeting as a task group
June 2020 Call for comments on D0.1
November 2020 Initial WGLB (D1.0)
July 2021 D2.0 WGLB Recirculation LB
November 2021 Form SB Pool
November 2021 MEC/MDR done
Jan 2022 Initial SB
May 2022 Recirculation SB
July 2022 Final WG/EC approval
September 2022 Revcom/SASB approval

## Slide 6: References
Agenda for this week: 11-21/0608
Meeting / Chair’s Slide Deck: 11-21/0606
Meeting minutes: 11-21/0773
Snapshot Slide: 11-21/0607
Closing report: 11-21/0609
TGbc Motion Booklet: 11-18/2123
TGbc Selection Procedure: 11-19/0135
TGbc Functional Requirements: 11-19/0151
TGbc UseCase Document: 11-19/268