## Slide 1: 802.11REVme Editor’s Report
Date: 2021-July-12
Authors:

## Slide 2: Status of REVme Draft

## Slide 3: Reference Documents
Draft: P802.11REVme D 0.1 (members’ area)
  Draft P802.11REVme_D0.1.pdf
  Draft P802.11REVme_D0.1 Redline Compared to D0.0.pdf
D0.1 word docs and figures are also available (member’s area) for preparing submissions.
  REVme_D0.1.rtf.zip
  REVme-D0.1-Figure Source.zip
CC35 Comments
  https://mentor.ieee.org/802.11/dcn/21/11-21-0684-04-000m-revme-wg-cc35-comments.xlsx

## Slide 4: Amendment Roll-in Plan
802.11-2020 – Done, D0.0
802.11ax-2021 – Done, D0.1
802.11ay-2021 – by September 2021
802.11ba-2021 – by November 2021
… …
802.11az-2022 – TBD
802.11bb-2022 – TBD
802.11bc-2022 – TBD
802.11bd-2022 – TBD

## Slide 5: CC35 Comments - Resolution Status
ED1 (Emily Q): Editorial comments from clause 1 to clause 9.
ED2 (Edward A): Editorial comments from clause 10 to the end, plus non-clause specified
GEN (Jon R): Technical comments from clause 1 to clause 8, and Annexes.
MAC (Mark H): Technical comments from clause 9 to clause 11, clause 14.
PHY (Mark R): Technical comments from clause 15 to clause 25
SEC (Mike M): Technical comments from clause 12 and 13.
Owning Ad-hoc | Assigned | Discuss | Review | Ready for Motion | Approved | Duplicate | Grand Total
EDITOR |  |  |  |  | 29 |  | 29
GEN | 69 |  |  | 9 |  |  | 78
MAC | 226 |  |  | 2 |  |  | 228
SEC | 49 |  |  | 2 |  | 2 | 53
ED2 | 108 |  |  | 11 |  |  | 119
ED1 | 10 | 1 | 1 | 2 | 31 |  | 45
PHY | 29 | 10 |  | 13 |  |  | 52
Grand Total | 491 | 11 | 1 | 39 | 60 | 2 | 604

## Slide 6: CC35 Comments – Assignees by Ad-hoc Groups
Owning Ad-hoc | GEN | MAC | SEC | ED2 | ED1 | PHY | Grand Total
Brian HART | 2 | 1 |  |  |  | 5 | 8
Dan Harkins |  | 10 | 2 |  |  |  | 12
Edward Au | 3 |  |  | 95 |  |  | 98
Graham Smith | 3 |  | 1 |  |  |  | 4
Jon Rosdahl | 20 |  |  |  |  |  | 20
Mark HAMILTON | 1 | 24 | 1 |  |  | 1 | 27
Mark RISON | 24 | 111 | 26 | 13 | 6 | 9 | 189
Menzo WENTINK |  | 12 |  |  |  |  | 12
Michael Montemurro | 5 |  | 11 |  |  |  | 16
Stephen McCann | 3 | 1 |  |  | 1 |  | 5
(blank) |  |  |  |  | 1 | 10 | 11
Ganesh VENKATESAN |  |  |  |  | 1 |  | 1
Youhan KIM |  | 1 |  |  |  | 6 | 7
Emily Qi |  | 3 |  |  | 2 |  | 5
Sean Coffey | 1 |  |  |  |  | 3 | 4
Grand Total | 62 | 163 | 41 | 108 | 11 | 34 | 419

## Slide 7: Thank You for Your Contributions!