## Slide 1: 802.11REVme Editor’s Report
Date: 2023-January-15
Authors:

## Slide 2: Status of REVme Draft

## Slide 3: Reference Documents
Draft P802.11REVme D 2.1 will be available in members’ area soon.
Draft P802.11REVme D 2.0 (members’ area)
  Draft P802.11REVme_D2.0.pdf
  Draft P802.11REVme_D2.0 Redline Compared to D1.0.pdf
  Draft P802.11REVme_D2.0 Redline Compared to D1.4.pdf
D2.0 word docs and figures are also available (member’s area) for preparing submissions.
  REVme_D2.0.rtf.zip Figure Source-D2.0.zip
WG LB Comments
  All CC35 Comments – 604 ; All LB258 Comments - 1392 ; All LB270 comments – 822
  https://mentor.ieee.org/802.11/dcn/22/11-22-0065-14-000m-revme-wg-ballot-comments.xls

## Slide 4: Amendment Roll-in Plan
802.11-2020 – Done, D0.0
802.11ax-2021 – Done, D0.1
802.11ay-2021 – Done, D0.3
802.11ba-2021 – Done, D0.4
… …
802.11az-2022 (RevCom in Dec 2022) – By March 2023 ?
802.11bd-2022 (RevCom in Dec 2022) – By March 2023 ?
802.11bb-202? – TBD
802.11bc-202? – TBD

## Slide 5: LB270 Comments - Resolution Status
ED1 (Emily Q): Editorial comments from clause 1 to clause 10, plus non-clause specified editorial comments
ED2 (Edward A): Editorial comments from clause 11 to the end, plus non-clause specified editorial comments
GEN (Jon R): General Comments (G) and Technical comments from clause 1 to clause 8
MAC (Mark H): Technical comments from clause 9 to 11, clause 14, 26, 29
PHY (Mark R): Technical comments from clause 15 to 25, clause 27, 28, 30, and Annexes
SEC (Mike M): Technical comments from clause 12 and 13.
MISC (Mike M): non-clause specified tech comments
Owning Ad-hoc | (blank) | Discuss | Submission Required | Review | Ready for Motion | Resolved | More Work Required | Grand Total
EDITOR |  |  |  |  |  | 231 |  | 231
GEN | 1 | 29 | 19 | 13 |  |  | 2 | 64
MAC | 3 | 51 | 187 |  |  | 1 | 15 | 257
PHY | 1 | 8 | 16 | 1 | 3 |  | 26 | 55
SEC |  | 30 | 77 | 3 |  |  | 5 | 115
ED2 | 4 |  | 14 | 1 | 13 |  | 5 | 37
ED1 |  |  | 28 |  | 29 |  | 6 | 63
Grand Total | 9 | 118 | 341 | 18 | 45 | 232 | 59 | 822

## Slide 6: Thank You for Your Contributions!