## Slide 1: TGbe September 2021 Closing Report
Date: 2021-09-20
Authors:

## Slide 2: TGbe (Extremely High Throughput)
TGbe had scheduled 4 conf. calls during the September electronic interim
  Two Joint calls, and two parallel MAC/PHY calls
    Covered comment resolution documents
    Approved the resolution of several technical/editorial comments and PDT submissions
      ~30% of all CC36 comments are now resolved
  Approved the creation of TGbe D1.2
    TGbe D1.2 is expected to be available by end of this week
Agenda is available in 1319r8, with queue statuses available in 1478r3
  Future Teleconference Plan is provided in the next slide
Motions List is available in 1982r44
Distribution of ~4350 CIDs
9%
67%
24%
Resolution Status

## Slide 3: Teleconference Plan
Oct 11 (Monday) – MAC/PHY 19:00-21:00 ET
Oct 13 (Wednesday) – Joint (Motions) 10:00-12:00 ET
Oct 14 (Thursday) – MAC 10:00-12:00 ET
Oct 18 (Monday) – MAC/PHY 19:00-21:00 ET
Oct 20 (Wednesday) – Joint 10:00-12:00 ET
Oct 21 (Thursday) – MAC 10:00-12:00 ET
Oct 25 (Monday) – MAC/PHY 19:00-21:00 ET
Oct 27 (Wednesday) – Joint (Motions) 10:00-12:00 ET
Oct 28 (Thursday) – MAC 10:00-12:00 ET
Nov 01 (Monday) – MAC/PHY 19:00-21:00 ET
Nov 03 (Wednesday) – Joint 10:00-12:00 ET
Nov 04 (Thursday) – MAC 10:00-12:00 ET
Nov 08 (Monday) – MAC/PHY 19:00-21:00 ET
Nov 10 (Wednesday) – Joint 10:00-12:00 ET
Nov 11 (Thursday) – MAC 10:00-12:00 ET
Sept 13 (Monday) – MAC/PHY 19:00-21:00 ET
Sept 15 (Wednesday) – Joint (Motions) 09:00-11:00 ET
Sept 16 (Thursday) – MAC/PHY 09:00-11:00 ET
Sept 20 (Monday) – Joint (Motions) 09:00-11:00 ET
Sept 22 (Wednesday) – MAC 10:00-12:00 ET
Sept 23 (Thursday) – MAC 10:00-12:00 ET
Sept 27 (Monday) – MAC/PHY 19:00-21:00 ET
Sept 29 (Wednesday) – Joint 10:00-12:00 ET
Sept 30 (Thursday) – MAC 10:00-12:00 ET
Oct 04-08 (Mon-Fri) – No Conf Call Golden Week

## Slide 4: Timeline
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sep 2020
D1.0 WG Comment Collection May 2021
D2.0 WG Comment Collection Mar 2022
D3.0 Letter Ballot Nov 2022
Initial Sponsor Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024