## Slide 1: TGbc Closing Report
Date: 2021-09-16
Authors:

## Slide 2: Abstract
Closing report for IEEE 802.11 TGbc (Broadcast Services) for September 2021.

## Slide 3: Meeting Goals & Accomplishments of the week
Goal for the week:
Finish comment resolution
Motion to create D2.0 and to go to WG recirculation
Accomplishments
Group met 4 times this week
Discussion and approval of 91 comment resolutions
All comments from LB 252 resolved
Motion for WG recic LB passed

## Slide 4: Plans for Next Meeting & Upcoming Telcos
Upcoming meeting
Comment resolution from WG Reciculation LB
Weekly Telcos
  Every Tuesday, 09:30h – 11:30 ET, 2 hours
  Already announced with 10-day notice to WG and TG reflector
  Next telco on September 28th
  Used to engage in further discussion in view of potentially submitted comments during the recirculation ballot
  Comment resolution once Recirc LB closes

## Slide 5: TGbc schedule (unchanged)
January 2019 First meeting as a task group
June 2020 Call for comments on D0.1
November 2020 Initial WGLB (D1.0)
September 2021 D2.0 WGLB Recirculation LB
March 2022 Form SAB Pool
March 2022 MEC/MDR done
May 2022 Initial SAB (4.0)
September 2022 Recirculation SAB
Jan 2023 Final WG/EC approval
March 2023 Revcom/SASB approval

## Slide 6: References
Agenda for this week: 11-21/1355
Meeting / Chair’s Slide Deck: 11-21/1353
Meeting minutes: 11-21/1357
Snapshot Slide: 11-21/1354
Closing report: 11-21/1356
TGbc Motion Booklet: 11-18/2123
TGbc Selection Procedure: 11-19/0135
TGbc Functional Requirements: 11-19/0151
TGbc UseCase Document: 11-19/268