## Slide 1: TGaz Next Generation Positioning Nov. Electronic Meeting Closing Report
Date: 2021-11-15
Authors:

## Slide 2: Abstract
This document is the TGaz Next Generation Positioning closing report for the IEEE 802.11 plenary electronic meeting, Nov. 2021.

## Slide 3: Nov. Progress and Targets Towards the Jan. Meeting
Work completed this week:
  Conducted assignment to 1/3 of the technical comments received in P802.11az D4.0 SA1
  Started SA1 comment resolution to extent possible.
  Responded to WFA Liaison.
Targets towards the January meeting:
  Complete assignment of P802.11 D4.0 SA1 comments.
  Resolve 60 technical/General comments (~33% of SA1 T+G comments).

## Slide 4: Timeline – TG progress update past the Nov. meeting
Clean
2021
2020
2019
2017
2018
2022
2023
.11az requirement freeze
5-2017
11az SFD
.11az Draft 2.0 11-2019
Recirculation
D1.0
Jan. 19
.11az D0.1 Mar. 18
5/17-3/21
July 18
Inter.
comment
collection
SFD
Final
Initial
WG ballot
CC28
LB240 CR
Initial WG ballot LB240 Pass
SFD Freeze
LB249
LB240 completion/
recirc. init
LB249 completion/
2nd recirculation
.11az Draft 3.0 01-2021
Recirculation
.11az Draft 4.0 07-2021
Recirculation
.11az MDR and SA ballots
07-2021
Publication
LB253
SA2
MDR
SA1
LB 255
No changes made, in preparation to SA ballot
1st SA comp.
05-22
2nd SA comp.
07-22
LB249 completion/
2nd recirculation
1st SA start
REVcom
SA3
3rd SA comp.
11-22

## Slide 5: Scheduled telecons
* - newly announced
+ TGaz Plenary (motion) meeting.
** - meeting as part of the IEEE week, refer to WG agenda document for details.
Dec. 2nd Thu. 12:00 – 14:00 ET*
Dec. 9th Thu. 12:00 – 14:00 ET*
Dec. 16th Thu. 12:00 – 14:00 ET*
Jan. 6th Thu. 12:00 – 14:00 ET*
Jan. 13th Thu. 12:00 – 14:00 ET*