## Slide 1: IEEE 802.11 Plenary Nov 2021 IEEE 802.11 TGbd Closing Report
Chair: Bo Sun (ZTE)
Vice Chair: Hongyuan Zhang (NXP),
Joseph Levy (InterDigital)
Secretary: Yan Zhang (NXP)
Tech Editor: Yujin Noh (Senscomm)

## Slide 2: TGbd’s Progress during the plenary week
4 TGbd sessions were held during the week
Approved TG minutes for Sep interim week and following TCs before Nov plenary week.
Presented and discussed CRs and approved CRs for the last 108 CIDs of LB 254.
Approved TGbd tech editor to generate IEEE P802.11bd D3.0 to incorporate approved CRs and a 15-day recirculation LB for D3.0.
Approved the updated TGbd timeline and teleconference plan till Jan interim week.
TGbd agenda documents for this week:
  https://mentor.ieee.org/802.11/dcn/21/11-21-1623-04-00bd-tgbd-teleconference-agenda-for-nov-2021.pptx
Goal for future TCs: proceeding comments collected from recirculation LB and MDR (11bd D3.0)

## Slide 3: TGbd Progress Documents
TG Documents | Latest Revision
Definition and requirements | 11-19/0202r1
Selection Procedure document | 11-19/0030r6
Functional Requirement document | 11-19/0495r3
Spec Framework document | 11-19/0497r7
Liaison response to IEEE VT/ITS 1609 WG | 11-19/0437r3
Liaison response to ITU-T CITS | 11-19/0843r0
TBbd FRD/SFD Motion Booklet | 11-19/0514r14
TGbd Use Case document | 11-19/1342r1
Teleconference Agenda | 11-20/0774r10, 11-20/1164r7, 11-20/1352r9, 11-20/1561r7, 11-20/1806r2, 11-20/1891r0, 11-20/1923r11, 11-21/0177r2, 11-21/0207r8, 11-21/0595r3, 11-21/0597r7, 11-21/0904r1, 11-21/0941r2, 11-21/1303r4, 11-21/1326r8, 11-21/1622r4, 11-21/1623r4
Teleconference Minutes | 11-20/0276r11, 11-20/1105r8, 11-20/1489r1, 11-20/1655r3, 11-20/1775r1, 11-20/1907r1, 11-21/0068r0, 11-21/0117r0, 11-21/0327r0, 11-21/0453r0, 11-21/0454r0, 11-21/0565r0, 11-21/0655r0, 11-21/0806r0, 11-21/0889r0, 11-21/1138r0, 11-21/1468r0, 11-21/1544r0, 11-21/1769r0
Tech Editor Report | 11-19/2045r14 (D2.0)
Comment Database | 11-20/0701r7 (D0.3), 11-20/1887r10 (LB251), 11-21/1296r6 (LB254)
Coexistence Assurance Document | 11-20/1564r2

## Slide 4: Motion #1 (approval of Comment Resolutions)
Move to approve the comment resolutions to 108 CIDs which are marked as “ready for motion” as in 11-21/1296r6
Moved: Yujin Noh Seconded: Stephan Sand
Result: Approved unanimously

## Slide 5: Motion #2 (Generation of D3.0 and recirculation)
Having approved comment resolutions for all of the comments received from LB 254 on IEEE P802.11bd D2.0 as contained in document
https://mentor.ieee.org/802.11/dcn/20/11-21-1296-06-00bd-tgbd-lb251-comments.xlsx,
instruct the TGbd editor to create IEEE P802.11bd D3.0 and approve a motion request to WG11 for approval of a 15-day Working Group Recirculation Ballot asking the question “Should IEEE P802.11bd D3.0 be forwarded to SA Ballot?”
TGbd vote: Moved: Joseph Levy Seconded: John Kenney
Result: 16y-0n-3a

## Slide 6: TGbd Timeline (updated) (Note, the timeline may be accelerated based on 11az’s actual progress)
  PAR approved Dec 2018
  First TG meeting Jan 2019
  D0.1 Nov 2019
  D1.0 Letter Ballot Oct 2020
  D2.0 LB recirculation Jul 2021
  Form SA Ballot Pool Nov 1 to Nov 30, 2021
  D3.0 LB recirculation Jan 2022 (Try Nov 2021)  Dec 2021
  D3.0 unchanged recirculation Jan 2022
  D4.0 LB recirculation Jul 2022
  D4.0 LB unchanged recirculation Jul 2022
  Initial SA Ballot (D34.0) Mar 2022  Jul 2022
  Final 802.11 WG approval Sep 2022  Jan 2023
  802 EC approval Oct 2022  Feb 2023
  RevCom and SASB approval Dec 2022  May 2023

## Slide 7: IEEE 802.11 TGbd TC Plan
Dec 17th, 10:00am ~ 11:00am, ET
Dec 21st, 10:00am ~ 11:00am, ET
Jan 4th, 2022, 10:00am ~ 11:59am, ET
Jan 11th, 2022, 9:00am ~ 11:00am, ET