## Slide 1: TGbc Closing Report
Date: 2022-01-21
Authors:

## Slide 2: Abstract
Closing report for IEEE 802.11 TGbc (Broadcast Services) for January 2022.

## Slide 3: Meeting Goals & Accomplishments of the week
Goal for the week:
Continue comment resolution process
Revisit Timeline
Accomplishments
Group met 4 times this week
Resolved 101 technical comments
  87 comments resolved and approved
  14 comments resolved and ready for motion
Updated timeline
Owning Ad-hoc | Count of CID
EDITOR | 186
2021-11-11 - approved | 62
2021-11-12 - approved | 4
2021-11-23 - approved | 18
2022-01-04 - approved | 15
2022-01-19 - approved | 70
2022-01-20 - approved | 16
2022-01-20 - motion 144 approved | 1
CHAIR | 108
2022-02-01 - ready for motion | 14
(Leer) | 94
Gesamtergebnis | 294

## Slide 4: Plans for Next Meeting & Upcoming Telcos
Telcos
Continue comment resolution
Upcoming meeting
Finish comment resolution from WG Recirculation LB257 and
Create D3.0 (out of March meeting)
Go to WG recirculation LB (D3.0) out of March meeting
Weekly Telcos
Tuesdays, 10:00h – 11.00h ET (1 hours)

## Slide 5: TGbc schedule (updated)
January 2019 First meeting as a task group
June 2020 Call for comments on D0.1
November 2020 Initial WGLB (D1.0)
September 2021 D2.0 WG Recirculation LB
March 2022 D3.0 WG Recirculation LB
March 2022 Editorial review / MEC/MDR on D3.0
May 2022 D4.0 WG Recirculation LB
May 2022 Form SAB Pool
Jul 2022 D4.0-unchanged WG Recirculation LB
Jul 2022 Initial SAB (4.0)
November 2022 Recirculation SAB
March 2023 Final WG/EC approval
May 2023 Revcom/SASB approval

## Slide 6: References
Agenda for this week: 11-21/1954
Meeting / Chair’s Slide Deck: 11-21/1955
Meeting minutes: 11-22/0050
Snapshot Slide: 11-21/1956
Closing report: 11-21/1957
TGbc Motion Booklet: 11-18/2123
TGbc Selection Procedure: 11-19/0135
TGbc Functional Requirements: 11-19/0151
TGbc UseCase Document: 11-19/268