## Slide 1: TGbh Closing Report
Date: 2022-01-21
Authors:

## Slide 2: Abstract
This document is the closing report for TGbh
“Randomized and Changing MAC addresses” (RCM)
January 2022 Plenary Session (virtual)

## Slide 3: Work Completed
Agenda is here: 11-21/1995r6
Latest Issue Tracking document: 11-21/0332r29
Contributions reviewed (solutions direction, some with draft text):
  11-22/0117r0 : Secure Device ID exchange concept
  11-22/0118r0 : IRMA with ID Query
  11-22/0145r0 : STA identifier way forward
  11-22/0154r0 : Opaque device ID
  11-22/0158r0 : STA generated Device ID
  11-22/0157r0 : MAC Address designation MAAD
  11-21/1634r2 : Non-MAC device identifier requirements for TGbh (partially reviewed)
Missed target for D0.1, again, out of this session, timeline update needed

## Slide 4: Next steps
Consider proposed solutions for impacted features/functions, and incorporate into D0.1
Review what items remain open, for a complete D1.0
Still targeting D1.0 out of March – need to consider if that is feasible
WBA liaison response

## Slide 5: Timeline
  PAR approved Feb 2021
  First TG meeting Mar 2021
  D0.1 Jan 2022
  Initial Letter Ballot (D1.0) Mar 2022
  Recirculation LB (D2.0) Jul 2022
  Initial SA Ballot (D3.0) Nov 2022
  Final 802.11 WG approval Mar 2023
  802 EC approval May 2023
  RevCom and SASB approval May 2023

## Slide 6: Teleconference(s)
Feb 8, 9:00-11:00 ET
Feb 17, 17:00-19:00 ET
Feb 22, 9:00-11:00 ET
Mar 3, 17:00-19:00 ET

## Slide 7: March 2022 Plans
Four meeting slots planned
Consider “solutions” to use cases that are in 802.11 scope to resolve
Formulate D1.0