## Slide 1: Task Group BF January 2022 Closing Report
Date: 2022-01-24
Authors:
Name | Affiliation | Address | Phone | Email
Tony Xiao Han | Huawei Technologies Co., Ltd. | F3, Huawei Base, Shenzhen, China |  | Tony.hanxiao@huawei.com

## Slide 2: Abstract
This document is the closing report for Task Group BF for the January 2022 session.

## Slide 3: TGbf (WLAN Sensing) – January 2022
Progress during January 2022 meeting
  4 teleconference calls for TGbf (January 18, 19, 21, 24, 9am - 11:00am ET)
  Presentation of technical submissions (e.g., Feedback type, general protocol and procedure……)
  Developing the SFD and D0.1
Goals for the next two months
  Presentation of technical submissions (e.g., PDT for D0.1, Feedback type, general protocol and procedure ……)
  Speed up the technical discussion and developing the SFD and D0.1 (Requested 3 calls per week)

## Slide 4: TGbf Timeline (Updated)
  PAR approved Sep 2020
  First TG meeting Oct 2020
  Comment Collection (D0.1) Jan 2022Mar 2022
  Initial Letter Ballot (D1.0) Jul 2022 Sep 2022
  Recirculation LB (D2.0) Jan 2023
  Recirculation LB (D3.0) May 2023
  Recirculation LB (D4.0) July 2023
  Initial SA Ballot (D4.0) Sep 2023
  Final 802.11 WG approval July 2024
  802 EC approval July 2024
  RevCom and SASB approval Sep 2024
Timeline for D0.1 (Tentative)
Week of January 3
  Editor provides initial list of topics (and updated SFD revision) (Tuesday)
  Chair issues call for volunteers (Tuesday)
  POCs and volunteers are identified for topics in the initial list (Friday)
January 2128, 2022
  Deadline for baseline document for each topic (in the initial list) to be uploaded
March 2022 IEEE Plenary
  Deadline for contributions to pass motion and be included in D0.1
  Seek TGbf approval to go to comment collection (“Move to Approve a 30-day comment collection on TGbf D0.1?”)
March 28 (Monday, two weeks after March 2022 Plenary)
  Editor releases D0.1
  If the Motion is favorable, the TG chair sends a request to the WG chair (Dorothy) to start the comment collection
  30-day comment collection window opens

## Slide 5: Teleconference Schedule
  Confirmed:
    January Interim
    January 18 (Tuesday), 9am - 11:00am ET January 19 (Wednesday), 9am - 11:00am ET
    January 21 (Friday), 9am - 11:00am ET January 24 (Monday), 9am - 11:00am ET
    (January 28, deadline for baseline document for each topic (in the initial list) to be uploaded)
    February 7 (Monday), 9am - 11:00am ET February 8 (Tuesday), 9am - 11:00am ET
    February 10 (Thursday), 10pm - 12:00am ET
    February 14 (Monday), 9am - 11:00am ET February 15 (Tuesday), 9am - 11:00am ET
    February 17 (Thursday), 10pm - 12:00am ET
    February 22 (Tuesday), 9am - 11:00am ET
    February 24 (Thursday), 10pm - 12:00am ET
    February 28 (Monday), 9am - 11:00am ET March 1 (Tuesday), 9am - 11:00am ET
    March 3 (Thursday), 10pm - 12:00am ET
  To be confirmed:
    March 2022 IEEE Plenary (March 13-18 7-15) (Deadline for contributions to pass motion and be included in D0.1)
    March 8 (Tuesday), 9am - 11:00am ET
    March 9 (Wednesday), 9am - 11:00am ET
    March 9 (Wednesday), 10pm - 12:00am ET (Not sure if this slot is ok for Plenary and Interim?)
    March 11 (Friday), 9am - 11:00am ET
    March 14 (Monday), 9am - 11:00am ET
    Seek TGbf approval to go to comment collection (“Move to Approve a 30-day comment collection on TGbf D0.1?”)
  ** Note:
  1. when conflict with CAC, the call will be changed from 9am -11:00am to 10am -11:00am (Jan-March 2022 CAC calls (TBD): Monday February 21 and Thursday March 3 )
  2. Thursday 10pm - 12:00am ET (Thursday 7 PM - 9 PM PT, Friday 11am-1pm in China, Friday 5am-7am in Israel, Friday 4am – 6am in Central Europe), and Sang Kim will help to take the minutes for these slots.