## Slide 1: TGbc Closing Report
Date: 2022-03-14
Authors:

## Slide 2: Abstract
Closing report for IEEE 802.11 TGbc (Broadcast Services) for March 2022.

## Slide 3: Meeting Goals & Accomplishments of the week
Goal for the week:
Work on comment resolutions
Discussion with WG Editor and TG Editor on ANA assignments
Try to go to D3.0 recirculation WG LB
Accomplishments
Group met 5 times this week
Resolved 79 technical comments
  All comments resolved;
  TG motion to request WG recirc passed
ANA discussion with WG Editor deferred to upcoming telcos

## Slide 4: Plans for Next Meeting & Upcoming Telcos
Telcos
Discussion with WG Editor on ANA Assignment
To be decided: discussion on potential support of S1G
Start resolving comments from upcoming WG LB
Upcoming meeting
Resolution of comments from upcoming WG LB
Weekly Telcos
Tuesdays, 10:00h – 11.00h ET (1 hours)

## Slide 5: TGbc schedule (unchanged)
January 2019 First meeting as a task group
June 2020 Call for comments on D0.1
November 2020 Initial WGLB (D1.0)
September 2021 D2.0 WG Recirculation LB
March 2022 D3.0 WG Recirculation LB
March 2022 Editorial review / MEC/MDR on D3.0
May 2022 D4.0 WG Recirculation LB
May 2022 Form SAB Pool
Jul 2022 D4.0-unchanged WG Recirculation LB
Jul 2022 Initial SAB (4.0)
November 2022 Recirculation SAB
March 2023 Final WG/EC approval
May 2023 Revcom/SASB approval

## Slide 6: References
Agenda for this week: 11-22/0204
Meeting / Chair’s Slide Deck: 11-22/0205
Meeting minutes: 11-22/0426
Snapshot Slide: 11-22/0206
Closing report: 11-22/0207
TGbc Motion Booklet: 11-18/2123
TGbc Selection Procedure: 11-19/0135
TGbc Functional Requirements: 11-19/0151
TGbc UseCase Document: 11-19/268