## Slide 1: Guidelines: Status And Update
Date: 2022-03-22
Authors:
Alfred Asterjadhi, et. al.

## Slide 2: Introduction
In 396r2 we discussed the following items
  Proposed plan for post TGbe D2.0
  Proposal to go to WG letter ballot on TGbe D2.0
    Amending timeline milestone terminology
This presentation focuses on:
  Providing a status update of TGbe
  Amend the milestone for TGbe D2.0 in the TGbe timeline
    Move from March to May 2022 for delivering TGbe D2.0
  Review the updated guidelines for CRs until May

## Slide 3: Current TGbe Timeline
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sept 2020
D1.0 WG Comment Collection May 2021
D2.0 WG Letter Ballot Mar 2022
D3.0 LB Nov 2022
Initial Sponsor Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024
But TGbe motion to generate D2.0 and go to WG letter ballot failed
Concern was that there are still a lot of unresolved comments
We are here*

## Slide 4: Current CR Status
Undergoing a WG comment collection on TGbe D1.0
  All PHY comments & ~90% of Joint comments are resolved (40 CIDs unresolved)
    Joint calls have more than enough bandwidth to resolve these comments by May
  A little more than 65% of MAC ad-hoc comments are already resolved
    Resolution pace (in terms of #CIDs) has recovered recently
      Prioritization of docs based on # of CIDs, offline discussions, efficient use of ad-hoc calls, etc.
    But in order to meet the May deadline we need to do a little bit better
      ~1000 MAC comments to resolve over 10 MAC conf calls and sessions in the May hybrid F2F
        And, of course, during the scheduled Joint conf calls

## Slide 5: Future Planning
Continue the CC36 CR process until May’22
  Following the guidelines provided in item 10 of 984r13, noting that:
    The guideline has been amended to account for lesson’s learned during this period, and to streamline the process of dealing with “quarantined” CIDs.
In addition, the TG leadership is expected to:
  Follow up with POCs/assignees to get the document numbers and ETAs for the documents that contain comment resolutions for the CIDs assigned to them
    Promoting documents that contain large number of CIDs
  Re-assign CIDs to other volunteers (as tracked in the spreadsheet) if the CID is assigned to a non-responsive assignee or the assignee missed the pre-established deadline