## Slide 1: TGbc Closing Report
Date: 2022-05-13
Authors:

## Slide 2: Abstract
Closing report for IEEE 802.11 TGbc (Broadcast Services) for May 2022.

## Slide 3: Meeting Goals & Accomplishments of the week
Goal for the week:
Work on comment resolutions received against D3.0
Leadership elections
Review of timeline
Accomplishments
Group met 5 times this week
Resolved 87 technical comments
  72 resolutions approve;
  15 resolutions ready for motion;
117 CIDs remaining
  80 editorial
  37 technical
Current TGbc leadership (re)confirmed
Timeline approved
Owning Ad-hoc | Count of CID
EDITOR | 72
2022-05-13 - approved | 72
CHAIR | 132
2022-05-24 - ready for motion | 15
Unresolved | 117
TOTAL | 204

## Slide 4: TGbc Leadership Elections / Confirmation votes
TG Chair (appointed by WG Chair and subject to reconfirmation by WG)
Marc Emelmann
TG Vice Chairs (vote in TG: 31-0-2; subject to WG confirmation)
Stephen McCann
Hiroshi Morioka
Secretary (confirmation vote: unanimous consent)
Xiaofei Wang
Technical Editor (confirmation vote: unanimous consent)
Carol Ansley

## Slide 5: TGbc schedule
January 2019 First meeting as a task group
June 2020 Call for comments on D0.1
November 2020 Initial WGLB (D1.0)
September 2021 D2.0 WG Recirculation LB
March 2022 D3.0 WG Recirculation LB
May intermediate version D3.1
Editorial reviews: MEC & MDR on D3.1
June Form SAB Pool
July 2022 D4.0 WG Recirculation LB
EC Request for conditional approval
Jul -- Sep 2022 D4.0-unchanged WG Recirculation LB (if required)
August Initial SAB (D4.0)
January 2023 Recirculation SAB
July 2023 EC approval to RevCom
July 2023 RevCom/SASB approval

## Slide 6: Plans for Next Meeting & Upcoming Telcos
Telcos
Continue comment resolution
Upcoming meeting
Completion of comments
WG recirculation ballot on D4.0
Weekly Telcos
Tuesdays, 10:00h – 11.00h ET (1 hours)

## Slide 7: References
Agenda for this week: 11-22/0585
Meeting / Chair’s Slide Deck: 11-22/0586
Meeting minutes: 11-22/0774
Snapshot Slide: 11-22/0587
Closing report: 11-22/0588
TGbc Motion Booklet: 11-18/2123
TGbc Selection Procedure: 11-19/0135
TGbc Functional Requirements: 11-19/0151
TGbc UseCase Document: 11-19/268