## Slide 1
Task Group BF May 2022 Closing Report
Date: 2022-03-14
Authors:
Name | Affiliation | Address | Phone | Email
Tony Xiao Han | Huawei Technologies Co., Ltd. | F3, Huawei Base, Shenzhen, China |  | Tony.hanxiao@huawei.com

## Slide 2: Abstract
This document is the closing report for Task Group BF for the May 2022 session.

## Slide 3: TGbf (WLAN Sensing)– March 2022
Progress during May 2022 meeting
  3 teleconference calls for TGbf (May 10, 11, 16)
  Presentation of technical submissions (e.g., Feedback type, general protocol and procedure, DMG/EDMG, PDT……)
Goals for the next two months
  Presentation of technical submissions (e.g., PDT, comment resolution, Feedback type, general protocol and procedure ……)
  Further developing the Draft 0.1-1.0 (Requested 3 calls per week)

## Slide 4: TGbf Timeline (Updated)
  PAR approved Sep 2020
  First TG meeting Oct 2020
  Comment Collection (D0.1) Jan 2022Mar 2022
   April 2022
  Initial Letter Ballot (D1.0) Jul 2022 Sep 2022
  Recirculation LB (D2.0) Jan 2023
  Recirculation LB (D3.0) May 2023
  Recirculation LB (D4.0) July 2023
  Initial SA Ballot (D4.0) Sep 2023
  Final 802.11 WG approval July 2024
  802 EC approval July 2024
  RevCom and SASB approval Sep 2024
Timeline (Comment collection for D0.1)
Early-mid May
  Identify topics, PoCs, and volunteers
May 20th
  Comment collection closes
Week of May 23rd
  Editor classifies comments and share them with TTTs
June 3rd
  Deadline for comment assignment
Note: Initial letter ballot (D1.0) currently set for September 2022.
  Chair will discuss D1.0 timeline with the group at a later date.

## Slide 5: Teleconference Times
  Confirmed:
    March 2022 IEEE Plenary (March 7-15) (Deadline for contributions to pass motion and be included in D0.1)
    March 8 (Tuesday), 9am - 11:00am ET
    March 9 (Wednesday), 10pm - 11:59pm ET (Not sure if this slot is ok for Plenary and Interim? It’s ok!!)
    March 11 (Friday), 9am - 11:00am ET
    March 14 (Monday), 9am - 11:00am ET
    March 17 (Thursday), 23 ：00 - 01:00am ET
    March 21 (Monday), 10am - 12:00pm ET March 22 (Tuesday), 10am - 12:00pm ET
    March 24 (Thursday), 23：00 - 01:00am ET
    March 28 (Monday), 10am - 12:00pm ET March 29 (Tuesday), 10am - 12:00pm ET
    March 31 (Thursday), 23：00 - 01:00am ET
    April 7 (Thursday), 10am - 12:00pm ET
    April 11 (Monday), 10am - 12:00pm ET April 12 (Tuesday), 10am - 12:00pm ET
    April 14 (Thursday), 23：00 - 01:00am ET
    April 18 (Monday), 10am - 12:00pm ET April 19 (Tuesday), 10am - 12:00pm ET
    April 21 (Thursday), 23：00 - 01:00am ET
    April 25 (Monday), 10am - 12:00pm ET April 26 (Tuesday), 10am - 12:00pm ET
    April 28 (Thursday), 23：00 - 01:00am ET
    May 5 (Thursday), 10am - 12:00pm ET
  ** Note:
  1. when conflict with CAC, the call will be changed from 10am -12:00pm to 11am -12:00pm (March - May 2022 CAC calls (TBD): )
  2. Thursday 23:00 - 01:00am ET (Thursday 20：00 – 22:00 PT, Friday 11am-13:00 in China, Friday 5am-7am in Israel, Friday 4am – 6am in Central Europe), and Sang Kim will help to take the minutes for these slots.
 | Time Central Europe Warsaw | Eastern Time | Pacific time | Beijing Time
AM1 | 08:00-10:00 | 02:00-04:00 | 23:00-01:00 | 14:00-16:00
AM2 | 10:30-12:30 | 04:30-06:30 | 01:30-03:30 | 16:30-18:30
PM1 | 13:30-15:30 | 07:30-09:30 | 04:30-06:30 | 19:30-21:30
PM2 | 16:00-18:00 | 10:00-12:00 | 07:00-09:00 | 22:00-00:00
Evening 1 | 19:30-21:30 | 13:30-15:30 | 10:30-12:30 | 01:30-03:30
Evening 2 | 22:00-00:00 | 16:00-18:00 | 13:00-15:00 | 04:00-06:00

## Slide 6
Teleconference Times
  Confirmed:
  May interim 2022 (May 8-17)
    May 10 (Tuesday), 9：00 - 11:00 ET
    May 11 (Wednesday), 22：00 - 00:00 ET
    May 13 (Friday), 9：00 - 11:00 ET
    May 16 (Monday), 9：00 - 11:00 ET
  ** Note:
  1. when conflict with CAC, the call will be changed from 10am -12:00pm to 11am -12:00pm (March - May 2022 CAC calls (TBD): )
  2. Thursday 23:00 - 01:00am ET (Thursday 20：00 – 22:00 PT, Friday 11am-13:00 in China, Friday 6am-8am in Israel, Friday 5am – 7am in Central Europe), and Sang Kim will help to take the minutes for these slots.
  Confirmed:
    May 19 (Thursday), 23：00 - 01:00 ET
    May 24 (Tuesday), 10：00 - 12:00 ET
    May 26 (Thursday), 23：00 - 01:00 ET
    May 31 (Tuesday), 10：00 - 12:00 ET
    June 2 (Thursday), 23：00 - 01:00 ET
    June 6 (Monday), 10：00 - 12:00 ET
    June 7 (Tuesday), 10：00 - 12:00 ET
    June 9 (Thursday), 23：00 - 01:00 ET
    June 13 (Monday), 10：00 - 12:00 ET
    June 14 (Tuesday), 10：00 - 12:00 ET
    June 16 (Thursday), 23：00 - 01:00 ET
    June 20 (Monday), 10：00 - 12:00 ET
    June 21 (Tuesday), 10：00 - 12:00 ET
    June 23 (Thursday), 23：00 - 01:00 ET
    June 27 (Monday), 10：00 - 12:00 ET
    June 28 (Tuesday), 10：00 - 12:00 ET
    June 30 (Thursday), 23：00 - 01:00 ET
    July 4 (Monday), 10：00 - 12:00 ET
    July 5 (Tuesday), 10：00 - 12:00 ET
    July 7 (Thursday), 23：00 - 01:00 ET