## Slide 1: REVme Closing Report – May 2022
Date: 2022-05-16
Authors:

## Slide 2: Work Completed
Continued with LB 258 comment resolutions
No changes to timeline. Still trying to go to LB recirculation out of July meeting
Approved adhoc in August 23 – 25, 2022 in San Diego, US or Cambridge, UK

## Slide 3: Plans for July
Teleconferences:
  Monday/Friday calls through May/June:
  May 27, June 3, 6, 13, 17, 20, 24, 27 (with motions) – 10am ET, 2hrs
Continue comment resolution on initial LB
NOTE: Priority will be on Review/Discuss comments and the current submission queue.

## Slide 4: August Adhoc
Approve a TGme ad-hoc meeting on August 23-25, 2022 in US or UK for the purpose of REVme comment resolution and consideration of document submissions.
TG vote result: Unanimous (25 attendees). Passes. [Moved: Jon Rosdahl, Second: Mark Hamilton]
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 4