## Tabelle2
CID | Date | SA PIN | Name | Comment | Category | Page | Subclause | Line | Proposed Change | MBS | assigend | decision | resolution | action
1 | 06/14/2022 21:42:00 GMT | 109626 | Robert Sosack | The definition of PLCP was lost between D2.0 and D2.1. The definition of PLCP couldn't be found in the existing standard. Add "Physical Layer Convergence Protocol" into this sentence. | General | 14 | 32.3.1 | 7 | ...which a Physical Layer Convergence Protocol (PLCP) service data unit... | 0 |  | revise | implement the changes in doc. 11-22-1108r3 | done
2 | 06/24/2022 14:45:45 GMT | 75371 | Matthias Wendt | Add "optical" to make the sentence clear. | Technical | 13 | 32.1 | 13 | LC systems transmit on an optical wavelengths within the 800 nm to 1000 nm band. | 0 |  | accept |  | done.
3 | 06/24/2022 14:50:27 GMT | 75371 | Matthias Wendt | The formulation "modulate the solid-state lighting (SSL) device" seems unclear. Add the supply current as means for modulating the light flux and a reference to the figure. | Technical | 14 | 32.3.2 | 15 | change to: "An LC PHY uses an LC intermediate frequency (IF) in the frequency range of near direct current (DC) up to a few hundred MHz to modulate the supply current of a solid-state lighting (SSL) device (see Figure 32-2) in order to transport protocol data units (PDUs). | 0 |  | accept |  | done, since text was replaced with 11-22-1108r3
4 | 06/24/2022 14:55:13 GMT | 75371 | Matthias Wendt | In the RX and TX diagrams (Figure 32-1) most references are with arrows but for "LC IF signal" | Editorial | 14 | 32.3.2 | 23 | In Figure 32-1 change also the two reference lines to arrows for "LC IF signal" in the RX and TX diagrams | 0 |  | accept | arrow should be the same as for other signals | done
5 | 06/24/2022 14:57:09 GMT | 75371 | Matthias Wendt | Figure 32-1 and the related title are split by a page break | Editorial | 14 | 32.3.2 | 23 | Move figure to next page | 0 |  | accept |  | done, with 11-22-1108r3
6 | 06/27/2022 17:42:20 GMT | 95193 | CHONG HAN | the PPDU is available in 802.11-2020. 'Unit' is missing in the title. | Editorial | 13 | 32.1.2 | 26 | shorten the title to 'PPDU formats' | 0 |  | accept |  | done
7 | 06/27/2022 17:42:20 GMT | 95193 | CHONG HAN | Clear Channel Assessment is defined by 802.11-2020. | Editorial | 19 | 32.3.6 | 23 | shorten the title to 'CCA for LC' | 0 |  | accept |  | done, since text was replaced with 11-22-1108r7
8 | 06/27/2022 17:42:20 GMT | 95193 | CHONG HAN | reference to the equation is wrong | Editorial | 16 | 32.3.4 | 28 | correct the reference to the equation | 0 |  | revise | change "(1)" into "(32-1) | done, since text was replaced with 11-22-1108r8
9 | 06/27/2022 17:42:20 GMT | 95193 | CHONG HAN | Fig. should write 'Figure.' | Editorial | 19 | 32.3.6.1 | 32 | Fig. should write 'Figure.' | 0 |  | accept |  | done. To be revised due to new direct conversion TX.
10 | 06/27/2022 17:42:20 GMT | 95193 | CHONG HAN | The line 18-19 are not illustrated in Figure 32-5. The text was agreed to be deleted as CID50 in 678r7 | Technical | 20 | 32.3.6.2 | 18-19 | delete line 18-19 | 0 |  | accept |  | done.
11 | 06/27/2022 17:42:20 GMT | 95193 | CHONG HAN | fix the reference to subclause 32.3.5. The name is changed by TE in the D2.1. | Editorial | 22 | B4.37 | 3 in total | see comment | 0 |  | accept |  | done, since text was replaced with 11-22-1108r1
12 | 06/28/2022 06:58:20 GMT | 52241 | Bo Sun | The definition of LC STA is unclear. And the LC STA should provide all the stated functionalities. | Technical | 11 | 3.2 | 28 | Change the text to " A logical entity that consists of a singly addressable instance of ..." | 1 |  | revise | delete P11L27 ad L31-32 replace the definition text on P11L28-30 by "A station (STA) that operates in the light band with wavelengths in the range 800 nm to 1000 nm." | all done.
13 | 06/28/2022 07:03:11 GMT | 52241 | Bo Sun | The definition of LC STA is inconsistent with the LC STA definition in sub-clause 3.2 | Technical | 12 | 4.3.30 | 17 | Modify the statement to make it consistent with definition of LC STA and OFE in sub-clause 3.2 | 1 |  | revise | implement the changes in doc. 11-22-1108r3 | done
14 | 06/28/2022 07:19:26 GMT | 52241 | Bo Sun | It seems the LC STA has no individual LC MAC function, other than HT, VHT and HE MAC. While in the subclauses to describe HT, VHT or HE MAC, there's no statement to support LC PHYs. | General | 12 | 4.3.30 | 19 | Clarify the support of LC PHYs in corresponding MAC sections. Or define a converging function in LC Low MAC or PHY to pretend to be a HT, VHT or HE PHY | 1 |  | revise | insert after P12L20 "The LC HT mode PHY is substantially similar to the HT PHY in Clause 19 (High throughput (HT) PHY specification) , see 32.3.3.2 (LC High Throughput (LC HT) mode). The LC VHT mode PHY is substantially similar to the VHT PHY in Clause 21 (Very high throughput (VHT) PHY specification) , see 32.3.3.3 (LC Very High Throughput (LC VHT) mode). The LC HE mode PHY is substantially similar to the HE PHY in Clause 27 (High-efficiency (HE) PHY specification) , see 32.3.3.4 (LC High efficiency (LC HE) mode)." check that Clause names are consistent with latest Revme | done, since text was replaced with 11-22-1118r1
15 | 06/28/2022 08:07:00 GMT | 13492 | Stephen McCann | The 1st sentence references "Clause 31" that is self-referential and is not required. | Technical | 13 | 31.1 | 3 | Change the initial part of the first sentence to "An LC STA supports the SME, MAC and MLME functions defined in this clause, in addition to the MAC functions..." | 0 |  | accept |  | done.
16 | 06/28/2022 08:07:00 GMT | 13492 | Stephen McCann | There are some aspects of clause 10 that when inhertied by a LC STA don't make sense. A good example is clause 10.35 (REVme D1.2). I don't understand how a LC STA could perform antenna selection in the same way as a RF device? Another example is beamforming. | Technical | 13 | 31.1 | 4 | Change the text "in Clause 10 (MAC sublayer functional description)" to "in Clause 10 (MAC sublayer functional description) with the exception of clauses 10.33, 10.34 and 10.35". | 0 |  | reject | this point has been discussed in TGbb previously and it has been checked that those MIMO techniques work. We can have a direct discussion about this. | nothing done.
17 | 06/28/2022 08:07:00 GMT | 13492 | Stephen McCann | The acronym WLAN needs to be expanded up, as it is a definition. | Editorial | 11 | 3.1 | 19 | Change "WLAN" to "Wireless Local Area Network (WLAN)" | 0 |  | revise | remove P11L19 | done
18 | 06/28/2022 08:07:00 GMT | 13492 | Stephen McCann | The definition of light medium references LC that also mentions light medium and is therefore self-referential. This needs to be re-written. | Technical | 11 | 3.1 | 20 | Change the definition to "light medium: The wireless medium (WM) used to implement the transfer of protocol data units (PDUs) between peer optical front-end entities of a wireles local area network (WLAN)." | 0 |  | revise | same as CID44 Change to "The wireless medium (WM) over which protocol data units (PDUs) are exchanged between light communications (LC) stations (STAs)." | done
19 | 06/28/2022 16:15:24 GMT | 109465 | Nancy Lee | Tie example Fig 32-1 to the entities defined in 4.3.30 | Technical | 14 | 32.3.2 | 18 | state that LC PHY TX is essentially an HT/VHT/HE STA and the two boxes together are an LC STA, and that the light interface is transparent (functions like a wireless cable) |  |  | revise | add after P14L17 : "Because the LC channel is nearly transparent, it functions like a wireless cable." Add after P14L22: "In this example, the LC PHY TX/RX are HT/VHT/HE PHY TX/RX where the RF antennas are replaced by LC optical antennas." | done
20 | 06/28/2022 16:15:24 GMT | 109465 | Nancy Lee | wrong subclause number | Editorial | 15 | 32.3.3.2 | 24 | 32.3.2.2 should be 32.3.3.2 |  |  | accept |  | done, since text was replaced with 11-22-1108r4
21 | 06/28/2022 16:15:25 GMT | 109465 | Nancy Lee | add that 2.4 GHz operation of HT STA is not used by LC | Technical | 15 | 32.3.3.2 | 26 | insert "2.4 GHz operation of HT PHY does not apply to the LC HT PHY mode." |  |  | revise | accept comment as is for HT PHY insert on P16L10 "2.4 GHz operation of VHT PHY does not apply to the LC VHT PHY mode." | done, since text was replaced with 11-22-1108r5
22 | 06/28/2022 16:15:25 GMT | 109465 | Nancy Lee | wrong subclause number | Editorial | 16 | 32.3.3.3 | 8 | 32.3.2.3 should be 32.3.3.3 |  |  | revise | replace "except when the specifications in 32.3.2.2 (LC High Throughput (LC HT) mode) supersede corresponding text in Clause 19 (High-throughput (HT) PHY specification)." by "except for requirements in Clause 19 (High-throughput (HT) PHY specification) that are superseded by the remainder of this subclause. | done, since text was replaced with 11-22-1108r7
23 | 06/28/2022 16:15:25 GMT | 109465 | Nancy Lee | add that 2.4 GHz operation of HE STA is not used by LC | Technical | 16 | 32.3.3.3 | 10 | insert "2.4 GHz operation of HE PHY does not apply to the LC HE PHY mode." |  |  | accept |  | done, since text was replaced with 11-22-1108r8
24 | 06/28/2022 16:15:25 GMT | 109465 | Nancy Lee | wrong subclause number | Editorial | 16 | 32.3.3.4 | 20 | 32.3.2.4 should be 32.3.3.4 |  |  | revise | replace P16L8 "except when the specifications in 32.3.2.3 (LC Very high throughput (LC HT) mode) supersede corresponding text in Clause 21 (Very High throughput (VHT) PHY specification)." by "except for requirements in Clause 21 (Very high throughput (VHT) PHY specification) that are superseded by the remainder of this subclause. replace P16L20 "except when the specifications in 32.3.2.4 (LC High efficiency (LC HE) mode) supersede corresponding text in Clause 27 (High efficiency (HE) PHY specification)." by "except for requirements in Clause 27 (High Efficiency (HE) PHY specification) that are superseded by the remainder of this subclause. | done, since text was replaced with 11-22-1108r10
25 | 06/28/2022 16:15:25 GMT | 109465 | Nancy Lee | paragraph corresponds to elements deleted from Fig 32-5 | Technical | 20 | 32.3.6.2 | 18 | delete lines 18-19 |  |  | accept |  | done
26 | 06/28/2022 18:47:49 GMT | 4181 | Peter Ecclesine | Table E-6 Operating claasses in China is mis-numbered | Editorial | 28 | E.1 | 2 | Renumber to E-6. | 0 |  | accept |  | done, since text was replaced with 11-22-1108r2
27 | 06/28/2022 20:47:49 GMT | 84143 | Volker Jungnickel | clarify abstract | Technical | 2 | 0. abstract | 2 | add the word "transparent" after "enable" | 0 |  | accept |  | done
28 | 06/28/2022 20:49:52 GMT | 84143 | Volker Jungnickel | mention concrete min./max values for data rates | Technical | 2 | 0. abstract | 3 | replace "achieve minimum single-link throughput of 10 Mb/s" by "a minimum and maximum throughput of 6.5 Mbit/s and 9.6 Gbit/s" | 0 |  | revise | replace "achieve minimum single-link throughput of 10 Mb/s" by "a minimum and maximum throughput of 10 Mb/s and 9.6 Gb/s, respectively." | done
29 | 06/28/2022 20:56:36 GMT | 84143 | Volker Jungnickel | reconsider end of the abstract which is meaningless (LEDs do not interoperate, rather 802.11 LC STAs with OFEs having different mobulation bandwidths | Technical | 2 | 0. abstract | 5 | replace "solid state light sources with different modulation bandwidths" by "802.11 LC STAs with optical frontends having different bandwidths" | 0 |  | revise | implement the changes in doc. 11-22-1108r3 | done. But there is nothing related to the abstract in 1108r3.
30 | 06/28/2022 20:58:39 GMT | 84143 | Volker Jungnickel | change wording | Editorial | 7 | 00. Introduction | 7 | replace "for" by "which enable" | 0 |  | reject |  | nothing done.
31 | 06/28/2022 21:01:23 GMT | 84143 | Volker Jungnickel | I have some doubts this is required. If we use a MIMO STA with one antenna using RF and equip the other antenna with an OFE, the same is reached. Better update the section on MIMO with such an exemplary implementation. | Technical | 12 | 4.3.30 | 21 | preplace "is" on P12L23 by "or mixed use of RF/LC configurations are" and add exemplary implementation option in 32.3.5. | 0 |  | reject | withdrawn by the commenter | done, since text was replaced with 11-22-1118r2
32 | 06/28/2022 21:08:26 GMT | 84143 | Volker Jungnickel | 802.11bb proposes a very enery inefficient HW architecture which is in no way acceptable for implementation at mobile devices | General | 14 | 32.3.2 | 13 | revise the LC light interface and add a baseband implementation proposal which is interoperable with the up-/down conversion HW architecture | 1 |  | revise | implement the changes in doc. 11-22-1108r3 | done
33 | 06/28/2022 21:09:43 GMT | 84143 | Volker Jungnickel | correct wording | Editorial | 14 | 32.3.2. | 18 | add "an" before "LC" | 0 |  | accept |  | done, since text was replaced with 11-22-1108r3
34 | 06/28/2022 21:11:25 GMT | 84143 | Volker Jungnickel | correct grammar | Editorial | 14 | 32.3.2 | 21 | add comma after e.g. | 0 |  | accept |  | done, since text was replaced with 11-22-1108r3
35 | 06/28/2022 21:15:28 GMT | 84143 | Volker Jungnickel | correct the reference and check circular reference | Technical | 15 | 32.3.3.2 | 24 | change into 32.3.3.2 and reformulate so that clause does not reference itself (circular reference) | 0 |  | revise | same as CID22 replace "except when the specifications in 32.3.2.2 (LC High Throughput (LC HT) mode) supersede corresponding text in Clause 19 (High-throughput (HT) PHY specification)." by "except for requirements in Clause 19 (High-throughput (HT) PHY specification) that are superseded by the remainder of this subclause. | done, since text was replaced with 11-22-1108r6
36 | 06/28/2022 21:19:22 GMT | 84143 | Volker Jungnickel | correct 32.3.3.3. and avoid circular reference | Technical | 16 | 32.3.3.3 | 8 | correct into 32.3.3.3. and avoid circular reference | 0 |  | revise | same as first part of CID24 replace P16L8 "except when the specifications in 32.3.2.3 (LC Very high throughput (LC HT) mode) supersede corresponding text in Clause 21 (Very High throughput (VHT) PHY specification)." by "except for requirements in Clause 21 (Very high throughput (VHT) PHY specification) that are superseded by the remainder of this subclause. | done, since text was replaced with 11-22-1108r9
37 | 06/28/2022 21:27:07 GMT | 84143 | Volker Jungnickel | correct into 32.3.3.4. and avoid circular reference | Technical | 16 | 32.3.3.4 | 20 | change into 32.3.3.4. and avoid circular reference | 0 |  | revise | same as second part of CID24 replace P16L20 "except when the specifications in 32.3.2.4 (LC High efficiency (LC HE) mode) supersede corresponding text in Clause 27 (High efficiency (HE) PHY specification)." by "except for requirements in Clause 27 (High Efficiency (HE) PHY specification) that are superseded by the remainder of this subclause. | done, since text was replaced with 11-22-1108r11
38 | 06/28/2022 21:29:35 GMT | 84143 | Volker Jungnickel | improve readablity | Technical | 16 | 32.3.4 | 24 | : add a graphics that shows the channelization in 5/6 Ghz band and the related one in LC IF band | 0 |  | revise | replace text from P16L33-P17L15 by the text proposed in doc. 11-22-1087r1 to the draft Insert a subclause into the MAC section that explains requirements on channelization. In particular explain which channels shall not be used (Volker). | done
39 | 06/28/2022 21:31:47 GMT | 84143 | Volker Jungnickel | add a paragraph for mixed RF/LC operations in 802.11 using MT chains and MR chains | Technical | 17 | 32.3.5. | 16 | as in comment | 0 |  | reject | withdrawn by the commenter | nothing done
40 | 06/28/2022 21:33:02 GMT | 5073 | Robert Stacey | Regarding the second sentence of the inserted text. The fact that it is a virtual point has already been established in the previous sentence. | Technical | 11 | 3.1 | 16 | Change "It is a virtual point representing" to "It represents" | 0 |  | revise | Change "It is a virtual point representing" to "The virtual point represents" | done
41 | 06/28/2022 21:34:31 GMT | 84143 | Volker Jungnickel | chenge "should" into "shall" as "should" would lead to non-functional implementations | General | 19 | 32.3.5. | 1 | as in comment | 1 |  | revise | replace P19L1-2 by "All LC optical TX antennas shall be synchronized to a common reference clock in a device that has more than one LC Optical TX antennas. All LC optical RX antennas shall be synchronized to a common reference clock in a device that has more than one LC Optical RX antennas." | done
42 | 06/28/2022 21:48:42 GMT | 5073 | Robert Stacey | "input to the receiver" and "output from the transmitter" are both ambiguous. Is the optical front-end not part of the transceiver? | Technical | 11 | 3.1 | 13 | Replace the first inserted sentence with "In systems using light communications, the antenna connector is the RF interface of the optical front-end." | 1 |  | revise | Replace P11L13: "the antenna connector is a virtual point representing the electrical input to the receiver from the output of the optical front-end, and the electrical output from the transmitter being used as input to the optical-front end" with "the antenna connector is a virtual point representing the RF interface of the optical front-end" | done
43 | 06/28/2022 23:12:06 GMT | 5073 | Robert Stacey | Expand acronyms on first use in each definition | Editorial | 11 | 3.1 | 22 | Change "LC" to "light communications (LC)" | 0 |  | accept |  | done
44 | 06/28/2022 23:16:10 GMT | 5073 | Robert Stacey | Simplify "used to implement the transfer of" | Editorial | 11 | 3.1 | 20 | Change to "that transfers". Or better yet, change definition to "The wireless medium (WM) over which protocol data units (PDUs) are exchanged between light communications (LC) stations (STAs). | 0 |  | revise | same as CID18 Change to "The wireless medium (WM) over which protocol data units (PDUs) are exchanged between light communications (LC) stations (STAs)." | done
45 | 06/28/2022 23:24:05 GMT | 5073 | Robert Stacey | While it's electrical, the signal has not yet been transmitted (the transmitted signal is electromagnetic). Also, "signal into optical power" is inaccurate. The conversion is from electrical signal to optical signal -- signal because we are transferring information -- and not from electrical signal to optical power. | Technical | 11 | 3.1 | 22 | Change definition to optical front-end (OFE): Optoelectronic module that, in a transmitter, converts an RF electrical signal to an optical signal, and, in the receiver, converts the optical signal to an RF electrical signal. | 0 |  | revise | Change definition to optical front-end (OFE): Optoelectronic module that, in a transmitter, converts an RF electrical signal to an intensity modulated optical signal, and, in the receiver, converts the intensity modulate optical signal to an RF electrical signal. | done
46 | 06/28/2022 23:34:32 GMT | 5073 | Robert Stacey | "An LC STA is a STA with an OFE": based on Figure 32-1, I don't think this is accurate. Figure 32-1 has modules called "LC Optical TX Antenna" and "LC Optical RX Antenna" that, in addition to the OFE, have RF up/down conversion. | Technical | 12 | 4.3.30 | 17 | Maybe something like: "An LC STA is an HT, VHT or HE STA where the RF antenna is replaced by an LC optical antenna." And then all we really need to do is define this "LC optical antenna" | 1 | Robert Stacey & Volker Jungnickel | revise | implement the changes in doc. 11-22-1108r3 | done
47 | 06/28/2022 23:41:46 GMT | 5073 | Robert Stacey | Invalid editing instruction -- see page 8 for valid options. | Editorial | 23 | E.1 | 5 | Change to a set of instructions, one for each table: "Change Table E-xx as follows:" | 0 |  | accept |  | done, since text was replaced with 11-22-1108r4
48 | 06/28/2022 23:48:05 GMT | 5073 | Robert Stacey | "LC transmission" should be "LC STA transmissions". Also, I wouldn't say it was mostly directional (that is a little bit like being mostly pregnant); it is directional.. | Technical | 19 | 32.3.6.2 | 35 | Change "LC transmission are mostly directional, ..." to "An LC STA transmission is directional, ..." | 0 |  | accept |  | done.
49 | 06/29/2022 00:12:53 GMT | 5073 | Robert Stacey | It is not clear what an "LC system" is in this context. Or what a "user" is in this context. Sounds a bit like an "LC system" is a BSS and a "user" is a STA. Let's try to use the terminology introduced in Clause 4 (of the base standard). Also, terms such as "minimize" are problematic since they imply some sort of guarantee and should be avoided. And, it is not clear why the number of users is relevant here anyway. | Technical | 19 | 32.3.6.2 | 36 | Replace the 2nd and 3rd sentence with "LC repetition is an optional feature in an LC AP that effectively extends the area covered by a transmission from a non-AP LC STA to include the area covered by the LC AP. LC repetition together with other mechanisms, such as the RTS/CTS mechanism defined in 10.3, might reduce collisions in an LC BSS." | 0 |  | accept |  | done.
50 | 06/29/2022 00:29:13 GMT | 5073 | Robert Stacey | Define LC repetition using normative verbs (may/should/shall). Also, some of the terminology used makes it difficult to understand what exactly needs to be implemented. For example, it talks about "when it detects a transmission". What does that mean? Detects a valid .11 signal? How long does this detection go on for? So is there some control logic required the looks for signals and switches on the repeat mechanism until it not longer detects the transmission and then stops the repeat mechanism? | Technical | 20 | 32.3.6.2 | 4 | Replace the 2nd and 3rd paragraph in 32.3.6.2 with "An LC AP may transmit at the Tx OFE a repeat of the signal it receives at the Rx OFE. The delay between the received signal and the transmitted signal shall be less than 1 us." | 1 |  | accept |  | done.
51 | 06/29/2022 00:36:55 GMT | 5073 | Robert Stacey | There is no "Light communications (LC) protocol" | Technical | 2 | 0. frontmatter | 6 | Change to "Light communications (LC)" (note capitalization) | 0 |  | accept |  | done