## Slide 1: IEEE 802.11 Jul 2022 Plenary IEEE 802.11 TGbd Closing Report
Chair: Bo Sun (ZTE)
Vice Chair: Hongyuan Zhang (NXP),
Joseph Levy (InterDigital)
Secretary: Yan Zhang (NXP)
Tech Editor: Yujin Noh (Senscomm)

## Slide 2: TGbd’s Progress during this plenary week
Before the week: the SA Recirculation Ballot for IEEE P802.11bd D5.0 was closed with 92% approval rate and 41 comments collected. All SA recirculation ballot comments were assigned.
One TGbd session was held in this week and 3 CR documents were presented with resolutions to 25 CIDs ready for motion.
Approved TGbd teleconference before Sep interim week
TGbd agenda and minutes for this week are as below:
  https://mentor.ieee.org/802.11/dcn/22/11-22-0849-02-00bd-tgbd-session-agenda-for-jul-plenary-2022.pptx
  https://mentor.ieee.org/802.11/dcn/22/11-22-1096-00-00bd-ieee-802-11bd-july-2022-plenary-meeting-minutes.docx
Goal of future TCbd work: process CRC comment resolution and prepare next round SA recirculation ballot

## Slide 3: TGbd Timeline (updated)
  PAR approved Dec 2018
  First TG meeting Jan 2019
  D0.1 Nov 2019
  D1.0 Letter Ballot Oct 2020
  D2.0 LB recirculation Jul 2021
  Form SA Ballot Pool Nov 1 to Nov 30, 2021
  D3.0 LB recirculation Dec 2021
  D4.0 LB recirculation Mar 2022
  D4.0 LB unchanged recirculation Apr 2022
  Initial SA Ballot (D4.0) Apr 2022
  Final 802.11 WG approval Nov 2022
  802 EC approval Nov 2022
  RevCom and SASB approval Dec 2022

## Slide 4: IEEE 802.11 TGbd TC Plan
Jul 26th, 2022, 10:00am ~ 11:59am, ET (all CRs presented)
Aug 9th, 2022, 10:00am ~ 11:59am, ET ( all CRs done)
Aug 23rd, 2022, 10:00am ~ 11:59am, ET
Sep 6th, 2022, 10:00am ~ 11:59am, ET