## Slide 1: REVme Closing Report – July 2022
Date: 2022-07-14
Authors:

## Slide 2: Work Completed
Continued with LB 258 comment resolutions
Will now proceed to recirculation LB out of September meeting.
Updated timeline

## Slide 3: Plans for September
Teleconferences:
  Monday calls through July/Aug:
  July 25, Aug 8, 15, 29 with motions – 10am ET, 2hrs
  August adhoc – mixed mode:
    Location: San Diego, CA
    Dates: Aug 23-25
Continue comment resolution on initial LB
NOTE: Priority will be on Review/Discuss comments.

## Slide 4: TGme Timeline
Feb 2021 – PAR Approval
March 2021– Initial meeting, issue comment collection on IEEE Std 802.11-2020 (if published)
March 2021 – Draft 0.00 available
May 2021 – Process CC input, 11ax, 11ay, 11ba integration begins
Nov 2021 – Initial D1.0 WG Letter ballot
Sep 2022 – D2.0 Recirculation LB
Mar 2023 – D3.0 Recirculation LB (11az + other amendments <11bc, 11bd, 11bb> )
Sep 2023 – D4.0 Recirculation (<other amendments – if Jul>)
Nov 2023 – D5.0 Initial SA Ballot
Mar 2024 – D6.0 Recirculation SA Ballot
May 2024 – D7.0 Recirculation SA Ballot
Jun 2024 – D7.0 Recirculation SA Ballot (clean recirculation)
Sep 2024 – RevCom/SASB Approval