## Slide 1: TGbe September 2022 Closing Report
Date: 2022-09-15
Authors:

## Slide 2: TGbe (Extremely High Throughput)
TGbe had scheduled 12 sessions during the July plenary
  Five Joint calls, and seven parallel MAC/PHY calls
    Discussed comment resolution documents and a couple of technical submissions
      Around 2230 comments from LB266 are resolved (~55% of total, see figure for more details)
        Of which ~650 comments were resolved during this plenary
    Resolved comments on the TGbe coexistence assessment (CA) document
  Instructed the editor to generate IEEE802.11 TGbe D2.2
    TGbe D2.2 is expected to be available by beginning of October’22
Agenda is available in 11-22/1246r22
  Future Teleconference Plan is provided in the next slide
Motions List is available in 1038r15
Goals for November:
  Hold a MAC ad-hoc meeting in Bangkok, Thailand (11-12 November 2022)
  Aim at completing comment resolutions for LB266
CID Distribution (~4120)
16%
73%
11%
PHY
MAC
JOINT

## Slide 3: Teleconference Plan
Sept 21 (Wednesday) – Joint 10:00-12:00 ET
Sept 22 (Thursday) – MAC 10:00-12:00 ET
Sept 26 (Monday) – MAC/PHY 19:00-21:00 ET
Sept 28 (Wednesday) – MAC 10:00-12:00 ET
Oct 03-07 (Mon-Fri) - No Conf Calls Holiday
Oct 12 (Wednesday) – Joint 10:00-12:00 ET
Oct 13 (Thursday) – MAC 10:00-12:00 ET
Oct 17 (Monday) – MAC/PHY 19:00-21:00 ET
Oct 19 (Wednesday) – MAC 10:00-12:00 ET
Oct 26 (Wednesday) – Joint (Motions) 10:00-12:00 ET
Oct 27 (Thursday) – MAC 10:00-12:00 ET
Oct 31 (Monday) – MAC/PHY 10:00-12:00 ET
Nov 02 (Wednesday) – MAC 10:00-12:00 ET

## Slide 4: TGbe Timeline And Status
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sep 2020
D1.0 WG Comment Collection May 2021
D2.0 WG Letter Ballot May 2022
D3.0 Letter Ballot Nov 2022
Initial SA Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024