## Slide 1: TGbc Closing Report
Date: 2022-09-15
Authors:

## Slide 2: Abstract
Closing report for IEEE 802.11 TGbc (Broadcast Services) for September 2022.

## Slide 3: Meeting Goals & Accomplishments of the week
Goals for the week:
Resolve all comments received from LB268
Approve report to EC on requesting unconditional approval for SA Ballot
Accomplishments
Goals achieved !
Reviewed timeline
Passed motions to
  Approve report to the EC for unconditionally moving forward to SA Ballot
  Reaffirm the TGbc CSD
  Note: TGbc does not change the Phy and does not have a CAD; no reaffirmation required

## Slide 4: TGbc schedule (revised)
January 2019 First meeting as a task group
June 2020 Call for comments on D0.1
November 2020 Initial WGLB (D1.0)
September 2021 D2.0 WG Recirculation LB
March 2022 D3.0 WG Recirculation LB
May intermediate version D3.1
June Form SAB Pool
July Editorial reviews completed: MEC & MDR on D3.1
D4.0 WG Recirculation LB
September 2022 WG request EC for unconditional approval to forward
draft D4.0 to SA ballot
Oct 4th EC telco EC approval to go to SA Ballot (unconditional)
Oct. 6th 2022 Initial SA Ballot (D4.0), Start of
March 2023 Second SA Ballot
July 2023 Third SA Ballot
September 2023 EC approval to RevCom
December 2023 RevCom/SASB approval

## Slide 5: Motion for WG (TGbc CSD Re-Affirmation)
Re-affirm the P802.11bc CSD in in https://mentor.ieee.org/802-ec/dcn/18/ec-18-0250-00-ACSD-p802-11bc.pdf
Moved on behalf of TGbc/Second: Marc Emmelmann / xxx
Result: Yes: xx, No: xx, Abstain: xx (Motion passes/fails)
[TGbc: Moved: Stephen McCann, 2nd: Abhi Patil, Result: 6/0/0]

## Slide 6: Motion for WG (TGbc Unconditional SA Ballot)
Approve document 11-22/1405r2 as the report to the IEEE 802 Executive Committee (EC) on the requirements for unconditional approval to forward P802.11bc D4.0 to SA Ballot, and
Request the IEEE 802 EC to unconditionally approve forwarding P802.11bc D4.0 to SA ballot.
Moved on behalf of TGbc/Second: Marc Emmelmann / xxx
Result: Yes: xx, No: xx, Abstain: xx (Motion passes/fails)
[TGbc: Moved: Stephen McCann, 2nd: Abhi Patil, Result: 6/0/0]

## Slide 7: Plans for Next Meeting & Upcoming Telcos
Telcos
Assign & resolve comments received from First SA Ballot
Upcoming meeting
Resolve comments received from First SAB on D4.0
Weekly Telcos (dates to be announced; likely the week before the November meeting)
Tuesdays, 10:00h – 11.00h ET (1 hours)

## Slide 8: References
Agenda for this week: 11-22/1299
Meeting / Chair’s Slide Deck: 11-22/1300
Meeting minutes: 11-22/1406
Snapshot Slide: 11-22/1407
Closing report: 11-22/1408
TGbc Motion Booklet: 11-18/2123
TGbc Selection Procedure: 11-19/0135
TGbc Functional Requirements: 11-19/0151
TGbc UseCase Document: 11-19/268