## Slide 1: P802.11az Report to EC on Conditional Approval to go to REVcom
Date: 2022-09-13
Authors:

## Slide 2: Introduction
This document contains the report to the IEEE 802 Executive Committee in support of a request for conditional approval to send IEEE P802.11az D7.0 to REVcom.
R0 – Initial draft.
R1 -

## Slide 3: Standards Association (SA) Ballot Results – P802.11az
Ballot Close Date | Title | Ballot Type | Pool | Return | %Return | Abstain | %Abstain | Approve | Disapprove | %Approve
Nov.–05-2021 | Initial SA ballot for D4.0 | Technical | 122 | 97 | 79% | 5 | 5% | 86 | 6 | 93%
Jun.-09-2022 | First Recirculation Ballot for TGaz draft 5.0 | Recirculation | 122 | 102 | 83% | 5 | 4% | 91 | 6 | 93%
Sep.-07-2022 | Second Recirculation Ballot for TGaz draft 6.0 | Recirculation | 122 | 103 | 84% | 4 | 3% | 98 | 1 | 98%

## Slide 4: SA Ballot Comments – P802.11az
Ballot Close Date | Title | Total Number of Comments received (Yes and No votes)
Nov.–05-2021 | Initial SA ballot for P802.11az draft D4.0 | 364 (166T, 6G, 192E)
Jun.-09-2022 | First Recirculation SA Ballot for P802.11az draft 5.0 | 65 (36T, 2G, 27E)
Sep.-07-2022 | Second Recirculation SA Ballot for P802.11az draft 6.0 | 21 (0T, 0G, 21E)

## Slide 5: Unsatisfied Technical comments by commenter
Voter | Initial | 1st Re | 2nd Re | Comment topic | Total
None |  |  |  | No technical unsatisfied comments | 

## Slide 6: IEEE-SA Mandatory Coordination
Coordination Entity | Draft | Date | Status
IEEE-SA Editorial (MEC) | D3.0 | July 2021 | “Meets all editorial requirements.”
Quantities, Units and Letter Symbols (SCC14) |  |  | Not required
Terms and Definitions (SCC10) |  |  | Not required
Registration Authority Committee (RAC) |  |  | Not Required

## Slide 7: P802.11az Timeline
Report to EC for conditional approval to proceed to RevCom | 2022-09-16
2nd Recirculation on D7.0 | 2022-09-20 – 2022-09-30
Comment Response Notification | 2022-09-30
Post to RevCom by | 2022-10-13