## Slide 1: P802.11bb Report to EC on Approval to go to SA Ballot
Date: 2022-10-03
Authors:

## Slide 2: Introduction
This document contains the report to the IEEE 802 Executive Committee in support of a request for conditional approval to send IEEE P802.11bb to SA Ballot.
The doc. 11-22/1593r2 document was approved during the interim session of the 802.11 working group on September 16, 2022.
  WG motion results: Y/N/A 57-1-19
doc. 11-22/1593r3 adds motion results

## Slide 3: Status Summary
The TGbb Draft has gone through 3 WG Letter Ballots
Draft 1.0 was the first to achieve > 75% needed for an approved draft
The WG Letter Ballot on D3.0
  99% approval rate considering post-ballot vote changes
  Did not result in any new disapprove votes
  14 new “must be satisfied comments” were received.
  29 new comments came from “approve voters”
  The TG decided create a D4.0 to address the comments to perfect the draft; Motion to started WG Letter Ballot on D4.0 passed during September 2022 Interim Meeting
The TG has resolved 510 comments received on drafts 1.0 to 3.0.

## Slide 4: 802.11 WG Letter Ballot Results – P802.11bb
Ballot ID | Ballot Close Date | Title | Ballot Type | Pool | Return | %Return | Abstain | %Abstain | Approve | Disapprove | %Approve
LB260 | 12 Jan. 2022 | Technical TGbb Draft 1.0 | Technical | 485 | 314 | 65% | 59 | 18.79% | 221 | 34 | 87%
LB263 | 22 Apr. 2022 | Recirculation TGbb Draft 2.0 | Recirculation | 485 | 357 | 74% | 68 | 19.05% | 271 | 18 | 94%
LB267 | 31 Aug. 2022 | Recirculation TGbb Draft 3.0 | Recirculation | 485 | 371 | 76% | 75 | 20.22% | 281 | 15 | 95%
LB267 |  | Post-ballot update |  | 485 | 371 | 76% | 75 | 20.22% | 293 | 3 | 99%
 | 26 Sept. 2022 | Recirculation TGbb Draft 4.0 | Recirculation |  |  |  |  |  |  |  | 

## Slide 5: 802.11 WG Letter Ballot Comments – P802.11bb
Ballot ID | Ballot Close Date | Title | Total Number of Comments received (Yes and No votes)
LB260 | 12 Jan. 2022 | Technical TGbb Draft 1.0 | 333 (183 T, 131 E, 19 G)
LB263 | 22 Apr. 2022 | Recirculation TGbb Draft 2.0 | 112 (63 T, 38 E, 11 G)
LB267 | 31 Aug. 2022 | Recirculation TGbb Draft 3.0 | 65 (30 T, 21 E, 14 G)
Total |  |  | 510 (276 T, 190 E, 44 G)

## Slide 6: Unsatisfied Technical comments by commenter
Voter name | LB260 | LB263 | LB267 |  | Total
Aboulmagd, Osama (Huawei) | 2 | 0 | 0 |  | 2
Segev, Jonathan (Intel) | 0 | 1 | 0 |  | 1
Van Zelst, Allert (Qualcomm) | 0 | 0 | 4 |  | 4
Total | 2 | 1 | 4 |  | 7

## Slide 7: Unsatisfied comments
The composite of all unsatisfied comments and the resolutions approved by the comment resolution committee received during working group ballot may be found in the embedded document on the right:
  Double click on the icon to the right to open this.
Unsatisfied for LB 260 through LB267

## Slide 8: Unsatisfied Technical Comments – Topics
Aboulmagd, Osama (Huawei) – (over 5 emails sent, presentation during TGbb teleconference held to address the concerns, reply to the concerns provided and in-person discussions held during Sept.’22 interim)
  More information was required on the MAC/PHY for LC. The commenter failed to identify changes in sufficient details so that the specific wording of the changes that would satisfy the commenter could be determined.
Segev, Jonathan (Intel) – (over 4 emails sent, and in-person discussions held during Sept.’22 interim)
  Concerns that the Fine Time Measurement mechanisms might not work with LC. The commenter failed to identify changes in sufficient details so that the specific wording of the changes that would satisfy the commenter could be determined.
Van Zelst, Allert (Qualcomm) – (over 4 emails sent, problem captured in an email and largely resolved)
  Concerns that the Channel Number mechanisms proposed exceeded the intended range. The comments were addressed with a revised section and Channel Numbering instructions.

## Slide 9: CSD Reaffirmation
The CSD has been re-affirmed as part of the motion to request the EC to forward the draft to SA Ballot:
https://mentor.ieee.org/802-ec/dcn/18/ec-18-0080-00-ACSD-802-11bb.docx

## Slide 10: IEEE-SA Mandatory Editorial Coordination
Mandatory Draft Review (MDR) completed in the final report doc.: IEEE 802.11-22/0975r1:
https://mentor.ieee.org/802.11/dcn/22/11-22-0975-01-0000-tgbb-mdr-report.docx
Awaiting MEC feedback

## Slide 11: TGbb Projected Timeline
 | Open | Close
WG recirculation LB on D4.0 | 16 Sept. | 1 Oct.
Conf. call for motions on D4.0 comments | 3 Oct | 
EC approval to SA ballot | 4 Oct. | 
Conf call on WG recirculation LB on D4.0unchanged | 5 Oct. | 15 Oct.
First SA Ballot | Oct. 15th 2022 | Nov. 14, 2022 (30 days)
Second SA Ballot | March 2023 | Apr. 2023
Third SA Ballot | July 2023 | August 2023
EC to Revcom | Sep. 2023 | 
REVcom to SASB | Dec. 2023 | 

## Slide 12: Revision history of this document
R0 Unfinished draft version
R1 Updated draft removing known Approve voters and changing the associate relevant resolutions
R2 Updated draft to include new timeline
R3 Updated draft to include WG results