## Slide 1
Task Group BF September 2022 Closing Report
Date: 2022-09-15
Authors:
Name | Affiliation | Address | Phone | Email
Tony Xiao Han | Huawei Technologies Co., Ltd. | F3, Huawei Base, Shenzhen, China |  | Tony.hanxiao@huawei.com

## Slide 2: Abstract
This document is the closing report for Task Group BF for the September 2022 session.

## Slide 3: TGbf (WLAN Sensing)– September 2022
Progress during September 2022 meeting
  5 teleconference calls scheduled for TGbf (September 12 PM1 & PM2, 13 PM2, 14 PM2, 15 PM2)
  Continued comment resolution for D0.1 (802.11bf CC40 comments)
    Newly approved the comment resolution for 88+ CID
    ~49.8% of all CC40 comments are now resolved (454/912, Please refer to the figure)
  Presentation of technical submissions (e.g., Comment resolution, PDT, and developing the Draft ……)
Goals for the next two months
  Continue comment resolution for D0.1
  Presentation of technical submissions
  Further developing the Draft 0.1-1.0
  Requested 3 calls per week
Chart: P802.11bf D0.1 CR Status
| Technical | General | Editorial
Received | 591 | 55 | 266
Resolved | 198 | 18 | 238

## Slide 4: TGbf Timeline (Updated)
  PAR approved Sep 2020
  First TG meeting Oct 2020
  Comment Collection (D0.1) Jan 2022Mar 2022
   April 2022
  Initial Letter Ballot (D1.0) Jul 2022 Sep 2022
   Nov 2022
  Recirculation LB (D2.0) Jan 2023
  Recirculation LB (D3.0) May 2023
  Recirculation LB (D4.0) July 2023
  Initial SA Ballot (D4.0) Sep 2023
  Final 802.11 WG approval July 2024
  802 EC approval July 2024
  RevCom and SASB approval Sep 2024
Timeline (Comment collection for D0.1)
Early-mid May
  Identify topics, PoCs, and volunteers
May 20th
  Comment collection closes
Week of May 23rd
  Editor classifies comments and share them with TTTs
June 3rd
  Deadline for comment assignment
Sep 1, 2022
  TGbf decide to change the timeline for Initial Letter Ballot (D1.0) to November 2022
  SP Result: Unanimous consent

## Slide 5
Teleconference Times
  Confirmed:
    September 19 (Monday), 10：00 - 12:00 ET (Too close to September interim)
    September 20 (Tuesday), 10：00 - 12:00 ET
    September 22 (Thursday), 23：00 - 01:00 ET
    September 26 (Monday), 10：00 - 12:00 ET
    September 27 (Tuesday), 10：00 - 12:00 ET
    September 29 (Thursday), 23：00 - 01:00 ET
    October 3 (Monday), 10：00 - 12:00 ET (Holiday)
    October 4 (Tuesday), 10：00 - 12:00 ET
    October 6 (Thursday), 23：00 - 01:00 ET
    October 10 (Monday), 10：00 - 12:00 ET
    October 11 (Tuesday), 10：00 - 12:00 ET
    October 13 (Thursday), 23：00 - 01:00 ET
    October 17 (Monday), 10：00 - 12:00 ET
    October 18 (Tuesday), 10：00 - 12:00 ET
    October 20 (Thursday), 23：00 - 01:00 ET
    October 24 (Monday), 10：00 - 12:00 ET
    October 25 (Tuesday), 10：00 - 12:00 ET
    October 27 (Thursday), 23：00 - 01:00 ET
    October 31 (Monday), 10：00 - 12:00 ET
    November 1 (Tuesday), 10：00 - 12:00 ET
    November 3 (Thursday), 23：00 - 01:00 ET
    November 7 (Monday), 09：00 - 11:00 ET (Daylight saving time end on Nov. 6)
    November 8 (Tuesday), 09：00 - 11:00 ET
    November 10 (Thursday), 22：00 - 00:00 ET
  To be confirmed:
  November Plenary 2022 (November 13-18)
  (Daylight saving time end on Nov. 6)
    November 14 (Monday AM 2), 10:30-12:30 Thailand time
    November 14 (Monday PM 1), 13:30-15:30 Thailand time
    November 15 (Tuesday AM 1), 08:00-10:00 Thailand time
    November 16 (Wednesday AM 1), 08:00-10:00 Thailand time
    November 17 (Thursday AM 1), 08:00-10:00 Thailand time
  ** Note:
  when conflict with CAC, the call will be changed
  (July - September 2022 CAC calls: 9:00 Jun 6 & 27, 18:00 July 10)
  2. Thursday 23:00 - 01:00am ET (Thursday 20：00 – 22:00 PT, Friday 11am-13:00 in China, Friday 6am-8am in Israel, Friday 5am – 7am in Central Europe), and Sang Kim will help to take the minutes for these slots.
 | Thailand time | Beijing Time | Time Central Europe | Israel | Eastern Time | Pacific time
AM1 | 08:00-10:00 | 09:00-11:00 | 2:00-4:00 | 3:00-5:00 | 20:00-22:00 | 17:00-19:00
AM2 | 10:30-12:30 | 11:30-13:30 | 4:30-6:30 | 5:30-7:30 | 22:30-00:30 | 19:30-21:30
PM1 | 13:30-15:30 | 14:30-16:30 | 7:30-9:30 | 8:30-10:30 | 01:30-03:30 | 22:30-00:30
PM2 | 16:00-18:00 | 17:00-19:00 | 10:00-12:00 | 11:00-13:00 | 04:00-06:00 | 01:00-03:00
Evening 1 | 19:30-21:30 | 20:30-22:30 | 13:30-15:30 | 14:30-16:30 | 07:30-09:30 | 04:30-06:30