## Slide 1: REVme Closing Report – November 2022
Date: 2022-11-17
Authors:

## Slide 2: Work Completed
Began comment resolution on comments received on D2.0 from LB270
Decided to move forward with removing WEP from the baseline. Thank you to Graham Smith for preparing a document to drive the discussion.

## Slide 3: Plans up to January
Teleconferences:
  Monday Nov 28 – 10am ET, 2hrs
  Friday Dec 2, 16 – 10am ET, 2hrs
  Friday Jan 6, 27 – 10am ET, 2hrs
  Monday Jan 9 – 10am ET, 2hrs
Adhoc on Dec 5-7 in Piscataway, NJ
4 meeting slots requested for January

## Slide 4: TGme Timeline
Feb 2021 – PAR Approval
March 2021– Initial meeting, issue comment collection on IEEE Std 802.11-2020 (if published)
March 2021 – Draft 0.00 available
May 2021 – Process CC input, 11ax, 11ay, 11ba integration begins
Nov 2021 – Initial D1.0 WG Letter ballot
Sep 2022 – D2.0 Recirculation LB
Mar 2023 – D3.0 Recirculation LB (11az + other amendments <11bc, 11bd, 11bb> )
Sep 2023 – D4.0 Recirculation (<other amendments – if Jul>)
Nov 2023 – D5.0 Initial SA Ballot
Mar 2024 – D6.0 Recirculation SA Ballot
May 2024 – D7.0 Recirculation SA Ballot
Jun 2024 – D7.0 Recirculation SA Ballot (clean recirculation)
Sep 2024 – RevCom/SASB Approval