## Slide 1
Task Group BF November 2022 Closing Report
Date: 2022-11-17
Authors:
Name | Affiliation | Address | Phone | Email
Tony Xiao Han | Huawei Technologies Co., Ltd. | F3, Huawei Base, Shenzhen, China |  | Tony.hanxiao@huawei.com

## Slide 2: Abstract
This document is the closing report for Task Group BF for the November 2022 session.

## Slide 3: TGbf (WLAN Sensing)– September 2022
Progress during November 2022 session
  6 meetings scheduled for TGbf (November 14 PM1, 15 AM1 & PM1, 16 AM1 & AM2, 17 AM1)
  Continued comment resolution for D0.1 (802.11bf CC40 comments)
    the Comment resolution for 70+ CID are newly approved or marked as “ready for motion”
    ~77.9% of all CC40 comments are now resolved or marked as “ready for motion” (711/912, Please refer to the figure)
  Presentation of technical submissions (e.g., Comment resolution, PDT, and developing the Draft ……)
Goals for the next two months
  Continue comment resolution for D0.1
  Further developing the Draft 0.1-1.0
  Requested 3 calls per week
  Approve a TGbf ad-hoc meeting on January 13-14, 2023, in the Baltimore Hilton, Baltimore, Maryland for the purpose of TGbf comment resolution and consideration of document submissions. (Need further WG confirmation)
Chart: P802.11bf D0.1 CR Status
| Technical | General | Editorial
Received | 591 | 55 | 266
Resolved | 417 | 33 | 261

## Slide 4: TGbf Timeline (Updated)
  PAR approved Sep 2020
  First TG meeting Oct 2020
  Comment Collection (D0.1) Jan 2022Mar 2022
   April 2022
  Initial Letter Ballot (D1.0) Jul 2022 Sep 2022
   Nov 2022
   Jan 2023
  Recirculation LB (D2.0) Jan 2023  March 2023
  Recirculation LB (D3.0) May 2023
  Recirculation LB (D4.0) July 2023
  Initial SA Ballot (D4.0) Sep 2023
  Final 802.11 WG approval July 2024
  802 EC approval July 2024
  RevCom and SASB approval Sep 2024
Timeline (Comment collection for D0.1)
Early-mid May
  Identify topics, PoCs, and volunteers
May 20th
  Comment collection closes
Week of May 23rd
  Editor classifies comments and share them with TTTs
June 3rd
  Deadline for comment assignment
Sep 1, 2022
  TGbf decide to change the timeline for Initial Letter Ballot (D1.0) to November 2022
  SP Result: Unanimous consent
Nov 8, 2022
  TGbf decide to change the timeline for Initial Letter Ballot (D1.0) to January 2023 (Hard deadline)
  SP Result: Unanimous consent

## Slide 5
Teleconference Times
  Confirmed:
    November 21 (Monday), 09：00 - 11:00 ET (Too close to November interim)
    November 22 (Tuesday), 09：00 - 11:00 ET
    November 24 (Thursday), 22：00 - 00:00 ET – Thanks giving
    November 28 (Monday), 09：00 - 11:00 ET
    November 29 (Tuesday), 09：00 - 11:00 ET
    December 1 (Thursday), 22：00 - 00:00 ET
    December 5 (Monday), 09：00 - 11:00 ET
    December 6 (Tuesday), 09：00 - 11:00 ET
    December 8 (Thursday), 22：00 - 00:00 ET
    December 12 (Monday), 09：00 - 11:00 ET
    December 13 (Tuesday), 09：00 - 11:00 ET
    December 15 (Thursday), 22：00 - 00:00 ET - 1st Workshop on Wi-Fi Sensing (WiSe 1)
    December 19 (Monday), 09：00 - 11:00 ET
    December 20 (Tuesday), 09：00 - 11:00 ET
    December 22 (Thursday), 22：00 - 00:00 ET
    December 26 (Monday), 09：00 - 11:00 ET-- Holidays
    December 27 (Tuesday), 09：00 - 11:00 ET
    December 29 (Thursday), 22：00 - 00:00 ET
    January 2 (Monday), 09：00 - 11:00 ET
    January 3 (Tuesday), 09：00 - 11:00 ET
    January 5 (Thursday), 22：00 - 00:00 ET
    January 9 (Monday), 09：00 - 11:00 ET
    January 10 (Tuesday), 09：00 - 11:00 ET
    January 12 (Thursday), 22：00 - 00:00 ET
  To be Confirmed:
  January Interim 2023 (January 16-20)
    January 16 (Monday PM 1), 13:30-15:30 Baltimore time (ET)
    January 16 (Monday EV 1), 19:30-21:30 Baltimore time -- TBD
    January 17 (Tuesday AM 1), 08:00-10:00 Baltimore time
    January 17 (Tuesday PM 1), 13:30-15:30 Baltimore time
    January 17 (Tuesday EV 1), 19:30-21:30 Baltimore time -- TBD
    January 18 (Wednesday AM 1), 08:00-10:00 Baltimore time
    January 18 (Wednesday AM 2), 10:30-12:30 Baltimore time
    January 19 (Thursday AM 1), 08:00-10:00 Baltimore time
    January 19 (Thursday AM 2), 10:30-12:30 Baltimore time -- TBD
  ** Note:
  when conflict with CAC, the call will be changed
  (Sept - Nov 2022 CAC calls: October 10, 31 09:00 ET; November 13 06:00 ET)
  2. Thursday 23:00 - 01:00am ET (Thursday 20：00 – 22:00 PT, Friday 11am-13:00 in China, Friday 6am-8am in Israel, Friday 5am – 7am in Central Europe), and Sang Kim will help to take the minutes for these slots.
 | Baltimore time | Beijing Time | Time Central Europe | Israel | Eastern Time | Pacific time
AM1 | 08:00-10:00 | 21:00-23:00 | 14:00-16:00 | 15:00-17:00 | 08:00-10:00 | 05:00-07:00
AM2 | 10:30-12:30 | 23:30-01:30 | 16:30-18:30 | 17:30-19:30 | 10:30-12:30 | 07:30-09:30
PM1 | 13:30-15:30 | 02:30-04:30 | 19:30-21:30 | 20:30-22:30 | 13:30-15:30 | 10:30-12:30
PM2 | 16:00-18:00 | 05:00-07:00 | 22:00-00:00 | 23:00-01:00 | 16:00-18:00 | 13:00-15:00
Evening 1 | 19:30-21:30 | 08:30-10:30 | 01:30-03:30 | 02:30-04:30 | 19:30-21:30 | 16:30-18:30