## Slide 1: REVme Closing Report – January 2023
Date: 2023-01-19
Authors:

## Slide 2: Work Completed and Plans for March
Continued comment resolution on comments received on D2.0 from LB70
Teleconferences:
  Monday Feb 6, 13, 27 – 10am ET, 2hrs
  Friday Feb 3, 10, 17, 24, Mar 4, 24 – 10am ET, 2hrs
7 meeting slots requested for March

## Slide 3: Plans up to January
Teleconferences:
  Monday Feb 6, 13, 27 – 10am ET, 2hrs
  Friday Feb 3, 10, 17, 24, Mar 4, 24 – 10am ET, 2hrs
7 meeting slots requested for March

## Slide 4: TGme Timeline
Feb 2021 – PAR Approval
March 2021– Initial meeting, issue comment collection on IEEE Std 802.11-2020 (if published)
March 2021 – Draft 0.00 available
May 2021 – Process CC input, 11ax, 11ay, 11ba integration begins
Nov 2021 – Initial D1.0 WG Letter ballot
Sep 2022 – D2.0 Recirculation LB
Mar 2023 – D3.0 Recirculation LB (11az + other amendments <11bc, 11bd, 11bb> )
Sep 2023 – D4.0 Recirculation (<other amendments – if Jul>)
Nov 2023 – D5.0 Initial SA Ballot
Mar 2024 – D6.0 Recirculation SA Ballot
May 2024 – D7.0 Recirculation SA Ballot
Jun 2024 – D7.0 Recirculation SA Ballot (clean recirculation)
Sep 2024 – RevCom/SASB Approval