## Slide 1
Task Group BF January 2023 Closing Report
Date: 2023-01-19
Authors:
Name | Affiliation | Address | Phone | Email
Tony Xiao Han | Huawei Technologies Co., Ltd. | F3, Huawei Base, Shenzhen, China |  | Tony.hanxiao@huawei.com

## Slide 2: Abstract
This document is the closing report for Task Group BF for the January 2023 session.

## Slide 3: TGbf (WLAN Sensing)– January 2023
Progress during January 2023 session
  5 meetings scheduled for TGbf (January 16 EV1, 17 AM1 & EV1, 18 AM1, 19 AM2)
  Continued comment resolution for D0.1 (802.11bf CC40 comments)
    the Comment resolution for 6+ CID are newly approved
    100% of all CC40 comments are now resolved (912/912, Please refer to the figure)
  Presentation of technical submissions (e.g., Comment resolution, PDT, and developing the Draft ……)
  Finished CC40
  TG Motion passes: TGbf Initial LB
Goals for the next two months
  Release the Draft 1.0
  Comment collection for D1.0, and assign the comments
  Requested 1-2 calls per week
Chart: P802.11bf D0.1 CR Status
| Technical | General | Editorial
Received | 591 | 55 | 266
Resolved | 591 | 55 | 266
Finished

## Slide 4: TGbf Timeline (Updated)
  PAR approved Sep 2020
  First TG meeting Oct 2020
  Comment Collection (D0.1) Jan 2022Mar 2022
   April 2022
  Initial Letter Ballot (D1.0) Jul 2022 Sep 2022
   Nov 2022
   Jan 2023
  Recirculation LB (D2.0) Jan 2023  March 2023à July 2023
  Recirculation LB (D3.0) May 2023à Nov 2023
  Recirculation LB (D4.0) July 2023à Jan 2024
  Initial SA Ballot (D4.0) Sep 2023à March 2024
  Final 802.11 WG approval July 2024 à Jan 2025
  802 EC approval July 2024 à Jan 2025
  RevCom and SASB approval Sep 2024à March 2025

## Slide 5
Teleconference Times
  Confirmed:
    January 23 (Monday), 09：00 - 11:00 ET (Holidays)
    January 24 (Tuesday), 09：00 - 11:00 ET
    January 26 (Thursday), 22：00 - 00:00 ET –
    January 30 (Monday), 09：00 - 11:00 ET (1 calls/week for the first 3 weeks)
    January 31 (Tuesday), 09：00 - 11:00 ET
    February 2 (Thursday), 09：00 - 11:00 ET -- added back??
    February 6 (Monday), 09：00 - 11:00 ET --CAC
    February 7 (Tuesday), 09：00 - 11:00 ET
    February 9 (Thursday), 22：00 - 00:00 ET
    February 13 (Monday), 09：00 - 11:00 ET (2 calls/week after the first 3 weeks)
    February 14 (Tuesday), 09：00 - 11:00 ET
    February 16 (Thursday), 22：00 - 00:00 ET
    February 20 (Monday), 09：00 - 11:00 ET
    February 21 (Tuesday), 09：00 - 11:00 ET
    February 23 (Thursday), 22：00 - 00:00 ET
    February 27 (Monday), 09：00 - 11:00 ET -- CAC
    February 28 (Tuesday), 09：00 - 11:00 ET
    March 2 (Thursday), 22：00 - 00:00 ET
    March 6 (Monday), 09：00 - 11:00 ET
    March 7 (Tuesday), 09：00 - 11:00 ET
    March 9 (Thursday), 22：00 - 00:00 ET
12 Mar 2023 - Daylight Saving Time Starts
Sunday, 12 March 2023, 02:00:00 clocks are turned forward 1 hour to Sunday, 12 March 2023, 03:00:00 local daylight time instead.
  To be Confirmed:
  March Plenary 2023 (March 12-17)
    March 13 (Monday EV 1), 19:30-21:30 Atlanta time –Tutorial?
    March 14 (Tuesday AM 1), 08:00-10:00 Atlanta time
    March 14 (Tuesday EV 1), 19:30-21:30 Atlanta time
    March 15 (Wednesday AM 1), 08:00-10:00 Atlanta time
    March 15 (Wednesday AM 2), 10:30-12:30 Atlanta time
    March 16 (Thursday AM 1), 08:00-10:00 Atlanta time
    March 16 (Thursday AM 2), 10:30-12:30 Atlanta time
  ** Note:
  when conflict with CAC, the call may be changed
  (Jan2023 – Mar 2023 CAC calls: February 6, 27, and March 12)
  2. Thursday 22:00 - 00:00am ET (Thursday 19：00 – 21:00 PT, Friday 11am-13:00 in China, Friday 5am-7am in Israel, Friday 4am – 6am in Central Europe), and Sang Kim will help to take the minutes for these slots.
 | Atlanta time | Beijing Time | Time Central Europe | Israel | Eastern Time | Pacific time
AM1 | 08:00-10:00 | 20:00-22:00 | 13:00-15:00 | 14:00-16:00 | 07:00-09:00 | 05:00-07:00
AM2 | 10:30-12:30 | 22:30-00:30 | 15:30-17:30 | 16:30-18:30 | 09:30-11:30 | 07:30-09:30
PM1 | 13:30-15:30 | 01:30-03:30 | 18:30-20:30 | 19:30-21:30 | 12:30-14:30 | 10:30-12:30
PM2 | 16:00-18:00 | 04:00-06:00 | 21:00-23:00 | 22:00-00:00 | 15:00-17:00 | 13:00-15:00
Evening 1 | 19:30-21:30 | 07:30-09:30 | 00:30-02:30 | 01:30-03:30 | 18:30-20:30 | 16:30-18:30
Notes: Draft may be ready by February 3rd (that is, 2 weeks after the interim closes).
Given that Dorothy may need a day or two to open the ballot, let’s say that the ballot opens on February 6th.
30 days later means that the ballot would around March 10th – which is the week before the March plenary.