## Slide 1: TGbe January Closing Report
Date: 2023-01-19
Authors:

## Slide 2: TGbe (Extremely High Throughput)
TGbe had scheduled 12 sessions during the November plenary
  Five Joint sessions, and seven MAC ad-hoc sessions
    Discussed comment resolution documents
      All comments from LB266 are resolved (see figure for more details)
  Instructed the editor to generate IEEE802.11 TGbe D3.0
    TGbe D3.0 is expected to be available by mid-February 2023
Agenda is available in 11-22/2118r4
Motions List is available in 1038r43
Goals for March 2023:
  Complete comment assignment (if available from LB on TGbe D3.0)
  Start comment resolution (if comments are available)
CID Distribution (~4120)
16%
73%
11%
PHY
MAC
JOINT

## Slide 3: Teleconference Plan
No Telcos planned.
May allocate one teleconference with 10-day advanced notice
  For comment (if available) assignment the week before March plenary

## Slide 4: (Unchanged) TGbe Timeline And Status
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sep 2020
D1.0 WG Comment Collection May 2021
D2.0 WG Letter Ballot May 2022
D3.0 Letter Ballot Jan 2023
Initial SA Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024