## Slide 1: TGbh Closing Report
Date: 2023-01-19
Authors:

## Slide 2: Abstract
This document is the closing report for TGbh
“Randomized and Changing MAC addresses” (RCM)
January 2023 Plenary Session (mixed-mode)

## Slide 3: Work Completed - 1
Agenda is here: 11-22/2124r6
Joint meeting with TGbi agenda is here: 11-23/0135r0
Latest Issue Tracking document: 11-21/0332r37
Draft D0.2 is posted, in members’ area
Comment resolution spreadsheet: 11-22/0973r13
Motions: 11-22/0651r9

## Slide 4: Work Completed - 2
Contributions considered:
11-22/2150r2 – Clarfication of requirements (Graham Smith)
11-23/0061r1 – Discussion on pre-association identification schemes (Jay Yang)
11-23/0083r2 – Identifier status codes (Kurt Lumbatis)
11-22/1329r13 – CID resolutions for 12.2.11 (Kurt Lumbatis)
11-23/0022r1 – Use case for OWE mode (Jay Yang)
11-23/0119r4 – Way Ahead Decisions (Graham Smith)
Contributions still in queue:
11-22/2013r1 – ID encoding in pre-schemes (Jouni Malinen)
11-22/1084r1 – STA ID Opt-in (Sid Thakur)
11-22/0928r1 – MAAD Text for TGbh (Graham Smith)
11-22/0925r3 – Text for MAAD and IRM in TGbh (Graham Smith)
11-22/1585r0 – Multiple schemes text (Graham Smith)
11-22/1079r8 – CR for STA generated ID (Jay Yang)
11-22/0435r2 – Open issues from Issues Tracking document (Mark Hamilton)

## Slide 5: Work Completed - 3
Straw Polls on way forward (consideration of adding any more solutions to the D0.2 material
  All SPs failed to get majority support
  One additional possible solution discussed, needs details to be worked out off-line, to be considered on teleconference
Joint meeting with TGbi (Agenda items):
  Any concerns with overlap of scope between TGbh/TGbi? Clarify the scope, if/as needed.
  Can TGbh adopt a solution that can help or be leveraged into TGbi?
  How do we ensure TGbh does _NOT_ adopt a solution that makes TGbi a harder problem, and/or causes TGbi to “undo” TGbh and do something different.

## Slide 6: Timeline
  PAR approved Feb 2021
  First TG meeting Mar 2021
  D0.2 CC May 2022
  Initial WG Letter Ballot (D1.0) Mar 2023
  Recirculation LB (D2.0) Jul 2023
  Initial SA Ballot (D3.0) Nov 2023
  Final 802.11 WG approval Mar 2024
  802 EC approval Apr 2024
  RevCom and SASB approval Apr 2024

## Slide 7: Teleconference(s)
Dates TBD: Tuesdays between Jan and Mar, as possible (still working out conflicts), at 9:30am ET, 2 hours
March plans
4 meeting slots
Target D1.0 initial WG LB