## Slide 1: TGbh Closing Report
Date: 2023-03-16
Authors:

## Slide 2: Abstract
This document is the closing report for TGbh
“Randomized and Changing MAC addresses” (RCM)
March 2023 Plenary Session (mixed-mode)

## Slide 3: Work Completed - 1
Agenda is here: 11-23/0180r6
Latest Issue Tracking document: 11-21/0332r37
Draft D0.2 is posted, in members’ area
Comment resolution spreadsheet: 11-22/0973r19
Motions: 11-22/0651r14

## Slide 4: Work Completed - 2
Contributions considered:
CIDs 16 and 32 resolution (Device ID in Assoc for FILS) 11-23/0459r0, 11-23/0452r0
CIDs 19 & 20 (Device ID and PASN) 11-22/1732r1, 11-22/1806r0
CID 35 (Opaque container for Device ID) (email proposal)
CIDs 5 and 62 (PICS and MIB): 11-23/0461r0
Presentation on IRM: 11-23/0421r1
Presentation on “IE-based solution”: 11-23/0441r0

## Slide 5: Work Completed - 3
Resolutions prepared for all remaining CIDs (on CC 41), except to add one/more additional solutions.
  11-22/0973r18
Motion on comments to stop consideration of adding any more solutions to the D0.2 material
  Failed: 17-6-5 (74%)
Motion for D1.0, and initial WG LB not considered

## Slide 6: Timeline
  PAR approved Feb 2021
  First TG meeting Mar 2021
  D0.2 CC May 2022
  Initial WG Letter Ballot (D1.0) Mar 2023
  Recirculation LB (D2.0) Jul 2023
  Initial SA Ballot (D3.0) Nov 2023
  Final 802.11 WG approval Mar 2024
  802 EC approval Apr 2024
  RevCom and SASB approval Apr 2024

## Slide 7: Teleconference(s)
Dates TBD: Tuesdays between Mar and May, as possible (still working out conflicts/holidays), at 9:30am ET, 2 hours
May plans
4 meeting slots
Target D1.0 initial WG LB