## Slide 1: TGbe March Closing Report
Date: 2023-03-16
Authors:

## Slide 2: TGbe (Extremely High Throughput)
TGbe had scheduled 9 sessions during the March plenary
  Four Joint sessions, five MAC and three PHY ad-hoc sessions
    Discussed comment resolution documents
      Around 750 comments are resolved (see figure for more details)
  Instructed the editor to generate IEEE802.11 TGbe D3.1
    TGbe D3.1 is expected to be available by end of March 2023
Agenda is available in 11-23/191r13
Motions List is available in 11-23/442r2
Goals for May 2023:
  Hold an ad-hoc in San Jose, CA the week before may interim
  Continue comment resolution for LB271 comments
CID Distribution (~3340)
~10%
~80%
~10%

## Slide 3: Teleconference Plan
Mar 20-24 (Mon-Fri) - No Conf Calls Holiday
Mar 27 (Monday) – MAC/PHY 19:00-21:00 ET
Mar 29 (Wednesday) – MAC 10:00-12:00 ET
Apr 05 (Wednesday) – Joint 10:00-12:00 ET
Apr 06 (Thursday) – MAC 10:00-12:00 ET
Apr 10 (Monday) – MAC/PHY 19:00-21:00 ET
Apr 12 (Wednesday) – MAC 10:00-12:00 ET
Apr 19 (Wednesday) – Joint* 10:00-12:00 ET
Apr 20 (Thursday) – MAC 10:00-12:00 ET
Apr 24 (Monday) – MAC/PHY 19:00-21:00 ET
Apr 26 (Wednesday) – MAC 10:00-12:00 ET
May 3 (Wednesday) - No Conf Call Holiday
May 4 (Thursday) – MAC 10:00-12:00 ET

## Slide 4: TGbe Timeline And Status
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sep 2020
D1.0 WG Comment Collection May 2021
D2.0 WG Letter Ballot May 2022
D3.0 Letter Ballot Jan 2023
Initial SA Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024