## Slide 1
Task Group BF May 2023 Closing Report
Date: 2023-05-18
Authors:
Name | Affiliation | Address | Phone | Email
Tony Xiao Han | Huawei Technologies Co., Ltd. | F3, Huawei Base, Shenzhen, China |  | Tony.hanxiao@huawei.com

## Slide 2: Abstract
This document is the closing report for Task Group BF for the May 2023 session.

## Slide 3: TGbf (WLAN Sensing)– May 2023
Progress during May 2023 session
  7 teleconference calls scheduled for TGbf (May 15 AM2 & PM 2, 16 AM1 & AM2, 17 AM1 & AM2, 18 AM1 & AM2)
  Comment resolution for D1.0 (LB272)
    the Comment resolution for 224 CID are newly approved or marked as “ready for motion”
    56.682 % of all LB272 comments are now resolved or marked as “ready for motion”
    (738/1302, Please refer to the figure)
Goals for the next two months
  Continue comment resolution for D1.0 (LB272)
  Requested 2 calls per week
  Requested TGbf ad-hoc meeting on July 6, 7, 8, 2023, in the Ericsson Office, Lund, Sweden
Chart: P802.11bf D1.0 CR Status
| Technical | General | Editorial
Received | 815 | 28 | 459
Resolved | 245 | 8 | 261

## Slide 4: TGbf Timeline (Updated)
  PAR approved Sep 2020
  First TG meeting Oct 2020
  Comment Collection (D0.1) Jan 2022Mar 2022
   April 2022
  Initial Letter Ballot (D1.0) Jul 2022 Sep 2022
   Nov 2022
   Jan 2023
  Recirculation LB (D2.0) Jan 2023  March 2023à July 2023
  Recirculation LB (D3.0) May 2023à Nov 2023
  Recirculation LB (D4.0) July 2023à Jan 2024
  Initial SA Ballot (D4.0) Sep 2023à March 2024
  Final 802.11 WG approval July 2024 à Jan 2025
  802 EC approval July 2024 à Jan 2025
  RevCom and SASB approval Sep 2024à March 2025
Timeline (Comment resolution for D1.0)
January 20, 2023
  802.11 Working group Motion passes：802.11bf (WLAN Sensing) Draft 1.0 and Initial Letter Ballot
Tuesday January 31, 2023 at 23:59 Eastern Time USA (11:59 PM)
  Initial LB start for D1.0
Thursday March 2, 2023 at 23:59 Eastern Time USA (11:59 PM)
  Initial LB end for D1.0
  Assign the comments
Consider Ad Hoc meeting before July Plenary (decide during May Interim)

## Slide 5
Teleconference Times
  Confirmed:
    May 22 (Monday), 10：00 - 12:00 ET – Too close to May Interim
    May 23 (Tuesday), 10：00 - 12:00 ET
    May 25 (Thursday), 23：00 - 01:00 ET
    May 29 (Monday), 10：00 - 12:00 ET-- holiday
    May 30 (Tuesday), 10：00 - 12:00 ET
    June 1 (Thursday), 23：00 - 01:00 ET
    June 5 (Monday), 10：00 - 12:00 ET – CAC?
    June 6 (Tuesday), 10：00 - 12:00 ET-- holiday
    June 8 (Thursday), 23：00 - 01:00 ET
    June 12 (Monday), 10：00 - 12:00 ET
    June 13 (Tuesday), 10：00 - 12:00 ET
    June 15 (Thursday), 23：00 - 01:00 ET
    June 19 (Monday), 10：00 - 12:00 ET-- holiday
    June 20 (Tuesday), 10：00 - 12:00 ET
    June 22 (Thursday), 23：00 - 01:00 ET -- holiday
    June 26 (Monday), 10：00 - 12:00 ET
    June 27 (Tuesday), 10：00 - 12:00 ET
    June 29 (Thursday), 23：00 - 01:00 ET
    July 3 (Monday), 10：00 - 12:00 ET-- holiday
    July 4 (Tuesday), 10：00 - 12:00 ET -- holiday
    July 6 (Thursday), 23：00 - 01:00 ET
  To be Confirmed:
  July Plenary 2023 (July 9-14)
    July 10 (Monday AM 1), 08:00-10:00 Berlin time
    July 10 (Monday PM 2), 16:00-18:00 Berlin time
    July 11 (Tuesday AM 1), 08:00-10:00 Berlin time
    July 11 (Tuesday PM 2), 16:00-18:00 Berlin time
    July 12 (Wednesday AM 1), 08:00-10:00 Berlin time
    July 12 (Wednesday PM 2), 16:00-18:00 Berlin time
    July 13 (Thursday AM 1), 08:00-10:00 Berlin time
    July 13 (Thursday PM 2), 16:00-18:00 Berlin time
  ** Note:
  when conflict with CAC, the call may be changed
  (April 2023 – May 2023 CAC calls: April 3, and May 8, 14)
  2. Thursday 23:00 - 01:00am ET (Thursday 20：00 – 22:00 PT, Friday 11am-13:00 in China, Friday 6am-8am in Israel, Friday 5am – 7am in Central Europe), and Sang Kim will help to take the minutes for these slots.
 | Berlin time | Beijing Time | Time Central Europe | Israel | Eastern Time | Pacific time
AM1 | 08:00-10:00 | 14:00-16:00 | 08:00-10:00 | 9:00-11:00 | 02:00-04:00 | 23:00-01:00
AM2 | 10:30-12:30 | 16:30-18:30 | 10:30-12:30 | 11:30-13:30 | 04:30-06:30 | 01:30-03:30
PM1 | 13:30-15:30 | 19:30-21:30 | 13:30-15:30 | 14:30-16:30 | 07:30-09:30 | 04:30-06:30
PM2 | 16:00-18:00 | 22:00-24:00 | 16:00-18:00 | 17:00-19:00 | 10:00-12:00 | 07:00-09:00
Evening 1 | 19:30-21:30 | 01:30-03:30 | 19:30-21:30 | 20:30-22:30 | 13:30-15:30 | 10:30-12:30