## Slide 1: REVme Closing Report – May 2023
Date: 2023-05-18
Authors:

## Slide 2: Work Completed
Revised timeline (no change to end date)
Initiated comment resolution on LB 273

## Slide 3: Plans for July
Telecons schedule at 10am ET on
  Friday May 26 (discussed earlier in the week)
  Friday June 2, 16, 23
  Monday June 12, 19, 26
Complete comment resolution on D3.0 from LB 273
Request conditional approval from EC to go to SA Ballot
5 meeting slots requested for July

## Slide 4: TGme Timeline
Feb 2021 – PAR Approval
March 2021– Initial meeting, issue comment collection on IEEE Std 802.11-2020 (if published)
March 2021 – Draft 0.00 available
May 2021 – Process CC input, 11ax, 11ay, 11ba integration begins
Nov 2021 – Initial D1.0 WG Letter ballot
Sep 2022 – D2.0 Recirculation LB
Mar 2023 – D3.0 Recirculation LB
July 2023 – D4.0 Recirculation
Sep 2023 – D5.0 Initial SA Ballot
Feb 2024 – D6.0 Recirculation SA Ballot (roll-in of published amendment 11az, 11bd, 11bc, 11bb)
May 2024 – D7.0 Recirculation SA Ballot
Jul 2024 – D8.0 Recirculation SA Ballot (clean recirculation)
Sep 2024 – RevCom/SASB Approval