## Slide 1: P802.11REVme Report to EC on Conditional Approval to SA Ballot
Date: 2023-07-12
Authors:

## Slide 2: Introduction
This document contains the report to the IEEE 802 Executive Committee in support of a request for conditional approval to send P80211REVme to SA Ballot.
This document was approved during the plenary session of the 802.11 working group on <>
  Passed in the Working Group: <>

## Slide 3: Status Summary
80211REVme completed one comment collection and 3 WG Letter Ballots.
The ballot results on Draft 1.0 achieved > 75% needed for an approved draft
3200+ comments received on drafts 0.1 to 3.0.

## Slide 4: 802.11 WG Letter Ballot Results
Ballot ID | Ballot Close Date | Title | Ballot Type | Pool | Return | %Return | Abstain | %Abstain | Approve | Disapprove | %Approve
258 | 10 January 2022 | Technical Letter Ballot for D1.0 | Technical | 443 | 277 | 63 | 20 | 5 | 216 | 41 | 84
270 | 11 November 2022 | First Recirculation Ballot for D2.0 | Recirculation | 443 | 311 | 75 | 21 | 5 | 250 | 40 | 86
273 | 7 May 2023 | Second Recirculation Ballot for D3.0 | Recirculation | 443 | 337 | 76 | 18 | 1.3 | 258 | 22 | 92.1
273.1 |  | LB 273 Post-Ballot vote change |  | 443 | 337 | 76 | 18 | 1.3 | 269 | 11 | 96

## Slide 5: 802.11 WG Letter Ballot Comments
Ballot ID | Ballot Close Date | Title | Total Number of Comments received (Yes and No votes)
258 | 10 January 2022 | Technical Letter Ballot for D1.0 | 1392 (921 T, 415 E, 56 G)
270 | 11 November 2022 | First Recirculation Ballot for D2.0 | 822 (204 T, 601 E, 17 G)
273 | 7 May 2023 | Second Recirculation Ballot for D3.0 | 417 (272 T, 138 E, 7 G)

## Slide 6: Unsatisfied Technical comments by commenter
Voter | LB258 | LB270 | LB273 | Total
Jarkko Kneckt |  |  | 3 | 3
Daniel Harkins |  |  | 1 | 1
Andrew Myles |  |  | 1 | 1
Yongho Seok |  | 3 |  | 3
Yan Zhang | 1 |  | 3 | 4
Jouni Malinen | 1 |  | 1 | 2
John Coffey |  |  | 9 | 9
Mark Hamilton |  |  | 1 | 1
Mark RISON |  |  | 3 | 3
Chaoming Luo |  |  | 1 | 1
Graham Smith | 2 |  |  | 2
Total | 4 | 3 | 23 | 30

## Slide 7: Unsatisfied Technical Comments – Topics
Jarkko Kneckt – Peer to peer communication
Daniel Harkins – Password identifiers
Andrew Myles – Regulatory - enablement
Yongho Seok – Off-channel TWT
Yan Zhang – No response – PHY equations
Jouni Malinen – Password identifiers
John Coffey – Receiver Sensitivity
Mark Hamilton –Various topics
Mark RISON – Various topics
Chaoming Luo – Block ACK segmentation and reassembly
Graham Smith – Spatial reuse

## Slide 8: Unsatisfied comments
The composite of all unsatisfied comments and the resolutions approved by the comment resolution committee received during working group ballot may be found in the embedded document on the right:
  Double click on the icon to the right to open this.

## Slide 9: REVme Timeline
 | Open | Close
Third Recirculation Ballot (D4.0) | August 2023 | September 2023
Initial SA Ballot (D4.0) | September 2023 | October 2023
Second SA Ballot Recirculation (D5.0) | February 2024 | March 2024
Third SA Ballot Recirculation (D6.0) | June 2024 | July 2024
EC approval to RevCom | July 2024 | 
RevCom and Standards Board | September 2024 | 

## Slide 10: References