## Slide 1
Task Group BF July 2023 Closing Report
Date: 2023-07-14
Authors:
Name | Affiliation | Address | Phone | Email
Tony Xiao Han | Huawei Technologies Co., Ltd. | F3, Huawei Base, Shenzhen, China |  | Tony.hanxiao@huawei.com

## Slide 2: Abstract
This document is the closing report for Task Group BF for the July 2023 session.

## Slide 3: TGbf (WLAN Sensing)– July 2023
Progress during July 2023 session
  8 teleconference calls scheduled for TGbf (July 10 AM1 & AM 2, 11 AM1 & PM1, 12 AM1 & AM2, 13 AM1 & PM2)
  TGbf ad-hoc meeting on July 6, 7, 8, 2023, in the Ericsson Office, Lund, Sweden
  Comment resolution for D1.0 (LB272)
    the Comment resolution for 157 CID are newly approved or marked as “ready for motion”
    100% of all LB272 comments are now resolved or marked as “ready for motion”
    (1302/1302, Please refer to the figure)
    Finished CR for LB272
    TG Motion passes: TGbf Recirculation LB
Goals for the next two months
  Release the Draft 2.0
  Comment collection for D2.0, and assign the comments
  Requested 1 calls per week
Chart: P802.11bf D1.0 CR Status
| Technical | General | Editorial
Received | 815 | 28 | 459
Resolved | 815 | 28 | 459

## Slide 4: TGbf Timeline (Updated)
  PAR approved Sep 2020
  First TG meeting Oct 2020
  Comment Collection (D0.1) Jan 2022Mar 2022
   April 2022
  Initial Letter Ballot (D1.0) Jul 2022 Sep 2022
   Nov 2022
   Jan 2023
  Recirculation LB (D2.0) Jan 2023  March 2023à July 2023
  Recirculation LB (D3.0) May 2023à Nov 2023
  Recirculation LB (D4.0) July 2023à Jan 2024
  Initial SA Ballot (D4.0) Sep 2023à March 2024
  Final 802.11 WG approval July 2024 à Jan 2025
  802 EC approval July 2024 à Jan 2025
  RevCom and SASB approval Sep 2024à March 2025
Timeline (Comment resolution for D1.0)
January 20, 2023
  802.11 Working group Motion passes：802.11bf (WLAN Sensing) Draft 1.0 and Initial Letter Ballot
Tuesday January 31, 2023 at 23:59 Eastern Time USA (11:59 PM)
  Initial LB start for D1.0
Thursday March 2, 2023 at 23:59 Eastern Time USA (11:59 PM)
  Initial LB end for D1.0
  Assign the comments
Consider Ad Hoc meeting before July Plenary (decide during May Interim)

## Slide 5
Teleconference Times
  Confirmed:
    July 17 (Monday), 10：00 - 12:00 ET – Too close to May Interim
    July 18 (Tuesday), 10：00 - 12:00 ET
    July 20 (Thursday), 23：00 - 01:00 ET
    July 24 (Monday), 10：00 - 12:00 ET
    July 25 (Tuesday), 10：00 - 12:00 ET
    July 27 (Thursday), 23：00 - 01:00 ET
    July 31 (Monday), 10：00 - 12:00 ET
    Aug 1 (Tuesday), 10：00 - 12:00 ET
    Aug 3 (Thursday), 23：00 - 01:00 ET
    Aug 7 (Monday), 10：00 - 12:00 ET – CAC
    Aug 8 (Tuesday), 10：00 - 12:00 ET
    Aug 10 (Thursday), 23：00 - 01:00 ET
    Aug 14 (Monday), 10：00 - 12:00 ET
    Aug 15 (Tuesday), 10：00 - 12:00 ET-- holiday
    Aug 17 (Thursday), 23：00 - 01:00 ET
    Aug 21 (Monday), 10：00 - 12:00 ET
    Aug 22 (Tuesday), 10：00 - 12:00 ET
    Aug 24 (Thursday), 23：00 - 01:00 ET
    Aug 28 (Monday), 10：00 - 12:00 ET – CAC
    Aug 29 (Tuesday), 10：00 - 12:00 ET
    Aug 31 (Thursday), 23：00 - 01:00 ET
    Sept 4 (Monday), 10：00 - 12:00 ET holiday
    Sept 5 (Tuesday), 10：00 - 12:00 ET
    Sept 7 (Thursday), 23：00 - 01:00 ET
  To be Confirmed:
  September Interim 2023 (Sept 10-15)
    Sept 11 (Monday AM 1), 08:00-10:00 Atlanta time
    Sept 11 (Monday AM 2), 10:30-12:30 Atlanta time
    Sept 12 (Tuesday AM 2), 10:30-12:30 Atlanta time
    Sept 12 (Tuesday PM 1), 13:30-15:30 Atlanta time
    Sept 13 (Wednesday AM 1), 08:00-10:00 Atlanta time
    Sept 13 (Wednesday AM 2), 10:30-12:30 Atlanta time
    Sept 14 (Thursday AM 2), 10:30-12:30 Atlanta time
    Sept 14 (Thursday PM 1), 13:30-15:30 Atlanta time
  ** Note:
  when conflict with CAC, the call may be changed
  (July 2023 – Sept 2023 CAC calls: Aug 7, Aug 28, Sept 10)
  2. Thursday 23:00 - 01:00am ET (Thursday 20：00 – 22:00 PT, Friday 11am-13:00 in China, Friday 6am-8am in Israel, Friday 5am – 7am in Central Europe), and Sang Kim will help to take the minutes for these slots.
 | Atlanta time | Beijing Time | Time Central Europe | Israel | Eastern Time | Pacific time
AM1 | 08:00-10:00 | 20:00-22:00 | 14:00-16:00 | 15:00-17:00 | 08:00-10:00 | 05:00-07:00
AM2 | 10:30-12:30 | 22:30-00:30 | 16:30-18:30 | 17:30-19:30 | 10:30-12:30 | 07:30-09:30
PM1 | 13:30-15:30 | 01:30-03:30 | 19:30-21:30 | 20:30-22:30 | 13:30-15:30 | 10:30-12:30
PM2 | 16:00-18:00 | 04:00-06:00 | 22:00-24:00 | 23:00-01:00 | 16:00-18:00 | 13:00-15:00
Evening 1 | 19:30-21:30 | 07:30-09:30 | 01:30-03:30 | 02:30-04:30 | 19:30-21:30 | 16:30-18:30