## Slide 1: September 2023 AIML TIG Closing Report
Date: 2023-09-14
Authors:

## Slide 2: Abstract
Closing report for the AIML TIG for September 2023

## Slide 3: Work Completed
  4 Meeting Slots
    Monday PM1
    Tuesday PM1
    Wednesday AM2
    Thursday PM1
    Agenda: 11-23/1300r3
  8 technical contributions
    7 technical report draft proposals
    1 additional technical contribution on AIML-based CSI compression
An additional use case has been approved
  Multi-AP coordination

## Slide 4: AIML TIG Technical Report
AIML TIG Technical report draft r16 has been approved:
  11-22/987r16 now contains 4 use cases with two additional use cases under consideration
  AIML-based CSI Compression
  AIML-based channel access
  AIML Model sharing
  AIML-based roaming enhancement
  Multi-AP coordination
Feedback on AIML Technical Report during this meeting, but have not had time to address all the feedback
  Needs executive summary
  Needs conclusion
  Needs additional editorial review
  Differentiate use cases in which AIML are used to improve WLAN performance, and use cases in which WLAN can enable support for AIML techniques
  In addition, needs a few more improvements on the text (e.g., privacy)

## Slide 5: Plans for November 2023
The AIML TIG is scheduled to end in September 2023
Need to request an extension to complete the report
In case an extension is granted, finalize the AIML TIG report in November 2023
  Privacy considerations
  May look at additional use cases
Discuss next steps for AIML TIG