## Slide 1: REVme Closing Report – September 2023
Date: 2023-09-14
Authors:

## Slide 2: Work Completed
Revisited previous LB comments to provide further feedback
Discussed potential ways forward with SAE password identifiers proposal.
Discussed “searchable terms” and further enhancements
Approved adhoc in Piscataway NJ on Dec 7 and 8
No updates to timeline

## Slide 3: Plans for November
Process any comments received on initial SA Ballot
  SA Ballot closes Oct 7.
Adhoc meeting on Oct 10-12 in Toronto, Canada.
Teleconferences on Nov 6 and 20.

## Slide 4: Adhoc Motion
Authorize TGme to hold a mixed mode ad-hoc meeting on December 7 and 8 (Thursday and Friday) with the preferred venue being Piscataway, NJ, for the purpose of SA Ballot comment resolution.
Moved: Jon Rosdahl
Second: Mark Hamilton
Result: Unanimous. Approved. 18 voters present.

## Slide 5: TGme Timeline
Feb 2021 – PAR Approval
March 2021– Initial meeting, issue comment collection on IEEE Std 802.11-2020 (if published)
March 2021 – Draft 0.00 available
May 2021 – Process CC input, 11ax, 11ay, 11ba integration begins
Nov 2021 – Initial D1.0 WG Letter ballot
Sep 2022 – D2.0 Recirculation LB
Mar 2023 – D3.0 Recirculation LB
July 2023 – D4.0 Recirculation
Sep 2023 – D5.0 Initial SA Ballot
Feb 2024 – D6.0 Recirculation SA Ballot (roll-in of published amendment 11az, 11bd, 11bc, 11bb)
May 2024 – D7.0 Recirculation SA Ballot
Jul 2024 – D8.0 Recirculation SA Ballot (clean recirculation)
Sep 2024 – RevCom/SASB Approval