## Slide 1: IEEE 802 JTC1 Standing Committee November 2023 agenda (mixed mode)
14 November 2023
Authors:
Name | Company | Phone | email
Peter Yee (Chair) | AKAYLA |  | peter@akayla.com

## Slide 2: This document will be used to provide information for any IEEE 802 JTC1 SC meetings in November 2023
  This presentation contains a proposed running order for any IEEE 802 JTC1 Standing Committee meeting, including
    Proposed agenda
    Other supporting material
  It will be modified during the meeting to include motions, straw polls and other material referred to during the meeting

## Slide 3: Registration is not required for the IEEE 802 JTC1 SC session in November 2023

## Slide 4: The SC will review the official IEEE-SA patent material for pre-PAR groups

## Slide 5: Participant behavior in IEEE-SA activities is guided by the IEEE Codes of Ethics & Conduct
  All participants in IEEE-SA activities are expected to adhere to the core principles underlying the:
    IEEE Code of Ethics
    IEEE Code of Conduct
  The core principles of the IEEE Codes of Ethics & Conduct are to:
    Uphold the highest standards of integrity, responsible behavior, and ethical and professional conduct
    Treat people fairly and with respect, to not engage in harassment, discrimination, or retaliation, and to protect people's privacy.
    Avoid injuring others, their property, reputation, or employment by false or malicious action
  The most recent versions of these Codes are available at
    http://www.ieee.org/about/corporate/governance

## Slide 6: Participants in the IEEE-SA “individual process” shall act independently of others, including employers
  The IEEE-SA Standards Board Bylaws require that “participants in the IEEE standards development individual process shall act based on their qualifications and experience”
  This means participants:
    Shall act & vote based on their personal & independent opinions derived from their expertise, knowledge, and qualifications
    Shall not act or vote based on any obligation to or any direction from any other person or organization, including an employer or client, regardless of any external commitments, agreements, contracts, or orders
    Shall not direct the actions or votes of other participants or retaliate against other participants for fulfilling their responsibility to act & vote based on their personal & independently developed opinions
  By participating in standards activities using the “individual process”, you are deemed to accept these requirements; if you are unable to satisfy these requirements then you shall immediately cease any participation

## Slide 7: IEEE-SA standards activities shall allow the fair & equitable consideration of all viewpoints
  The IEEE-SA Standards Board Bylaws (clause 5.2.1.3) specifies that “the standards development process shall not be dominated by any single interest category, individual, or organization”
    This means no participant may exercise “authority, leadership, or influence by reason of superior leverage, strength, or representation to the exclusion of fair and equitable consideration of other viewpoints” or “to hinder the progress of the standards development activity”
  This rule applies equally to those participating in a standards development project and to that project’s leadership group
  Any person who reasonably suspects that dominance is occurring in a standards development project is encouraged to bring the issue to the attention of the Standards Committee or the project’s IEEE-SA Program Manager

## Slide 8: IEEE SA Copyright Policy
  By participating in this activity, you agree to comply with the IEEE Code of Ethics, all applicable laws, and all IEEE policies and procedures including, but not limited to, the IEEE SA Copyright Policy.
    Previously Published material (copyright assertion indicated) shall not be presented/submitted to the Working Group nor incorporated into a Working Group draft unless permission is granted.
    Prior to presentation or submission, you shall notify the Working Group Chair of previously Published material and should assist the Chair in obtaining copyright permission acceptable to IEEE SA.
    For material that is not previously Published, IEEE is automatically granted a license to use any material that is presented or submitted.

## Slide 9: IEEE SA Copyright Policy
  The IEEE SA Copyright Policy is described in the IEEE SA Standards Board Bylaws and IEEE SA Standards Board Operations Manual
    IEEE SA Copyright Policy, see:
      Clause 7 of the IEEE SA Standards Board Bylaws
      Clause 6.1 of the IEEE SA Standards Board Operations Manual
    IEEE SA Copyright Permission
    IEEE SA Copyright FAQs
    IEEE SA Best Practices for IEEE Standards Development
    Distribution of Draft Standards (see Clause 6.1.3 of the SASB Ops Man)

## Slide 10: The IEEE 802 JTC1 SC will meet in mixed mode on 14 November 2023 in the PM2 slot in Honolulu
Call to Order
Announce recording secretary
Approve agenda
Execute agenda
Adjourn
Hybrid
Tue, 14 November 2023 @ 4:00 pm (Honolulu)
Webex details
https://ieeesa.webex.com/ieeesa/j.php?MTID=m6d066f09b2555eb10fb463c9469490b0
Meeting number (access code): 2331 902 0537
Meeting password: wireless (not JTC1, as it was in the past)

## Slide 11: The IEEE 802 JTC1 SC regular meeting has a high-level list of agenda items to be considered
In no particular order:
  Announcement
  Approve minutes
    From IEEE 802 JTC1 SC meeting in September 2023
  Review extended goals
  Review status of SC 6 interactions
    Review liaisons of drafts to SC 6
    Review notifications of projects to SC 6
    Review status of 60-day/FDIS ballots
  Review SC 6 activities
  Consider any motions

## Slide 12: The IEEE 802 JTC1 SC will consider approving its agenda
Motion to approve agenda
  The IEEE 802 JTC1 SC approves the agenda for its mixed-mode meeting on 14 November 2023, as documented on slide 11 of 11-23/1725r00.
  Moved:
  Seconded:
  Result:

## Slide 13: The IEEE 802 JTC1 SC will consider approval of the minutes of its September 2023 meeting
Motion to approve minutes
  The IEEE 802 JTC1 SC approves the minutes for its hybrid meeting in September 2023, as documented in 11-23/1638r02
  Moved:
  Seconded:
  Result:

## Slide 14: The goals of the IEEE 802 JTC1 SC were reaffirmed by the IEEE 802 EC in Nov 2020
The IEEE 802 JTC 1 SC has agreed goals from November 2010 …
  Provides a forum for 802 members to discuss issues relevant to both:
    IEEE 802
    ISO/IEC JTC 1/SC 6
  Recommends positions to ExCom on ISO/IEC JTC 1/SC 6 actions affecting IEEE 802
    Note that IEEE 802 LMSC holds the liaison to SC 6, not the IEEE 802.11 WG
  Participates in dialog with IEEE staff and 802 ExCom on issues concerning IEEE’s relationship with ISO/IEC
  Organises IEEE 802 members to contribute to liaisons and other documents relevant to the ISO/IEC JTC 1/SC 6 members
  … that were reaffirmed by 802 EC in Mar 2014, July 2018 & Nov 2020

## Slide 15: The IEEE 802 WGs continue to liaise drafts to SC 6 for their information
  IEEE 802 has agreed (see N15606) to liaise to SC 6 drafts of standards/amendments that are likely to be ratified under the PSDO agreement
  Generally, IEEE 802 will liaise drafts during the SA Ballot process, but may also do so during the Letter Ballot process
  So far drafts have been liaised by most WGs
    IEEE 802.1/3/11/15/16/21/22 WGs
    IEEE 802.16/21/22 are now hibernating
    IEEE 802.19 has not yet considered liaisons
  Note: as of March 2015, any drafts liaised to SC 6 will need a “permission statement” added to the front of the draft
    Please contact the staff liaisons for each of the Working Groups

## Slide 16: IEEE 802 continues to notify SC 6 of various new projects
  IEEE 802 has agreed to notify SC 6 when IEEE 802 starts new projects
  The benefit to IEEE 802 is that it might cause SC 6 members to participate in or contribute to IEEE 802 activities
  After the July 2023 plenary in Berlin, the IEEE 802 LMSC Recording Secretary notified (in N18093) the approval of:
    IEEE 802.3 Improved Support of Asymmetric Applications for Cameras (ISAAC) Study Group
    IEEE 802.15 Next Generation SUN PHY Study Group
    IEEE 802.19 Enhanced Methods for Sub-1GHz Coexistence

## Slide 17: The iMeet area for the “Adoption of IEEE 802 standards by ISO/IEC JTC1” is operational
  IEEE-SA staff have completed the first iteration of the iMeet area for the Adoption of IEEE 802 standards by ISO/IEC JTC1
  The public view of the process is up and running
    See https://ieee-sa.imeetcentral.com/802psdo/ (link updated in July 2016)
    The site is up-to-date as of 8 Aug 2023
  iMeet also contains links to a document that explains processes for interactions between SC 6 & IEEE 802:
    How does a WG send a liaison to SC 6?
    How does a WG send a document to SC 6 for information or review?
    How does a WG submit a standard for adoption under the PSDO process?
    How does a WG submit response to comments received?
    Feb 2017: John D'Ambrosia is developing some standard motion templates

## Slide 18: IEEE 802 has sent 102 standards through the PSDO adoption process, with 44 in-process
WG | Completed | In-process
802.1 | 50 | 9
802.3 | 29 | 8
802.11 | 13 | 14
802.15 | 3 | 14
802.16 | 0 | 0
802.19 | 0 | 0
802.21 | 3 | 0
802.22 | 4 | 0
All | 102 | 45

## Slide 19: IEEE 802.1 WG has sent 50 standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802 | Oct 2014 | Nov 2015 | Jan 2016
802.1X | 2013 | Oct 2013 | Jan 2014
802.1AE | 2013 | Oct 2013 | Jan 2014
802.1AB | May 2013 | Dec 2013 | May 2014
802.1AR | May 2013 | Dec 2013 | May 2014
802.1AS | May 2013 | Dec 2013 | May 2014
802.1AEbw | Jan 2014 | Feb 2015 | Apr 2015
802.1AEbn | Jan 2014 | Feb 2015 | Apr 2015
802.1AX | May 2015 | Nov 2015 | n/a
802.1Xbx | Mar 2015 | Dec 2015 | May 2016
802.1Q-Rev | Mar 2015 | Jan 2016 | May 2016
802.1BA | Sep 2015 | Aug 2016 | n/a

## Slide 20: IEEE 802.1 WG has sent 50 standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.1BR | Sep 2015 | Aug 2016 | n/a
802.1Qbv | May 2016 | Apr 2017 | Jul 2017
802.1AB | Jul 2016 | Apr 2017 | Jul 2017
802.1Qca | Jul 2016 | Apr 2017 | Jul 2017
802.1Qbu | Feb 2017 | Oct 2017 | n/a
802.1Qbz | Feb 2017 | Oct 2017 | n/a
802.1Qcd | Oct 2016 | Dec 2017 | n/a
802.1Q-Cor1 | - | Mar 2017 | Jul 2017
802.1AC-Rev | May 2017 | Mar 2018 | Apr 2018
802d | Jun 2017 | Mar 2018 | n/a
802.1AX/Cor1 | - | Jul 2018 | n/a
802.1AEcg | Sep 17 | Aug 18 | Jan 19

## Slide 21: IEEE 802.1 WG has sent 50 standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.1CB | 20 Jan 18 | 26 Dec 18 | n/a
802.1Qci | 9 Dec 17 | 3 Jan 19 | n/a
802.1Qch | 20 Jan 18 | 3 Jan 19 | n/a
802c | 2 Feb 18 | 26 Dec 18 | Apr 19
802.1CM | 14 Oct 18 | 27 Jun 19 | n/a
802.1AR-Rev | 14 Oct 18 | 14 Nov 19 | Apr 20
802.1AC/Cor-1 | n/a | 17 Mar 19 | n/a
802.1Q-2018 | 11 Mar 19 | 4 May 20 | Jun 20
802.1AE-Rev | 11 Mar 19 | 26 Jun 20 | Aug 20
802.1Xck | 11 Mar 19 | 26 Jun 20 | Aug 20
802.1AE/Cor1 | n/a | 13 Jan 21 | n/a

## Slide 22: IEEE 802.1 WG has sent 50 standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.1Qcp | Jul 2020 | Jul 2021 | n/a
802.1Qcy | Jul 2020 | Jul 2021 | n/a
802.1AX-REV | Aug 2020 | Jul 2021 | n/a
802.1Qcc | Jul 2020 | Sep 2021 | Jan 2022
802.1AS-Rev | Aug 2020 | Sep 2021 | Jan 2022
802.1CMde | Jan 2021 | Sep 2021 | Jan 2022
.1X-2020 | Dec 2020 | Nov 2021 | Mar 2022
.1CS | Jul 2021 | Jun 2022 | n/a
.1CBdb | Jun 2022 | Jan 2023 | n/a
.1CBcv | Jun 2022 | Jan 2023 | n/a
.1AS/Cor-1 | Sep 2021 | Aug 2022 | Nov 2022
.1BA-REV | Jun 2022 | Mar 2023 | Jul 2023

## Slide 23: IEEE 802.1 WG has sent 50 standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.1ACct | Apr 2022 | Mar 2023 | Jul 2023
802.1ABcu | Jul 2022 | Jun 2023 | n/a
802.1ABdh | Jul 2022 | Jun 2023 | n/a

## Slide 24: IEEE 802.3 WG has sent 32 standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.3 | 2013 | Feb 2014 | n/a
802.3 | Jul 2016 | Mar 2017 | Mar 2017
802.3 | Apr 2019 | Jul 2020 | Nov 2020
802.3.1 | Oct 2014 | Jun 2015 | Apr 2015
802.3bw | Sep 2016 | Sep 2017 | Nov 2017
802.3bp | Jan 2017 | Oct 2017 | n/a
802.3bq | Jan 2017 | Oct 2017 | n/a
802.3br | Feb 2017 | Oct 2017 | n/a
802.3by | Jan 2017 | Oct 2017 | n/a
802.3bz | Feb 2017 | Oct 2017 | n/a
802.3/Cor 1 | - | Nov 2017 | n/a

## Slide 25: IEEE 802.3 WG has sent 32 standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.3bn | Apr 17 | Sep 18 | n/a
802.3bv | Aug 17 | Sep 18 | n/a
802.3bu | Aug 17 | Sep 18 | n/a
802.3bs | Apr 18 | Dec 18 | n/a
802.3cc | Apr 18 | Dec 18 | n/a
802.3-rev | Apr 19 | Jul 20 | Nov 2020
802.3cn | Dec 20 | Sep 21 | Nov 2021
802.3cq | Dec 20 | Sep 21 | Nov 2021
802.3cm | Dec 20 | Sep 21 | Nov 2021
802.3ch | Dec 20 | Sep 21 | Nov 2021
802.3.2 | Dec 20 | Sep 21 | Nov 2021

## Slide 26: IEEE 802.3 WG has sent 32 standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.3cb | 8 Apr 19 | 11 Nov 21 | Feb 22
802.3bt | 17 Oct 20 | 11 Nov 21 | Feb 22
802.3cd | 17 Oct 20 | 11 Nov 21 | Feb 22
802.3cg | 14 Dec 20 | 17 Nov 21 | Feb 22
802.3ca | 14 Dec 20 | 17 Nov 21 | Feb 22
802.3cr | 11 Jun 21 | 4 Jun 22 | n/a
802.3cu | 11 Jun 21 | 4 Jun 22 | n/a
802.3ct | 9 Oct 21 | 2 Sep 22 | Oct 22
802.3cv | 9 Oct 21 | 1 Sep 22 | Oct 22
802.3cp | 9 Oct 21 | 2 Sep 22 | Oct 22

## Slide 27: IEEE 802.11 WG has sent 12 standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.11 | 2012 | 2012 | Nov 2013
802.11aa | Feb 2013 | Jan 2014 | July 2014
802.11ad | Feb 2013 | Jan 2014 | July 2014
802.11ae | Feb 2013 | Jan 2014 | July 2014
802.11ac | Sep 2014 | Jul 2015 | Jul 2015
802.11af | Sep 2014 | Jul 2015 | Jul 2015
802.11-2016 | Apr 2017 | Apr 2018 | May 2018
802.11ai | Sep 2017 | Dec 2018 | Feb 2019
802.11ah | Jul 2017 | Feb 2019 | Mar 2019

## Slide 28: IEEE 802.11 WG has sent 12 standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.11ah | Jul 2017 | Feb 2019 | Mar 2019
802.11aj | Feb 2019 | Jun 2020 | Jul 2020
802.11ak | Feb 2019 | Jun 2020 | Jul 2020
802.11aq | Feb 2019 | Jun 2020 | Jul 2020
802.11-2020 | Jan 2020 | Jun 2021 | Jul 2022

## Slide 29: IEEE 802.15 WG has sent three standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.15.3 | Oct 2016 | Sep 2017 | n/a
802.15.4 | Apr 2017 | Jan 2018 | n/a
802.15.6 | 23 Nov 16 | 7 Sep 17 | Jul 19

## Slide 30: IEEE 802.16 WG has sent zero standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE

## Slide 31: IEEE 802.19 WG has sent zero standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE

## Slide 32: IEEE 802.21 WG has sent three standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.21-2017 | Jul 2017 | Feb 2018 | Mar 2018
802.21.1 | Jul 2017 | Mar 2018 | Jul 2017
802.21/Cor1 | - | Jun 2018 | n/a

## Slide 33: IEEE 802.22 WG has sent four standards completely through the PSDO adoption process
IEEE 802 standard | 60-day pre-ballot | 5-month FDIS ballot | Comments resolved by IEEE
802.22 | May 2014 | Feb 2015 | n/a
802.22a | April 2016 | Jul 2017 | n/a
802.22b | April 2016 | July 2017 | Mar 2018
802.22-REV | Oct 2020 | Mar 2022 | Aug 2022

## Slide 34: Why does IEEE 802 spend so much time and effort to obtain ISO/IEC approval?
  IEEE 802 have put a lot of effort into ensuring our standards receive the ISO/IEC stamp of approval
    … starting with 802.11 and 802.3
    .. but now including 802.1, 802.15, 802.21, 802.22
  The following pages contain some material discussed in previous meetings … that may be refined further in the future

## Slide 35: Why does IEEE 802 spend so much time and effort to obtain ISO/IEC approval?
  This “international” stamp was certainly useful in the WAPI case because we could argue that 802.11 could not be excluded from the Chinese market under WTO rules
    … although Wi-Fi was partially excluded in practice for a while
  We discussed examples in Sep 2022 where it is useful in other situations
    Some European regulations suggest a preference for “international” standards (ie not IEEE) – see next page
    The Australian Govt sometimes requires references to “international” standards
    ITU-T prefers references to “international” standards (i.e., not IEEE)

## Slide 36: ISO/IEC approval of IEEE 802 standards is important in some circumstances in Europe
A summary of why ISO/IEC standardisation is important in Europe
  The EU Standardisation Regulation (an EU Regulation is a law that applies to all member states) is 1025/2012
  The definitions in article 2 of 1025/2012 include the following:
    (1) 'standard' means a technical specification, adopted by a recognised standardisation body, for repeated or continuous application, with which compliance is not compulsory, and which is one of the following:
      (a) 'international standard' means a standard adopted by an international standardisation body;
      (b) 'European standard' means a standard adopted by a European standardisation organisation;
      (c) 'harmonised standard' means a European standard adopted on the basis of a request made by the Commission for the application of Union harmonisation legislation;
      (d) 'national standard' means a standard adopted by a national standardisation body;
    (9) 'international standardisation body' means the International Organisation for Standardisation (ISO), the International Electrotechnical Commission (IEC) and the International Telecommunication Union (ITU)".
    (10) 'national standardisation body' means a body notified to the Commission by a Member State in accordance with Article 27 of this Regulation.
  …

## Slide 37: ISO/IEC approval of IEEE 802 standards is important in some circumstances in Europe
A summary of why ISO/IEC standardisation is important in Europe
  Based on the above, to be considered a "standard" under regulation 1025/2012, a standard must be from a "recognised standardisation body", either an "international standard" from ISO, IEC or ITU, a "European standard" or "harmonised standard" from CEN, CENELEC or ETSI, or a "national standard" from a Member State national standardisation body.
  As a result, while an ISO/IEC/IEEE 8802 standard is considered a "standard" under regulation 1025/2012, an IEEE 802 standard is not. One of the impacts of this is that strictly speaking, while an ISO/IEC/IEEE 8802 standard can be directly referenced in public procurement within the EU, an IEEE 802 standard cannot.
  While this approach to the definition of a "standard" and its impact on public procurement may work in sectors such as construction products, it isn't really practical in the Information and Communication Technology (ICT) sector where many standards bodies other than the "recognised standardisation" bodies develop widely use standards, IEEE being a prime example.
  …

## Slide 38: ISO/IEC approval of IEEE 802 standards is important in some circumstances in Europe
A summary of why ISO/IEC standardisation is important in Europe
  This is recognised in Article 13 'Identification of ICT technical specifications eligible for referencing' of the regulation that provides a path to "... identify ICT technical specifications that are not national, European or international standards, but meet the requirements set out in Annex II, which may be referenced, primarily to enable interoperability, in public procurement.". The requirements in Annex II are very similar to the WTO TBT principles.
  Unfortunately, however, as you will see from the list of identified Technical Specification available here, none have been added since 2017, and as you will see from the minutes of the 29th Meeting of the European Multi-Stakeholder Platform on ICT Standardisation held on 18 June 2020 - action item 24.7, progressing identifications are 'On hold’.
  …

## Slide 39: ISO/IEC approval of IEEE 802 standards is important in some circumstances in Europe
A summary of why ISO/IEC standardisation is important in Europe
  In summary, in Andrew Myles’ opinion, ISO/IEC/IEEE standardisation is useful as it permits direct referencing of these standards in EU public procurement (although it is not known how important this is in practice).
  If IEEE 802 standard were not adopted as ISO/IEC/IEEE 8802 standard, the other method to enable direct referencing would be the identification process, but as noted above, this process appears to be permanently on hold.
  ISO/IEC/IEEE standardisation is also a useful fallback in situations where an individual or organisation choose to rigidly follow the 1025/2012 regulation and won't acknowledge that IEEE 802 standards are "standards".

## Slide 40: IEEE 802.1 has 9 standards in the pipeline for adoption under the PSDO
802 | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
.1Q-REV | D1.0 | Sep 21 | Passed | 26 Mar 23 | Waiting | - | Jul 23
.1Qcz | D1.2 | Aug 20 | In ballot | 12 Nov 23 | - | - | -
.1AEdk | D2.1 | Sep 22 | In ballot | 12 Nov 23 | - | - | -
802f | D2.0 | Feb 23 | - | - | - | - | -
.1Qcw | D2.0 | Dec 22 | - | - | - | - | -
.1Qcj | D2.0 | Dec 22 | - | - | - | - | -
.1ASdr | D1.2 | Oct 22 | - | - | - | - | -
.1CS-2020/Cor1 | D2.0 | Oct 22 | - | - | - | - | -
.1DC | D3.0 | Oct 22 | - | - | - | - | -

## Slide 41: IEEE 802.1 WG has a number of regular participants in IEEE 802 JTC1 SC activities
Regular participants & stakeholders
  Karen Randall
  Paul Congdon
  Glen Parsons (802.1 WG Chair)
  Mick Seaman
  Jessy Rouyer

## Slide 42: Bridges & Bridged Networks IEEE 802.1Q-REV-2022 passed 60-day pre-ballot
Drafts sent to SC 6: sent
  802.1Q-REV D1.0 was liaised for information on 23 Sep 2021 (N17614)
60-day pre-ballot: closed 26 Mar 2023
  (N18055) – passed with one negative vote from the China NB for the usual reason.
FDIS ballot: waiting

## Slide 43: Bridges & Bridged Networks: Congestion Isolation IEEE 802.1Qcz was liaised for information in Aug 2020
Drafts sent to SC 6: sent
  802.1Qcz D1.2 was liaised in Aug 2020 (N17269)
60-day pre-ballot: In ballot
  There was a WG/EC motion in Nov 2020 to submit into the PSDO adoption process once approved & published
    (Jul 2021) IEEE 802.1Qcz is waiting on IEEE 802.1Q-Rev, but it is also dependent on IEEE 802.1ABcu for the YANG; no amendments of IEEE 802.1Q-Rev can publish until IEEE 802.1Q-Rev is published
    (Nov 2022) IEEE 802.1Qcz is going out for an SA recirculation ballot, so it’s not quite ready for balloting
    (Jan 2023) IEEE 802.1Qcz finished SA recirc ballot comment resolution
    (Feb 2023) D2.7 generated after another recirc/comment resolution cycle
    (Aug 2023) submitted for approval as it was published on 5 Jun 2023
    (Sept 2023) Ballot initiated 14 Sep 2023, close 12 Nov 2023
FDIS ballot: waiting

## Slide 44: MAC Privacy Protection IEEE 802.1AEdk D2.1 liaised for information in Sep 2022
Drafts sent to SC 6: sent
  IEEE 802.1AEdk D2.1 was liaised for information in Sep 2022 (N17883)
  (Nov 2022) 802.1AEdk will probably be submitted for balloting in Jan 2023
  (Mar 2023) Motion for RevCom and publication expected. Motion passed to send for SC 6 adoption upon IEEE publication.
60-day pre-ballot: waiting
Formally submitted for approval on 22 Aug 2023
Ballot initiated 14 Sept 2023, closes 12 Nov 2023
FDIS ballot: waiting

## Slide 45: YANG Data Model for Ethertypes IEEE 802f was liaised for information in Feb 2023
Drafts sent to SC 6: 15 Feb 2023
  (Nov 2022) 802f will be sent for information soonish, with its SA ballot expected in the next couple of months.
    (Jan 2023) IEEE 802f will start SA ballot soon hopefully
    (Feb 2023) Submission: N17968
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 46: YANG Data Models for Scheduled Traffic, Frame Preemption, Per-Stream Filtering & Policing IEEE 802.1Qcw D2.0 was liaised for information in Dec 2022
Drafts sent to SC 6: sent
  (Dec 2022) D2.0 was liaised for information (N17934)
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 47: Automatic Attachment to Provider Backbone Bridging (PBB) services IEEE 802.1Qcj D2.0 was liaised for information in Dec 2022
Drafts sent to SC 6: sent
  (Nov 2022) IEEE 802.1 is planning to have a motion at this plenary to send IEEE P802.1Qcj to SC 6 for information when the SA ballot starts
  (Dec 2022) D2.0 liaised for information (N17933)
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 48: Timing and Synchronization for Time-Sensitive Applications Amendment: Inclusive Terminology IEEE 802.1ASdr was liaised for information
Drafts sent to SC 6: sent
  (Oct 2023) Draft 1.2 liaised for information (N18119)
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 49: Automatic Attachment to Provider Backbone Bridging (PBB) services IEEE 802.1CS-2020/Cor-1 was liaised for information
Drafts sent to SC 6: sent
  During March 2023 plenary, WG approved sending draft upon start of SA ballot.
  (Oct 2023) Draft 2.0 liaised for information (N18124)
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 50: Quality of Service Provision by Network Systems IEEE 802.1DC was liaised for information
Drafts sent to SC 6: sent
  (Oct 2023) Draft 3.0 liaised for information (N18124)
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 51: IEEE 802.3 has 8 standards in the pipeline for adoption under the PSDO process
802 | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
.3-REV | Std | Nov 22 | Waiting | - | Waiting | - | n/a
.3dd | - | - | - | - | - | - | -
.3cs | - | - | - | - | - | - | -
.3db | - | - | - | - | - | - | -
.3ck | - | - | - | - | - | - | -
.3de | - | - | - | - | - | - | -
.3cx | - | - | - | - | - | - | -
.3cz | - | - | - | - | - | - | -

## Slide 52: IEEE 802.3 WG has a number of regular participants in IEEE 802 JTC1 SC activities
Regular participants
  David Law (802.3 Chair)
  Adam Healey

## Slide 53: IEEE 802.3-REV was submitted into the PSDO process in Feb 2023
Drafts sent to SC 6: submitted Feb 2023
  (Nov 2022) IEEE 802.3-REV was liaised for information (N17882)
  (Nov 2022) has the EC approved submission to PSDO
60-day pre-ballot: waiting
Pre-ballot had been scheduled for 27 April 2023
Pre-ballot cancelled on 27 April 2023. The reason stated by the ISO/IEC JTC 1/SC 6 Committee Manager was "due to the discovery of negative Letters of Assurance (LoA) associated with this standard, and as a result, the ballot cannot proceed”
Adoption of IEEE 802.3 standards halted until the disagreement about negative LoAs is resolved.
FDIS ballot: waiting

## Slide 54: IEEE 802.11 has 14 standards in the pipeline for adoption under the PSDO
Std | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
.11ax | D6.0 | Jan 20 | Passed | 10 Aug 21 | On hold | - | Nov 2021
.11ay | D8.0 | Feb 21 | Not approved | 9 Oct 21 | - | - | n/a
.11az | D4.0 | Apr 22 | - | - | - | - | -
.11ba | D8.0 | Feb 21 | On hold | - | - | - | -
.11bb | D4.0 | Dec 22 | Waiting | - | - | - | -
.11bc | D4.0 | Dec 22 | Waiting | - | - | - | -
.11bd | D4.0 | Jun 22 | Waiting | - | - | - | -
.11be | Waiting | - | - | - | - | - | -
.11bf | Waiting | - | - | - | - | - | -
.11 Cor 1 | Waiting | - | - | - | - | - | -

## Slide 55: IEEE 802.11 has 14 standards in the pipeline for adoption under the PSDO (continued)
Std | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
.11bh | Waiting | - | - | - | - | - | -
.11bi | Waiting | - | - | - | - | - | -
.11bk | Waiting | - | - | - | - | - | -
.11bn | Waiting | - | - | - | - | - | -

## Slide 56: IEEE 802.11 WG has a number of regular participants in IEEE 802 JTC1 SC activities
Regular participants
  Dan Harkins
  Dorothy Stanley (802.11 WG Chair)
  Peter Yee

## Slide 57: Wi-Fi 6 IEEE 802.11ax 60-day pre-ballot passed and responses have been sent, but it is on hold
Drafts sent to SC 6: sent
  Liaised D4.0 out of March 2019 meeting (N16974)
  Liaised D6.0 out of Jan 2020 meeting (N17096)
60-day pre-ballot: passed with responses sent but on hold
  IEEE 802.11ax 60-day ballot passed on 10 Aug 2021 (N17599)
    Passed 10/0/9 on need for ISO standard
    Passed 6/4/9 on support for submission to FDIS
    With negative comments from China (usual security comments)
    With negative comments from Sweden, Finland, Germany & a positive comment from Japan (in relation to negative LoAs)
    A response was sent – awaiting resolution
FDIS ballot: waiting

## Slide 58: Responses were sent in Nov 2021 in relation the 60-day ballot on IEEE 802.11ax
Latest news (Nov 2021)
  Ultimately the IEEE SA directed IEEE 802 that:
    The IEEE SA President would respond to ISO on the IPR related issues, based on content that had been developed by IEEE 802 (see 11-21-1400-05)
      Sent on 8 Nov 2021 (see following slides for update)
    IEEE 802 respond to the China NB technical comments to SC 6 (see 11-21-1400-08)
      IEEE 802 EC approval occurred on 5 Nov 2021
      IEEE SA staff liaised on 8 Nov 2021 (N17646)
  This approach had a number of benefits:
    It avoided the IEEE 802 EC arguing about whether it should respond to the non-technical IPR related comments
    It highlighted the importance of the issue to IEEE SA
    It meant responses were sent to SC 6 & ISO quickly so that ISO/IEEE SA staff discussions could commence

## Slide 59: There is not yet closure on the 802.11ax IPR related issue … but there are ongoing discussions
Latest news (Jan 2023)
  There have lots of discussions between various stakeholders over the last year or so … with limited progress so far
  It is now understood that the 802.11ax IPR related issue is still being discussed … and so hopefully good news can be reported in the future

## Slide 60: Enhanced Throughput for Operation in License-exempt Bands above 45 GHz IEEE 802.11ay 60-day ballot not approved on 9 Oct 2021 and the process will need to restart
Drafts sent to SC 6: sent
  Liaised D3.0 out of March 2019 meeting (N16974)
  Liaised D5.0 out of Jan 2020 meeting (N17096)
  Liaised D7.0 out of Jan 2021 meeting (N17479)
60-day pre-ballot: not approved
  802.11ay 60-day ballot not approved on 9 Oct 2021 (N17628)
    Passed 10/1/8 (Belgium) on need for ISO standard
    Not approved 6/6/7 (Belgium, Canada, China, Finland, Netherlands, Sweden) on support for submission to FDIS
      Note: Germany voted yes, unlike for 802.11ax
      Note: Japan also commented, while voting yes
      Note that three blanket negative LOAs and one explicit negative LOA on 802.11ay caused a similar problem to the 802.11ax problem
    Not passing means the process will need to restart once the IPR issue is sorted
FDIS ballot: waiting

## Slide 61: Next generation positioning IEEE 802.11az was liaised for information in Apr 2022
Drafts sent to SC 6: waiting
  802.11az D4.0 was liaised for information on 8 Apr 2022 (N17742)
  (Nov 2022) Approved for submission to PSDO (after publication)
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 62: Wake up radio IEEE 802.11ba is waiting for start of 60-day ballot, but it will not start until IPR related issues are resolved
Drafts sent to SC 6: sent
  Liaised D6.0 in March 2020 (N17157)
  Liaised D8.0 in Feb 2021 (N17479)
60-day pre-ballot: on hold
  WG motion to enter PSDO process approved in May 2021
    (Jul 2021) EC approved, for submission after publication
  (Nov 2021) The ballot has not yet started but it may run into the same IPR related issue as 802.11ay (and 802.11ax) because there are explicit negative LoAs associated with 802.11ba – and so it will not be progressed by IEEE 802 until the disagreement about negative LoAs is resolved.
FDIS ballot: waiting

## Slide 63: Light Communications IEEE 802.11bb was liaised in Dec 2022
Drafts sent to SC 6: sent
  (Dec 2022) D4.0 liaised for information
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 64: Enhanced Broadcast Service IEEE 802.11bc was liaised in Dec 2022
Drafts sent to SC 6: sent
  (Dec 2022) D4.0 liaised for information
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 65: Enhancements for Next Generation V2X IEEE 802.11bd D4.0 was liaised for information in June 2022
Drafts sent to SC 6: sent
  802.11bd D4.0 was liaised in June 2022 (N17743)
60-day pre-ballot: waiting
  (Nov 2022) Approved for submission to PSDO (after publication)
    [Realistically, this won’t happen because IEEE 802.11bd has negative LoAs]
FDIS ballot: waiting

## Slide 66: Extremely High Throughput IEEE 802.11be will be liaised when appropriate
Drafts sent to SC 6: waiting
  (Oct 2022) No approved draft yet
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 67: Correct IEEE 802.11ay Assignment of Protected Announce Support bit IEEE 802.11-2020 Cor 1 will be liaised for approval when appropriate
Drafts sent to SC 6: waiting
  Probably only makes sense to liaise or submit after the 802.11ay IPR related issue is resolved
60-day FDIS ballot: waiting

## Slide 68: WLAN Sensing IEEE 802.11bf will be liaised when appropriate
Drafts sent to SC 6: waiting
  (Jul 2023) No approved draft yet
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 69: Randomized and Changing MAC Addresses (RCM) IEEE 802.11bh will be liaised when appropriate
Drafts sent to SC 6: waiting
  (Jul 2023) No approved draft yet
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 70: Enhanced Data Privacy (EDP) IEEE 802.11bi will be liaised when appropriate
Drafts sent to SC 6: waiting
  (Jul 2023) No approved draft yet
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 71: 320 MHz Positioning IEEE 802.11bk will be liaised when appropriate
Drafts sent to SC 6: waiting
  (Jul 2023) No approved draft yet
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 72: Ultra High Reliability IEEE 802.11bn will be liaised when appropriate
Drafts sent to SC 6: waiting
  (Nov 2023) No approved draft yet
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 73: IEEE 802.15 WG has 14 standards in the pipeline for adoption under the PSDO
Std | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
.4-2020 | Std | Jan 23 | In ballot | 12 Nov 23 | Waiting | - | -
.4w-2020 | Std | Jan 23 | Waiting | - | Waiting | - | -
.4y-2021 | Waiting | - | Waiting | - | Waiting | - | -
.4z-2020 | Std | Jan 23 | Waiting | - | Waiting | - | -
.4aa-2022 | Std | Jan 23 | Waiting | - | Waiting | - | -
.3-2016 | No need | - | No need | - | No need | - | -
.3d-2017 | Std | Jan 23 | Waiting | - | Waiting | - | -
.3e-2017 | Std | Jan 23 | Waiting | - | Waiting | - | -
.3f-2017 | Std | Jan 23 | Waiting | - | Waiting | - | -
.3-2023 | Waiting | - | Waiting | - | Waiting | - | -

## Slide 74: IEEE 802.15 WG has 14 standards in the pipeline for adoption under the PSDO
Std | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
.9-2021 | Std | Jan 23 | In ballot | 12 Nov 23 | Waiting | - | -
.7-2018 | Waiting | - | Waiting | - | Waiting | - | -
.7a | Waiting | - | Waiting | - | Waiting | - | -
.13 | Waiting | - | Waiting | - | Waiting | - | -
.6 | Waiting | - | Waiting | - | Waiting | - | -

## Slide 75: IEEE 802.15 WG has a number of regular participants in IEEE 802 JTC1 SC activities
Regular participants
  Clint Powell
  Phil Beecher
  Ann Krieger

## Slide 76: Low-rate wireless networks IEEE 802.15.4-2020 has been liaised for information
Drafts sent to SC 6: Jan 2023
  (Sep 2022) It has been discovered that IEEE 802.15.4-2015 is already ratified as ISO/IEC/IEEE 8802-15-4-2018 (via JTC1/SC31, but now returned to SC 6); the new plan is to submit IEEE 802.15.4-2020 and amendments (802.15.4w/y/z/aa) ASAP for information … and then for PSDO consideration in early 2023
  (Nov 2022) IEEE 802.15.4 (and its amendments) have been approved by the IEEE 802 EC to be sent for information; IEEE 802.15.4 has been approved by the IEEE 802 EC to be submitted for adoption
    (Dec 2022) LS sent notifying SC 6 of plan (N17927)
    (Jan 2023) Staff is sending information version soon
60-day pre-ballot: in ballot
    Ballot initiated 14 Sep 2023, closes 12 Nov 2023
FDIS ballot: waiting

## Slide 77: Extension to low-energy critical infrastructure monitoring PHY IEEE 802.15.4w-2020 has been liaised for information
Drafts sent to SC 6: Jan 2023
  (Sep 2022) It has been discovered that IEEE 802.15.4-2015 is already ratified as ISO/IEC/IEEE 8802-15-4-2018 (via JTC1/SC31, but now returned to SC 6); the new plan is to submit IEEE 802.15.4-2020 and amendments (802.15.4w/y/z/aa) ASAP for information … and then for PSDO consideration in early 2023
  (Nov 2022) IEEE 802.15.4 (and its amendments) have been approved by the IEEE 802 EC to be sent for information; IEEE 802.15.4 has been approved by the IEEE 802 EC to be submitted for adoption
    (Dec 2022) LS sent notifying SC 6 of plan (N17927)
      Is it still planned that 802.15.4w is submitted into PSDO process?
      Staff suggests getting approval for submission into PSDO process after Mar 2023
    (Jan 2023) Staff is sending information version soon
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 78: AES-256 encryption & security extensions IEEE 802.15.4y-2021 will be liaised for information soon
Drafts sent to SC 6: waiting
  (Sep 2022) It has been discovered that IEEE 802.15.4-2015 is already ratified as ISO/IEC/IEEE 8802-15-4-2018 (via JTC1/SC31, but now returned to SC 6); the new plan is to submit IEEE 802.15.4-2020 and amendments (802.15.4w/y/z/aa) ASAP for information … and then for PSDO consideration in early 2023
  (Nov 2022) IEEE 802.15.4 (and its amendments) have been approved by the IEEE 802 EC to be sent for information; IEEE 802.15.4 has been approved by the IEEE 802 EC to be submitted for adoption
    Dec 2022) LS sent notifying SC 6 of plan (N17927)
      Is it still planned that 802.15.4y is submitted into PSDO process?
      Staff suggests getting approval for submission into PSDO process after Mar 2023
    (Jan 2023) Staff is sending information version soon
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 79: Enhanced UWB PHYs & associated ranging techniques IEEE 802.15.4z-2020 has been liaised for information
Drafts sent to SC 6: Jan 2023
  (Sep 2022) It has been discovered that IEEE 802.15.4-2015 is already ratified as ISO/IEC/IEEE 8802-15-4-2018 (via JTC1/SC31, but now returned to SC 6); the new plan is to submit IEEE 802.15.4-2020 and amendments (802.15.4w/y/z/aa) ASAP for information … and then for PSDO consideration in early 2023
  (Nov 2022) IEEE 802.15.4 (and its amendments) have been approved by the IEEE 802 EC to be sent for information; IEEE 802.15.4 has been approved by the IEEE 802 EC to be submitted for adoption
    Dec 2022) LS sent notifying SC 6 of plan (N17927)
      Is it still planned that 802.15.4z is submitted into PSDO process?
      Staff suggests getting approval for submission into PSDO process after Mar 2023
    (Jan 2023) Staff is sending information version soon
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 80: Higher data rate extension to Smart Utility Network FSK PHY IEEE 802.15.4aa-2022 has been liaised for information
Drafts sent to SC 6: Jan 2023
  (Sep 2022) It has been discovered that IEEE 802.15.4-2015 is already ratified as ISO/IEC/IEEE 8802-15-4-2018 (via JTC1/SC31, but now returned to SC 6); the new plan is to submit IEEE 802.15.4-2020 and amendments (802.15.4w/y/z/aa) ASAP for information … and then for PSDO consideration in early 2023
  (Nov 2022) IEEE 802.15.4 (and its amendments) have been approved by the IEEE 802 EC to be sent for information; IEEE 802.15.4 has been approved by the IEEE 802 EC to be submitted for adoption
    (Dec 2022) LS sent notifying SC 6 of plan (N17927)
      Is it still planned that 802.15.4aa is submitted into PSDO process?
      Staff suggests getting approval for submission into PSDO process after Mar 2023
    (Jan 2023) Staff is sending information version soon
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 81: High data rate wireless multi-media networks There is no need to submit IEEE 802.15.3-2016 for ratification as an ISO/IEC/IEEE standard
Drafts sent to SC 6: no need
  (Sep 2022) Discovered that IEEE 802.15.3-2016 already ratified as ISO/IEC 8802-15-3: 2017 (via JTC1/SC31, but now returned to SC 6); the new plan is to submit amendments (d/e/f) ASAP for information … and then PSDO submission in early 2023
  (Dec 2022) A LS was sent specifying plan (N17926)
    Overtaken by events (see slide on 802.15.3-2023)
60-day pre-ballot: no need
FDIS ballot: no need

## Slide 82: 100 Gb/s wireless switched point-to-point physical layer IEEE 802.15.3d-2017 has been liaised for information
Drafts sent to SC 6: Jan 2023
  (Sep 2022) Discovered that IEEE 802.15.3-2016 already ratified as ISO/IEC 8802-15-3: 2017 (via JTC1/SC31, but now returned to SC 6); the new plan is to submit amendments (d/e/f) ASAP for information … and then PSDO submission in early 2023
  (Nov 2022) The IEEE 802.15.3 amendments have been approved by the IEEE 802 EC to be submitted for information; they have not yet been approved to be submitted for adoption
    (Dec 2022) A LS was sent specifying plan (N17926)
      It states that the revision will be submitted for approval in the future; it is unclear whether the amendment will be submitted for approval; or just information
      Staff suggests getting approval for submission into PSDO process after Mar 2023
    (Jan 2023) Staff is sending information version soon
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 83: High-rate close proximity point-to-point communications IEEE 802.15.3e-2017 has been liaised for information
Drafts sent to SC 6: Jan 2023
  (Sep 2022) Discovered that IEEE 802.15.3-2016 already ratified as ISO/IEC 8802-15-3: 2017 (via JTC1/SC31, but now returned to SC 6); the new plan is to submit amendments (d/e/f) ASAP for information … and then PSDO submission in early 2023
  (Nov 2022) The IEEE 802.15.3 amendments have been approved by the IEEE 802 EC to be submitted for information; they have not yet been approved to be submitted for adoption
    (Dec 2022) A LS was sent specifying plan (N17926)
      It states that the revision will be submitted for approval in the future; it is unclear whether the amendment will be submitted for approval; or just information
      Staff suggests getting approval for submission into PSDO process after Mar 2023
    (Jan 2023) Staff is sending information version soon
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 84: Extending the PHY for mmWave to operate from 57.0 GHz to 71 GHz IEEE 802.15.3f-2017 has been liaised for information
Drafts sent to SC 6: Jan 2023
  (Sep 2022) Discovered that IEEE 802.15.3-2016 already ratified as ISO/IEC 8802-15-3: 2017 (via JTC1/SC31, but now returned to SC 6); the new plan is to submit amendments (d/e/f) ASAP for information … and then PSDO submission in early 2023
  (Nov 2022) The IEEE 802.15.3 amendments have been approved by the IEEE 802 EC to be submitted for information; they have not yet been approved to be submitted for adoption
    (Dec 2022) A LS was sent specifying plan (N17926)
      It states that the revision will be submitted for approval in the future; it is unclear whether the amendment will be submitted for approval; or just information
      Staff suggests getting approval for submission into PSDO process after Mar 2023
    (Jan 2023) Staff is sending information version soon
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 85: High data rate wireless multi-media networks IEEE 802.15.3-2023 will be submitted into the PSDO process soon
Drafts sent to SC 6: waiting
  (May 2023)
    IEEE 802.15.3 is now on RevCom agenda for June 2023.
  (September 2023)
    IEEE 802.15.3 is now on RevCom agenda for September 2023.
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 86: Short-range optical wireless communications IEEE 802.15.7-2018 will be submitted into the PSDO process soon
Drafts sent to SC 6: waiting
  (Sept 2022) Plan is to submit to PSDO ASAP
    (Dec 2022) A LS was sent specifying plan (N17929)
    (Nov 2022) Do we have EC approval for information & submission?
    (Jan 2023) Staff noted that she could not find EC motion
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 87: Higher rate, longer range optical camera communications IEEE 802.15.7a will be submitted into the PSDO process when ready
Drafts sent to SC 6: waiting
  (Sept 2022) 802.15.7a LB starts soon so is not ready for submission
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 88: Transport of key management protocol (KMP) datagrams IEEE 802.15.9-2021 has been liaised for information
Drafts sent to SC 6: Jan 2023
  (Dec 2022) A LS statement (N17928) was sent outlining a plan to submit IEEE 802.15.9-2021 for information soon, with a PSDO submission later in the year
  (Jan 2023) Staff sent the document for information
60-day pre-ballot: in ballot
    - Formally submitted on 22-Aug-2023
    - Ballot initiated 14 Sep 2023, closes 12 Nov 2023
FDIS ballot: waiting

## Slide 89: Multi Gigabit/sec Optical Wireless Communication IEEE 802.15.13 will be submitted into the PSDO process
Drafts sent to SC 6: waiting
  (Sep 2022) In SA ballot now – 802.15.13 will probably be submitted for information purposes after it firms up a bit more during the SA ballot process
  (Jan 2023) Approved by RevCom, should be published as IEEE 802.15.13-2023.
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 90: Body Area Networking There is no need to submit IEEE 802.15.6-2012 for ratification as ISO/IEC/IEEE standard
Drafts sent to SC 6: waiting
  (Sep 2022) Discovered that IEEE 802.15.6-2012 already ratified as ISO/IEC 8802-15-6: 2017 (via JTC1/SC31, but now returned to SC 6); the new plan is to submit when revised in a year or so
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 91: IEEE 802.19 has not yet considered submissions to the PSDO process
802 | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved

## Slide 92: IEEE 802.19 WG has had a number of regular participants in IEEE 802 JTC1 SC activities
Regular participants
  <none at the moment>

## Slide 93: IEEE 802.21 has no standard in the pipeline for adoption under the PSDO
802 | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved

## Slide 94: IEEE 802.22 has no standard in the pipeline for adoption under the PSDO
802 | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved

## Slide 95: IEEE 802.22 WG had a number of regular participants in IEEE 802 JTC1 SC activities
Regular participants
  Apurva Mody

## Slide 96: IEEE 802.22 WG had a number of regular participants in IEEE 802 JTC1 SC activities
Regular participants
  Apurva Mody

## Slide 97: PWI proposal: Multi-Functional Reconfigurable Intelligent Surface for Wireless Communication
Proposed by the China National Body in ISO/IEC JTC 1/SC 6/WG 1 N 385
Difference from previous RIS schemes appears to be:
Simultaneous amplification and reflection
“The MF-RIS first amplifies the incident signals, then divides them into reflection and refraction parts by power split circuits.”
RIS presentations have been heard before in IEEE 802.11 WNG and IEEE 802.15 WNG.

## Slide 98: PWI report of PWI 21284 on Requirements for APGAN Wireless and Radio Communications
APGAN is Automobile Proving Ground Area Network
Includes DSRC (IEEE 802.11p) as a Radio Access Technology
Also covers ordinary IEEE 802.11 as a separate RAT
Document was posted to show progress toward generating a New work item proposal (NP)
Project initiated in March 2023

## Slide 99: Study report for PWI Proposal on Space Fibre Channel Network Time Synchronization Protocol
Report surveys various time synchronization protocols (NTP, IEEE 1588, SAE AS6802, White Rabbit, 802.1AS, IEEE C37.238, IEEE C37.242, Fibre Channel Protocol FC-FS)
Notes publication of ISO/IEC/IEEE 8802-1AS:2021 as a reason why the FCTSP work should be done in ISO/IEC JTC 1/SC 6/WG 1

## Slide 100: SC 6 will have a plenary meeting in December 2023 in China
Meeting
  ISO/IEC JTC 1/SC 6
    WG 1 meeting
    WG 7 meeting
    WG 10 meeting
    Joint WGs meeting
    AG/AHG meetings
Dates
  11-15 December 2023
Location
  Nanning, Guangxi, China
  (N18072) for logistics
Deadlines
  30 Oct 2023: WG1 calling notice
  30 Oct 2023: Proposals for new WG1 agenda items / Proposals for the addition of new WG1 work item proposals
  27 Nov 2023: Contributions on existing WG1 agenda items and submitted documents
  4 Dec 2023: Comments on posted WG1 documents
  SC 6 itself has earlier deadlines

## Slide 101: The JTC1 SC chair will develop a liaison report for the SC 6 plenary meeting in December 2023
  Traditionally, IEEE 802 provides a status report to SC 6 at their plenary meetings
  Over the years, the status report has morphed to be a refined subset of this agenda … which SC 6 has indicated they appreciate
  Peter Yee usually puts the report together … and will do so again this time

## Slide 102: Call for Convenor for JTC 1/SC 6/WG 1
N18079 is a call for a new or continuing convenor for WG 1.
Deadline for application submission to the SC 6 Committee Manager is 30 September 2023.
A request was made on 3 October 2023 by the China NB to extend Mr. Zhenhai Huang as the convenor.
No other parties appear to have submitted requests for the convenorship.

## Slide 103: ISO/IEC JTC 1/SC 6 has a new Committee Manager as of July 2019
  The new ISO/IEC JTC 1/SC 6 Committee Manager is
    Name: Mr. Jungyup OH
    Nationality: Korea (Rep. of)
    Affiliation: Telecommunications Technology Association (TTA)
    E-mail: houman@tta.or.kr
  Various submissions to SC 6 should now be sent to Mr Oh

## Slide 104: ISO/IEC JTC1 has changed the rules so that “experts” rather than “NBs” participate in WGs
  The organisational structure in ISO/IEC JTC1 changed in 2016 to align its operation with ISO rules
  A communication from JTC1 states
    Working Groups are comprised of INDIVIDUAL EXPERTS appointed by National Bodies and Liaison Organizations
    These experts MUST be entered into Global Directory to be considered a member of the WG and to receive documents
    National Bodies are responsible for ensuring that their expert appointments are up to date
    Liaison Organizations work via ITTF to maintain their expert members
    If the expert is NOT in Global Directory, he/she will not receive documents and will NOT be considered a member of the WG.
  Technically this means someone not in the Global Directory could not speak SC 6 meetings but no one has raised this as an issue

## Slide 105: The SC Chair has been empowered to appoint experts to the SC 6 document access lists
  One way of dealing with this change is to empower the SC Chair to appoint experts to WG1 and WG7, with the understanding that anyone who volunteers will be appointed
  Motion (ratified in May 2014 by IEEE 802 EC)
    The IEEE 802 JTC1 SC recommends to the IEEE 802 EC that the Chair of the IEEE 802 JTC1 SC be empowered to submit the names to ITTF of any IEEE 802 members who volunteer as “experts” to the appropriate Working Group lists in ISO/IEC JTC1
    Moved
    Seconded
    Result 9/0/0
  Yell if you would like to be added …

## Slide 106: Are there any other matters for consideration by IEEE 802 JTC1 SC?

## Slide 107: The IEEE 802 JTC1 SC will adjourn for the week
Motion:
  The IEEE 802 JTC1 SC, having completed its business in September 2023, adjourns
    By consent

## Slide 108: Additional process material

## Slide 109: The SC agreed in Nov 2014 on a process for developing & approving PSDO comment resolutions
In the beginning …
  All 60 ballot and FDIS ballot comment responses were developed and approved by the IEEE 802 JTC1 SC and then the IEEE 802 EC
Now that we have matured …
  Most WGs are processing and approving comment resolutions, and then forwarding the resolutions to IEEE 802 EC directly without involving the IEEE 802 JTC1 SC
  The IEEE 802 JTC1 SC is continuing to provide advice on non-technical comments, to ensure consistency across WGs
Going forward …
  It is planned that we institutionalise the practice above – see11-15-1287
  It is expected that the WG Chairs and the IEEE 802 JTC1 SC Chair will keep each other informed

## Slide 110: Old status pages

## Slide 111: IEEE 802.11-2012 has been published
60-day pre-ballot: passed & comment resolutions liaised
  60-day pre-ballot passed in 2012
    Responses to comments were liaised to SC 6
FDIS ballot: passed & comment resolutions liaised
  FDIS passed in 2012 (6N15494)
  Standard published as ISO/IEC/IEEE 8802-11:2012
  FDIS comments liaised in Dec 2013
    All the FDIS comments were submitted to TGmc for processing
    Additional comments from Swiss NB in N15623 (a response to the IEEE 802/SC 6 collaboration procedure) were also referred to TGmc
    All the comments have been considered and resolutions approved as of November 2013
      See 11-13-0123-05 liaised as 6N15832 in Nov 2013

## Slide 112: IEEE 802.1X-2010 has been published
60-day pre-ballot: passed & comment resolutions liaised
  Submission of IEEE 802.1X-2010 in N15515 in Dec 2012
  Pre-ballot passed in 2013
    Voting results in N15555
    Comments from China NB replied to by IEEE 802 in N15607
FDIS ballot: passed & comment resolutions liaised
  FDIS passed 16/1/12 on 21 Oct 2013
    Voting results in N15771
    China NB only negative vote, with comments from China NB & Switzerland NB
  FDIS comments resolved in Dec 2013
    Liaised to SC 6 as N15871 in Jan 2014
  Standard has been published as ISO/IEC/IEEE 8802-1X:2013

## Slide 113: IEEE 802.1AE-2006 has been published
60-day pre-ballot: passed & comment resolutions liaised
  Submission of IEEE 802.1AE-2006 in N15516 in Dec 2012
  Pre-ballot passed in 2013
    Voting results in N15556
    Comments from China NB replied to by IEEE 802 in N15608
FDIS ballot: passed & comment resolutions liaised
  FDIS passed 16/1/13 on 21 Oct 2013
    Voting results in N15770
    China NB only negative vote, with comments from China NB & Switzerland NB
  FDIS comments resolved in Dec 2013
    Liaised to SC 6 as N15871 in Jan 2014
  Standard has been published as ISO/IEC/IEEE 8802-1AE:2013

## Slide 114: IEEE 802.1AB-2009 has been published
60-day pre-ballot: passed & comment resolutions liaised
  Submission of IEEE 802.1AB-2009 in N15588 in March 2013
  Pre-ballot passed in May 2013
    Voting results in N15626
    Comments from China replied to in N15659
FDIS ballot: passed & comment resolutions liaised
  FDIS passed 16/1/16 on 18 Dec 2013
    Voting results in N15829
    China NB only negative vote, with comments from China NB & Switzerland NB
  FDIS comment responses were approved by 802.1 WG in March 2014, and liaised to SC 6 in May 2014 as N15944
  The standard was published as ISO/IEC/IEEE 8802-1AB:2014 on 15 March 2014

## Slide 115: IEEE 802.1AR-2009 has been published
60-day pre-ballot: passed & comment resolutions liaised
  Submission of IEEE 802.1AR-2009 in N15589 in March 2013
  Pre-ballot passed in May 2013
    Voting results in N15627
    Comments from China replied to in N15659
FDIS ballot: passed & comment resolutions liaised
  FDIS passed 17/2/16 on 18 Dec 2013
    Voting results in N15830
    China NB & Switzerland NB voted “no” and commented
  FDIS comment responses were approved by 802.1 WG in March 2014, and liaised to SC 6 in May 2014 as N15947
  Standard was published as ISO/IEC/IEEE 8802-1AR:2014 on 15 March 2014

## Slide 116: IEEE 802.1AS-2011 has been published
60-day pre-ballot: passed & comment resolutions liaised
  Submission of IEEE 802.1AS-2011 in N15590 in March 2013
  Pre-ballot passed in May 2013
    Voting results in N15628
    Comments from China replied to in N15659
FDIS ballot: passed & comment resolutions liaised
  FDIS passed 18/1/16 on 18 Dec 2013
    Voting results in N15831
    China NB voted “no” and China NB & Switzerland NB commented
  FDIS comment responses were approved by 802.1 WG in March 2014, and liaised to SC 6 in May 2014 as N15948
  Standard was published as ISO/IEC/IEEE 8802-1AS:2014 on 15 March 2014

## Slide 117: IEEE 802.1BA-2011 has been published
Drafts sent to SC 6: sent
  IEEE 802.1BA-2011 was liaised (N16149) to SC 6 on 7 April 2015
60-day pre-ballot: passed & comment responses liaised
  The 60 ballot passed on 23 Sept 2015
    Support need for ISO standard? Passed 10/0/9
    Support this submission being sent to FDIS? Passed 8/0/11
    Only two substantive comments that needed a response
  A response was sent in Jan 2016
FDIS ballot: passed
  Ballot passed on 17 Aug 2016 (see N16461)
    Passed 14/0/18, with no comments
  Published as <what>

## Slide 118: IEEE 802.1BR-2012 has been published
Drafts sent to SC 6: sent
  IEEE 802.1BR-2012 was liaised to SC 6 on 7 April 2015
60-day pre-ballot: passed & comment responses liaised
  The 60 ballot passed on 23 Sept 2015
    Support need for ISO standard? Passed 10/0/9
    Support this submission being sent to FDIS? Passed 9/0/10
    Only one substantive comment that needed a response
  A response was sent in Jan 16
FDIS ballot: passed
  Ballot passed on 17 Aug 2016 (see N16462)
    Passed 14/0/18, with no comments
  Published as <what>

## Slide 119: IEEE 802.3-2012 has been published
60-day pre-ballot: passed & comment resolutions liaised
  Pre-ballot on N15595 passed in May 2013
    Voting results in N15632
    Comments from China were responded to by the 802.3 Maintenance TF in Geneva in N15724
FDIS ballot: passed & no comment resolutions required
  FDIS passed 16/0/20 on 16 Feb 2014
    Voting results in N15893
  No FDIS comments need to be resolved 
  Standard was published as ISO/IEC/IEEE 8802-3:2014

## Slide 120: IEEE 802.11ae-2012 has been published
60-day pre-ballot: passed & comment resolutions liaised
  Pre-ballot on N15552 passed in Feb 2013
    Voting results in N15599
    Comments from China replied to by IEEE 802 in N15647
    Comments from Japan in N15664 were resolved in discussions with commenter
FDIS ballot: passed & comment resolutions liaised
  FDIS passed 14/1/20 on 28 Jan 2014
    Voting results in N15883
    China NB voted “no” and commented they will not recognise result
  FDIS comment responses were approved by 802 in July 2014
    See 11-14-0552-00
  Standard was published as 8802-11:2012/Amd 1:2014

## Slide 121: IEEE 802.11aa-2012 has been published
60-day pre-ballot: passed & comment resolutions liaised
  Pre-ballot on N15554 passed in Feb 2013
    Voting results in N15602
    Comments from China replied to by IEEE 802 in N15647
    Comments from Japan in N15664 were resolved in discussions with commenter
FDIS ballot: passed & comment resolutions liaised
  FDIS passed 16/1/18 on 28 Jan 2014
    Voting results in N15884
    China NB voted “no” and commented they will not recognise result
  FDIS comment responses were approved by 802 in July 2014
    See 11-14-0552-00
  Standard was published as 8802-11:2012/Amd 2: 2014

## Slide 122: IEEE 802.11ad-2012 has been published
60-day pre-ballot: passed & comment resolutions liaised
  Pre-ballot on N15553 passed in Feb 2013
    Voting results in N15601
    Comments from China replied to by IEEE 802 in N15647
    Comments from Japan in N15664 were resolved in discussions with commenter
FDIS ballot: passed & comment resolutions liaised
  FDIS passed 16/1/17 on 28 Jan 2014
    Voting results in N15885
    China NB voted “no” and commented they will not recognise result
    Switzerland commented on editorial matters similar to comments on 802.1X/AE
  FDIS comment responses were approved by 802 in July 2014
    See 11-14-0552-00
  Standard was published as 8802-11:2012/Amd 3: 2014

## Slide 123: IEEE 802.22 has been published
60-day pre-ballot: passed & comment resolutions liaised
  Pre-ballot on 802.22 (N15925) passed in May 2014
    Voting results in N15954
    Passed 8/1/10
  FDIS comment responses were approved by 802.22 WG in July 2014, and were liaised to SC 6 as N16001
FDIS ballot: passed 15 Feb 2015 with no comments
  IEEE staff will facilitate the final process steps to make it an ISO/IEC/IEEE standard
  Was published on 1 May 2015 as ISO/IEC 8802-22:2015

## Slide 124: IEEE 802.1AEbn-2011 has been published
60-day pre-ballot: passed & comment resolutions liaised
  Pre-ballot on IEEE 802.1AEbn-2011 (N15809) passed in Jan 2014
    Voting results in N15857
    Passed 9/1/7
    Usual comment from China saying they will not recognise the result
  Pre-ballot comment responses were approved by 802.1 WG in March 2014, and were liaised to SC 6 as N15945
FDIS ballot: passed on 1 Feb 2015 & comment resolutions liaised
  FDIS closed on 1 Feb 2015, with one comment (N16123) from China NB
    Passed 12/1/23
    Response was liaised in April 2015 (see N16187)
  Standard is called ISO/IEC/IEEE 8802-1AE:2015/Amd 1 and was published on 28 April 2015

## Slide 125: IEEE 802.1AEbw-2013 has been published
60-day pre-ballot: passed & comment resolutions liaised
  Pre-ballot on IEEE 802.1AEbw-2013 (N15810) passed in Jan 2014
    Voting results in N15858
    Passed 9/1/7
    Usual comment from China saying they will not recognise the result
  Pre-ballot comment responses were approved by 802.1 WG in March 2014, and were liaised to SC 6 as N15946
FDIS ballot: passed on 1 Feb 2015 & comment resolutions liaised
  FDIS closed on 1 Feb 2015, with one comment (N16124) from China NB
    Passed 12/1/23
    Response was liaised in April 2015 (see N16187)
  Standard will be called ISO/IEC/IEEE 8802-1AE:2015/Amd 2 and was published on 28 April 2015

## Slide 126: IEEE 802.3.1-2013 has been published
60-day pre-ballot: passed & comment resolutions liaised
  The request to submit IEEE 802.3.1-2013 for approval under the PSDO was liaised in August 2014
  The pre-ballot closed on 6 Oct 2014, and passed 11/0/5 & 10/1/5 (N16047)
    Resolutions of “No” comment from China NB was liaised to SC 6 as N16086 in Nov 2014
FDIS ballot: passed with no comments
  FDIS passed on 19 June 2015 with 100% approval and no comments
  IEEE 802.3.1-2013 has been published as “Standard for Management Information Base (MIB) — Definitions for Ethernet — Part 3-1”

## Slide 127: IEEE 802.11ac-2013 has been published
60-day pre-ballot: passed & comment resolutions liaised
  The request to submit IEEE 802.11ac-2013 for approval under the PSDO was liaised in July 2014
  60-day pre-ballot closed on 22 Sept 2014 and passed 11/1/4
    Resolutions of “No” comments from China NB were liaised to SC 6 as N16085 in Nov 2014
FDIS ballot: passed & comment resolutions liaised
  FDIS closed on 11 July 2015 and passed 15/1/0
    Resolutions of “No” comments from China NB were liaised as 11-15-0958r1 in July 2015
  IEEE 802.11ac-2013 has been ratified as 8802-11:2012/Amd 4:2015

## Slide 128: IEEE 802.11af-2013 has been published
60-day pre-ballot: passed & comment resolutions liaised
  The request to submit IEEE 802.11af-2013 for approval under the PSDO was liaised in July 2014
  The 60-day pre-ballot closed on 22 Sept 2014, and passed 11/1/4
    Resolutions of “No” comments from China NB were liaised to SC 6 as N16085 (see previous page) in Nov 2014
FDIS ballot: passed & comment resolutions liaised
  FDIS closed on 11 July 2015 and passed 15/1/0
    Resolutions of “No” comments from China NB were liaised as 11-15-0958r1 in July 2015
  IEEE 802.11af-2013 has been ratified as 8802-11:2012/Amd 5:2015

## Slide 129: IEEE 802.1AX-2014 has been published
60-day pre-ballot: passed & no comment responses required
  IEEE 802.1AX-2014 was liaised (N16142) to SC 6 on 30 March 2015 for adoption under the PSDO process
  The 60-day pre-ballot ballot closed on 30 May 2015
  It passed with 100% approval and no comments
FDIS ballot: passed & no comment responses required
  FDIS ballot closed on 20 Nov 2015
  It passed with 100% approval and no comments
  It will be known as 8802-1AX:2015

## Slide 130: IEEE 802-2014 has been published
60-day pre-ballot: passed & comment responses liaised
  The submission of IEEE 802-2014 under the PSDO was approved by 802 EC in July 2014, and the 60-day pre-ballot passed on 26 Oct 014
  Comment responses approved by 802 EC on 16 Feb 2015
    See N6133
FDIS ballot: passed and response liaised in Jan 16
  FDIS ballot passed 2 Nov 2015
    Passed 14/1/19, with negative comment from China NB
  A response was discussed in Nov 2015 but it was decided that the 802.1 WG would take responsibility for sending
    Sent in Jan 2016
  The final standard will be known as ISO/IEC/IEEE 8802-A:2015

## Slide 131: IEEE 802.1Xbx-2014 has been published
Drafts sent to SC 6: sent
  D1.0, D1.2 (May 14), with submission to PSDO approved in July 2014
60-day pre-ballot: passed & comment responses liaised
  Passed on 19 Mar 2015 with a China NB comment
    Passed 9/1/9 on need for an ISO standard – China NB voted no
    Passed 8/1/10 on submission to FDIS – China NB voted no
  802.1 WG responded to comments in June 2015 (see N16255)
FDIS ballot: passed & comment responses liaised
  Passed on 24 Dec 2015 with a China comment
    Passed 15/1/18 – China NB voted no, with comments (see 6N16364)
  802.1 WG responded to the comment on 21 Apr 2016 (see N16424)
  The standard will be known as ISO/IEC/IEEE 8802-1X:2014/Amd1
    It has been published as of June 2016

## Slide 132: IEEE 802.1Q-Rev-2014 has been published
Drafts sent to SC 6: sent
  D2.0 (Jan 14)
60-day pre-ballot: passed & comment responses liaised
  Passed on 23 Mar 2015 with a China NB comment
    Passed 11/1/16 – China NB voted no (see N16135)
  802.1 WG responded to comments in June 2015 (see N16255)
FDIS ballot: passed & comment responses liaised
  Passed on 28 Jan 2016 with China NB comments
    Passed 15/1/20 - China NB voted no and commented (see N16377)
  802.1 WG responded to the comment on 21 Apr 2016 (see N16425)
  The standard will be known as ISO/IEC/IEEE 8802-1Q:2015
    It has been published as of June 2016

## Slide 133: IEEE 802-3-2015 has been published
Drafts sent to SC 6: sent
  Liaised to SC 6 in Apr 2015
60-day pre-ballot: passed & responses liaised
  Passed, with two comments from China NB (N16448)
    8/1/9 on need for ISO standard
    8/1/9 on support for submission to FDIS
  Responses were liaised in Jul 2016 (see N16458)
FDIS ballot: passed, responses sent and published
  Passed by16/1/20, with two comments from China NB (N16570)
  Response was sent in March 2017 (N16591)
  It has been published as of April 2017 as <what>

## Slide 134: IEEE 802.1Qbv-2015 has been published
Drafts sent to SC 6: sent
  802.1Qbv D3.0 was liaised for information in Nov 2015
60-day pre-ballot: passed & response liaised
  802.1Qbv passed 60 pre-ballot on 30 May 2016 (see N16412)
    Support need for ISO standard? Passed 6/1/11
    Support this submission being sent to FDIS? Passed 6/1/11
  China NB voted “no” with one comment
    Response was liaised in Oct 2016 (see N16486)
FDIS ballot: passed & response liaised
  802.1Qbv passed (15/1/17) FDIS ballot on 18 April 2017 (N16613)
  Passed China NB voted “no” with one comment
    Response (N16687) was liaised in July 2017
  Published in July 2017 as <what>

## Slide 135: IEEE 802.1AB-2016 has been published
Drafts sent to SC 6: sent
  802.1AB D1.2 was liaised for information in Dec 2015
60-day pre-ballot: passed & response liaised
  802.1QAB-2016 passed 60-day pre-ballot on 13 July 2016 (N16447)
    Passed 8/1/9 on need for ISO standard
    Passed 8/1/9 on support for submission to FDIS
  China NB voted “no” with one comment
    A response was approved in July 2016 & liaised in Oct 2016 (N16487)
FDIS ballot: passed & response liaised
  802.1QAB-2016 passed FDIS ballot (14/1/20) on 11 April 2017 (N16604)
  Passed China NB voted “no” vote with one comment
    Response (N16687) was liaised in July 2017
  Published in July 2017 as <what>

## Slide 136: IEEE 802.1Qca-2015 has been published
Drafts sent to SC 6: sent
  802.1Qca D2.1 was liaised for information in Nov 2015
60-day pre-ballot: passed & response liaised
  802.1Qca-2015 passed 60-day pre-ballot on 13 July 2016 (N16446)
    Passed 8/1/9 on need for ISO standard
    Passed 8/1/9 on support for submission to FDIS
  China NB voted “no” with one comment
    A response was approved in July 2016 and liaised in Oct 2016 (see N16485)
FDIS ballot: passed & response liaised
  802.1Qca-2015 passed FDIS ballot (15/1/17) on 18 April 2017 (N16612)
  China NB voted “no” with one comment
    Response (N16687) was liaised in July 2017
  Published in July 2017 as <what>

## Slide 137: IEEE 802.22a has been published
Drafts sent to SC 6: sent
  IEEE 802.22a was liaised in July 2015 to SC 6 to allow them to become familiar with it before submission for approval under the PSDO process
60-day pre-ballot: passed & response sent
  IEEE 802.22a was submitted for 60-day ballot in December 2015, and after a delay the ballot passed on 3 April 2016 (N16414)
    Support need for ISO standard? Passed 10/0/8
    Support this submission being sent to FDIS? 9/1/8
  The only comment was a security related comment from the China NB
    802.22 WG response was sent in Nov 2016
FDIS ballot: passed & published
  Passed on 27 July 2017 (12/0/17) with no comments (N16686)
  Final standard was published in Oct 2017 as <what>

## Slide 138: IEEE 8802.1Qbu has been published
Drafts sent to SC 6: sent
  802.1Qbu D3.0 was liaised for information in Nov 2015
60-day pre-ballot: passed & response liaised
  802.1Qbu-2016 passed its 60-day ballot on 7 Feb 2017 (N16541)
    Passed 9/0/11 on need for ISO standard
    Passed 7/1/12 on support for submission to FDIS
  China NB voted “no” with one comment
    Response sent to China NB comments (N16601)
FDIS ballot: passed & published
  802.1Qbu-2016 passed its FDIS ballot on 11 Oct 2017(N16721?)
    Passed 11/0/10
  Published in Nov 2017 as <what>

## Slide 139: IEEE 8802.1Qbz has been published
Drafts sent to SC 6: sent
  IEEE 802.1Qbz D3.0 was liaised for information in Dec 2015
60-day pre-ballot: passed & response liaised
  IEEE 802.1Qbz-2016 passed its 60-day ballot on 7 Feb 2017 (N16540)
    Passed 9/0/11 on need for ISO standard
    Passed 7/1/12 on support for submission to FDIS
  China NB voted “no” with one comment
    Response sent in March 2017 to China NB comments (N16601)
FDIS ballot: passed & published
  802.1Qbz-2016 passed its FDIS ballot on 11 Oct (N16722?)
    Passed 11/0/10
  Published in Nov 2017 as <what>

## Slide 140: IEEE 802.1Qcd-2015 has been published
Drafts sent to SC 6: sent
  802.1Qcd-2015 was liaised for information on 26 May 2015
60-day pre-ballot: passed & response sent
  802.1Qcd-2015 passed 60-day pre-ballot on 23 Oct 2016 (N16496)
    Passed 8/0/10 on need for ISO standard
    Passed 6/1/11 on support for submission to FDIS
  China NB voted “no” with one comment
    The response was sent in Nov 2016 (N16505)
FDIS ballot: passed & published
  802.1Qcd-2015 passed its FDIS ballot on 1 Dec 2017 (N??????)
    Passed 14/0/13
  Published in Jan 2018 as <what>

## Slide 141: IEEE 802.1Q-2014/Cor 1-2015 has been published
90-day FDIS ballot: passed & published
  802.1Q-2014/Cor 1-2015 was submitted to PSDO using a special process for corrigenda
  The ballot passed on 16 March 2017 (N16589)
    Do you support the need for a corrigendum to the subject ISO/IEC/IEEE International Standard? 9/0/11
    Do you approve the draft for publication? 8/1/11
  China NB voted “no” with an objection to the use of IEEE 802.1X based security
    Response (N16687) was liaised in July 2017
  Published in Oct 2017 as <what>

## Slide 142: IEEE 8802.3bw has been published
Drafts sent to SC 6: sent
  802.3bw was liaised to SC 6 in Nov 2015 to allow them to become familiar with it before submission for approval under the PSDO process
60-day pre-ballot: passed & response liaised
  802.3bw passed 60-day ballot on 19 Sep 2016 (see N16478)
    Support need for IS: passed 7/1/10 (China NB voted no)
    Support submission for this IS: passed 6/1/11 (China NB voted no)
  China NB voted “no” with comments
    Response sent to SC 6 in Dec 2016 (see N16509)
FDIS ballot: passed & published
  Passed on 11 Sep 2017 by 15/0/13 (N16712)
    China NB voted “yes” with one comment
    Response sent on 14 Nov 2017 (N16744)
  Published in Oct 2017 as <what>

## Slide 143: IEEE 8802.3bp has been published
Drafts sent to SC 6: sent
  D3.0 was liaised to SC 6 in Feb 2016 to allow them to become familiar with it before submission for approval under the PSDO process
60-day pre-ballot: passed with comments resolved
  Passed on 11 Jan 2017 (N16537)
    Support need for IS: passed 9/0/10
    Support submission for this IS: passed 7/1/11
  China NB voted “no” with two comments
    IEEE 802.3 sent a response in March 2017 (N16590)
FDIS ballot: passed & published
  802.3bp passed FDIS ballot on 18 Oct 2017
    Passed 12/0/8
  Published in Nov 2017 as <what>

## Slide 144: IEEE 8802.3bq has been published
Drafts sent to SC 6: sent
  802.3bq D3.0 was liaised to SC 6 in Feb 2016 to allow them to become familiar with it before submission for approval under the PSDO process
60-day pre-ballot: passed with comments resolved
  802.3bq passed 60-day pre-ballot on 11 Jan 2017 (N16536)
    Support need for IS: passed 9/0/10
    Support submission for this IS: passed 7/1/11
  China NB voted “no” with two comments
    IEEE 802.3 sent a response in March 2017 (see 802.3bp response)
FDIS ballot: passed & published
  802.3bq passed FDIS ballot on 18 Oct 2017
    Passed 12/0/8
  Published in Nov 2017 as <what>

## Slide 145: IEEE 8802.3br has been published
Drafts sent to SC 6: sent
  802.3br D3.0 was liaised to SC 6 in Feb 2016 to allow them to become familiar with it before submission for approval under the PSDO process
60-day pre-ballot: passed with comments resolved
  802.3br passed 60-day pre-ballot on 16 Feb 2017 (N16568)
    Support need for IS: passed 11/0/9
    Support submission for this IS: passed 10/1/9
  China NB voted “no” with one comment
    IEEE 802.3 sent a response in March 2017 (see IEEE 802.3bp response)
FDIS ballot: passed & published
  802.3br passed FDIS ballot on 11 Oct 2017 (N16723?)
    Passed 11/0/10
  Published in Nov 2017 as <what>

## Slide 146: IEEE 8802.3by has been published
Drafts sent to SC 6: sent
  802.3by D3.0 was liaised to SC 6 in Feb 2016 to allow them to become familiar with it before submission for approval under the PSDO process
60-day pre-ballot: passed with comments resolved
  802.3by passed 60-day pre-ballot on 11 Jan 2017 (N16535)
    Support need for IS: passed 9/0/10
    Support submission for this IS: passed 7/1/11
  China NB voted “no” with two comments
    IEEE 802.3 sent a response in March 2017 (see IEEE 802.3bp response)
FDIS ballot: passed & published
  802.3by passed FDIS ballot on 18 Oct 2017
    Passed 12/0/8
  Published in Nov 2017 as <what>

## Slide 147: IEEE 8802.3bz has been published
Drafts sent to SC 6: sent
  802.3bz was liaised in June 2016 (when in SB)
60-day pre-ballot: passed with comments resolved
  Passed on 16 Feb 2017 (N16567)
    Support need for IS: passed 11/0/9
    Support submission for this IS: passed 10/1/9
  China NB voted “no” with two comments
    IEEE 802.3 sent a response in March 2017 (see IEEE 802.3bp response)
FDIS ballot: passed & published
  802.3bz passed FDIS pre-ballot on 11 Oct 2017 (N16724)
    Passed 11/0/10
  Published in Nov 2017 as <what>

## Slide 148: ISO/IEC/IEEE 802.15.3 has been published
Drafts sent to SC 6: sent
  802.15.3-revA D2.0 was liaised in Dec 2015 for information
60-day pre-ballot: passed & response sent
  IEEE 802.15.3-2016 passed 60-day pre-ballot on 23 Oct 2016 (N16495)
    Passed 8/0/10 on need for ISO standard
    Passed 7/0/11 on support for submission to FDIS
    China NB voted yes with one comment
  Response was approved by 802 EC in Nov 2016 and sent in Feb 2017
    See 15-16-0768-01
FDIS ballot: passed & published
  Passed on 7 Sep 2017 by 14/0/14 (N16710)
  Published in Oct 2017 as <what>

## Slide 149: IEEE 802.15.4-2015 has been published
Drafts sent to SC 6: sent
  IEEE 802.15.4-2006 was adopted by ISO under JTC 1/SC 31 but JTC1/SC 6 has responsibility as of June 2015 for IEEE 802.15 standards
  IEEE 802.15.4-2015 submission to the PSDO was approved in March 2016 but nothing much happened
  IEEE 802.15.4-2015 was sent for information in Dec 2016
60-day pre-ballot: passed
  IEEE 802.15.4-2015 60-day pre-ballot closed on 20 April 2017 (N16615)
    Passed 8/0/11 on need for ISO standard
    Passed 8/0/11 on support for submission to FDIS
    No comments
FDIS ballot: passed & published
  Passed on 27 Jan 2018 by 12/0/10, with no comments (N16763)
  ISO/IEC/IEEE 8802-15-4:2018 was published in Mar 2018

## Slide 150: IEEE 802.21-2017 has been published
Drafts sent to SC 6: sent
  IEEE 802.21-2017 was approved for liaison for information in July 2016
    D7 was sent in Nov 2016
60-day pre-ballot: passed & response sent
  IEEE 802.21-2017 60-day pre-ballot closed on 10 April 2017 (N16671)
    Passed 6/1/14 on need for ISO standard
    Passed 6/1/14 on support for submission to FDIS
    Only negative vote was from China NB (the usual security comment)
  A response was sent on 20 July 2017
    See 21-17-0036-00 (N16682)
FDIS ballot: passed, response sent & published
  IEEE 802.21-2017 FDIS passed (N16768)
    Passed 12/1/6 (with comments from China NB)
  A response was sent in Mar 2018 (N16770)
  ISO/IEC/IEEE 8802-21:2018 published in Apr 2018

## Slide 151: IEEE 802.22b has been published
Drafts sent to SC 6: sent
  IEEE 802.22b was liaised in July 2015 to SC 6 to allow them to become familiar with it before submission for approval under the PSDO process
60-day pre-ballot: passed on 3 April 2016 and response sent
  IEEE 802.22b was submitted for 60-day ballot in December 2015, and after a delay the ballot passed on 3 April 2016 (N16415)
    Support need for ISO standard? Passed 9/1/8
    Support this submission being sent to FDIS? 8/2/8
  China NB & Japan NB voted “no”
    802.22 WG response was sent in Nov 2016
FDIS ballot: passed 27 July 2017 & published (& response sent later)
  Passed on 27 July 2017 by 12/1/16 (N16690)
    China NB voted “no” with two comments
  ISO/IEC/IEEE 8802-22:2015/Amd 2:2017 was published in Oct 2017
  Response to comments were sent in Mar 2018 (N16771)

## Slide 152: IEEE 802.1AC-Rev has been published
Drafts sent to SC 6: sent
  802.1AC-Rev D3.0 was liaised for information in Dec 2015
60-day pre-ballot: passed & response liaised
  802.1AC-Rev 60-day ballot passed on 24 May 2017 (N16647)
    Passed 11/0/8 on need for ISO standard
    Passed 10/1/9 on support for submission to FDIS
  China NB voted “no” with one comment
    Response (N16687) was liaised in July 2017
FDIS ballot: passed, response liaised & published
  802.1AC-Rev passed its FDIS ballot on 7 Mar 2018 (N16769)
    Passed 11/1/6
  China NB voted “no” with one comment
    A response was sent in Apr 2018 (N16795)
  Published as ISO/IEC/IEEE 8802-1AC:2018

## Slide 153: IEEE 802d has been published
Drafts sent to SC 6: sent
  IEEE 802d D1.0 (Overview and Architecture—Amendment: Allocation of Uniform Resource Name (URN) values in IEEE 802 standards) was liaised for information in Oct 2016 (see N16484)
60-day pre-ballot: passed
  802d passed 60-day pre-ballot on 15 June 2017 (N16657)
    Passed 9/0/11 on need for ISO standard
    Passed 9/0/11 on support for submission to FDIS
FDIS ballot: passed, and published
  802d passed FDIS ballot on 14 Mar 2018 (N16779/N16783)
    Passed 12/0/7
  Published as ISO/IEC/IEEE 8802-A:2015/AMD1:2018

## Slide 154: IEEE 802.11mc has been published
Drafts sent to SC 6: sent
  802.11mc drafts were liaised for information
    D5.0 in Jan 2016, D6.0 in Jul 2016 & D8.0 in Oct 2016
60-day pre-ballot: passed & responses liaised
  802.11-2016 passed 60-day pre-ballot (N16607) on 16 April 2017
    Need? 10/0/10
    Submission? 9/1/10
  China voted no with usual comment, for which a response was approved – see 11-17-0629-01 – was sent on 10 June (N16655)
FDIS ballot: passed, response sent & published
  802.11-2016 passed its FDIS ballot on 13 Apr 2018 (N16794)
    Passed 12/1/6 (with comments by China NB)
  A response has been sent (N16812)
  Published as ISO/IEC/IEEE 8802-11:2018

## Slide 155: IEEE 802.21.1 has been published
Drafts sent to SC 6: sent
  IEEE 802.21.1 was approved for liaison for information in July 2016
    D5 was sent in Nov 2016
60-day pre-ballot: passed
  IEEE 802.21.1 60-day pre-ballot passed on 10 April 2017 (N16672)
    Passed 6/0/14 on need for ISO standard
    Passed 6/0/14 on support for submission to FDIS
  China NB voted “no” with comments
    A response was sent on 20 July 2017 (N16682)
FDIS ballot: passed, response sent & published
  IEEE 802.21.1 FDIS ballot passed on 14 Mar 2018 (N16780, N16784)
    Passed 11/1/7 (with comment from China NB)
  A response has been sent (N16811) and waiting for publication
  Published as ISO/IEC/IEEE 8802-21-1:2018

## Slide 156: IEEE 802.1AX-2014/Cor1 has been published
90-day FDIS ballot: passed & published
  802.1AX-2014/Cor1 passed 90-day FDIS on 20 July 2018 (N16684)
    Passed 10/0/10
    There were no comments
  It has been published as ISO/IEC 8802-1AX:2016/Cor 1:2018

## Slide 157: IEEE 802.3/Cor 1 has been published
Drafts sent to SC 6: sent
  802.3/Cor 1 D2.1 was liaised in Feb 2017
90-day FDIS: passed & published
  Passed on 22 Nov 2017 (N16782)
    Support need for IS: passed 8/0/14
    Support this IS: passed 8/0/14
    No comments
  It has been published as ISO/IEC/IEEE8802-3:2017/Cor 1:2018

## Slide 158: IEEE 802.21-2017-Cor1 90-day FDIS ballot passed and response sent
Drafts sent to SC 6: sent
  Currently likely to be approved by RevCom in December
  P802.21-2017/Cor 1™/D02 was sent in Nov 2017
90-day FDIS ballot: passed and response sent
  IEEE 802.21-2017-Cor1 90-day FDIS ballot passed on 16 June 2018 (N16814)
    Passed 5/0/12
    Abstain comment from China NB
  Response was sent after July 2018 meeting (N16816)
  It has now been published as ISO/IEC/IEEE 8802-21:2018/Cor-1:2018

## Slide 159: IEEE 802.3bn is published
Drafts sent to SC 6: sent
  802.3bn D3.0 was liaised to SC 6 in Feb 2016 to allow them to become familiar with it before submission for approval under the PSDO process
60-day pre-ballot: passed and response sent
  802.3bn-2016 passed 60-day pre-ballot on 16 Apr 2017 (N16546)
    Need? 8/1/10
    Submission? 8/1/10
  China NB voted “no” and provided the usual comments
    A response was sent to SC 6 on 7 June 2017 (6N16649)
FDIS ballot: passed & published
  FDIS ballot passed 11/0/7 on 3 September 2018 (N16853)
  Published as ISO/IEC/IEEE 8802-3:2017/Amd 6

## Slide 160: IEEE 802.3bv is published
Drafts sent to SC 6: sent
  802.3bv D3.1 was liaised to SC 6 in Oct 2016
60-day pre-ballot: passed
  Note: another ISO group is developing a standard to complement IEEE Std 802.3bv-2017 (ISO TC22 SC32) and may be interested in ensuring it is approved in SC 6
  802.3bv passed 60-day pre-ballot on 18 August 2017 (N16694)
    Support need for IS: passed 8/0/13
    Support submission for this IS: passed 8/0/13
FDIS ballot: passed & published
  FDIS ballot passed 11/0/7 on 3 September 2018 (N16851)
  Published as ISO/IEC/IEEE 8802-3:2017/Amd 9

## Slide 161: IEEE 802.3bu is published
Drafts sent to SC 6: sent
  802.3bu D3.2 was liaised to SC 6 in Oct 2016
60-day pre-ballot: passed
  802.3bu passed 60-day pre-ballot on 18 August 2017 (N16693)
    Support need for IS: passed 8/0/13
    Support submission for this IS: passed 8/0/13
FDIS ballot: passed & published
  FDIS ballot passed 11/0/7 on 3 September 2018 (N16852)
  Published as ISO/IEC/IEEE 8802-3:2017/Amd 8

## Slide 162: IEEE 802.1AEcg has ratified as a ISO/IEC/IEEE standard
Drafts sent to SC 6: sent
  802.1AEcg D1.4 was liaised for information in Oct 2016 (N16484)
60-day pre-ballot: passed & response sent
  802.1AEcg passed 60-day pre-ballot on 7 Sept 2017 (N16707)
    Passed 6/1/12 on need for ISO standard
    Passed 5/1/13 on support for submission to FDIS
  China NB voted “no” with one comment
    The response was sent in Dec 2017 (N16753)
FDIS ballot: passed, response sent & published
  802.1AEcg passed FDIS ballot on 28 Aug 2018 (N??????)
    Passed 10/1/11, with China NB voting no
  Comment responses were sent in Jan 2019 (N16913)
  Published as ISO/IEC/IEEE 8802-1AE:2013/Amd 3:2018

## Slide 163: IEEE 802.16-2017 passed 60-day pre-ballot with comments but the PSDO process was cancelled
Drafts sent to SC 6: sent
  IEEE 802.16-2017 was sent for information in Mar 2018 (N16785)
60-day pre-ballot: passed but response required
  The 60-day (N16810) ballot passed (N16821) on 30 July 2018
    Need for IS on topic: 7/0/11
    Submission of this proposal as IS: 5/1/12, with “no” (with comments) from China
FDIS ballot: cancelled
  The EC approved cancelling the PSDO process in Nov 2018, and the following was sent to SC 6
    IEEE 802 thanks JTC 1/SC 6 for considering the adoption of IEEE 802.16-2017 under the ISO/IEEE PSDO Agreement. We further appreciate the comments received. At this time, IEEE would like to withdraw this document from the PSDO process and refer the comments received to the IEEE 802.16 Working Group for further consideration.

## Slide 164: IEEE 802.1CB has been published as ISO/IEC/IEEE 8802-1CB:2019
Drafts sent to SC 6: sent
  802.1CB D2.6 was submitted in Sep 2016
60-day pre-ballot: passed
  802.1CB was submitted in Nov 2017 (N16742)
  802.1CB passed 60-day pre-ballot on 18 Jan 2018 (N16761)
    Passed 9/0/13 on need for ISO standard
    Passed 8/0/14 on support for submission to FDIS
  There were no comments
FDIS ballot: passed & published
  FDIS ballot passed 10/0/9 on 26 Dec 2018 (N??????)
  Published as ISO/IEC/IEEE 8802-1CB:2019

## Slide 165: IEEE 802.1Qci has been published as ISO/IEC/IEEE 8802-1Q:2016/Amd 6:2019
Drafts sent to SC 6: sent
  802.1Qci D2.0 was submitted in Oct 2016
60-day pre-ballot: passed & response sent
  802.1Qci (6N16715) passed 60-day pre-ballot on 9 Dec 2017 (6N16760)
    Passed 8/0/13 on need for ISO standard
    Passed 6/1/14 on support for submission to FDIS
  China NB voted “no” with one comment
    A response was sent in Apr 2018 (N16796)
FDIS ballot: passed & published
  FDIS ballot passed 9/0/10 on 3 Jan 2019 (N??????)
  Published as ISO/IEC/IEEE 8802-1Q/Amd 6

## Slide 166: IEEE 802.1Qch has been published as ISO/IEC/IEEE 8802-1Q:2016/Amd 7:2019
Drafts sent to SC 6: sent
  802.1Qch D2.0 was submitted in Nov 2016
60-day pre-ballot: passed
  802.1Qch was submitted in Nov 2017 (N16743)
  802.1Qch passed 60-day pre-ballot on 18 Jan 2018 (N16762)
    Passed 9/0/13 on need for ISO standard
    Passed 7/0/15 on support for submission to FDIS
  No comments were received
FDIS ballot: passed & published
  FDIS ballot passed 9/0/10 on 3 Jan 2019 (N??????)
  Published as ISO/IEC/IEEE 8802-1Q:2016/Amd 7:2019

## Slide 167: IEEE 802.3bs has been published as ISO/IEC/IEEE 8802-3:2017/Amd 10:2019
Drafts sent to SC 6: sent
  802.3bs D3.0 was liaised in Feb 2017
60-day pre-ballot: passed
  Passed on 12 Apr 218 (N16792)
    Support need for IS: passed 11/0/8
    Support this IS: passed 11/0/8
    No comments
FDIS ballot: passed & published
  FDIS ballot passed 9/0/10 on 26 Dec 2018 (N??????)
  Published as ISO/IEC/IEEE 8802-3:2017/Amd 10:2019

## Slide 168: IEEE 802.3cc has been published as ISO/IEC/IEEE 8802-3:2017/Amd 11:2019
Drafts sent to SC 6: sent
  IEEE 802.3cc D3.0 was liaised in June 2016 (when in SB)
60-day pre-ballot: passed
  Passed on 12 Apr 218 (N16793)
    Support need for IS: passed 11/0/8
    Support this IS: passed 11/0/8
    No comments
FDIS ballot: passed & published
  FDIS ballot passed 9/0/10 on 26 Dec 2018 (N??????)
  Published as ISO/IEC/IEEE 8802-3:2017/Amd 11:2019

## Slide 169: IEEE 802.11ai has been published as ISO/IEC/IEEE 8802-11:2018/Amd 1:2019
Drafts sent to SC 6: sent
  802.11ai drafts were liaised for information
    D6.0 in Oct 2015, D8.0 in Jul 2016, D9.0 in Sep 2016
60-day pre-ballot: passed
  802.11ai-2016 passed 60-day pre-ballot (N16608) on 16 April 2017
    Need? 9/1/10
    Submission? 9/1/10
  China voted “no” with the usual security related comments, to which responses were developed
    See 11-17-612-02 – was sent on 10 June 2017 (N16656)
  …

## Slide 170: IEEE 802.11ai has been published as ISO/IEC/IEEE 8802-11:2018/Amd 1:2019
  …
  Unfortunately, errors in the publication process required a re-run of the 60-day pre-ballot, which passed on 1 Sept 2017 (N16697)
    Need? 9/1/11
    Submission? 9/1/11
  China voted “no” with the usual security related comment
    Response (11-17/1398r0) has been approved was sent in Oct 2017 (N16725)
FDIS ballot: passed & published
  FDIS ballot passed 9/1/9 on 26 Dec 2018 (N16982)
    China voted no
  A response was sent in Feb 2019 (N16888) – see 11-19-0062-01
  Published as ISO/IEC/IEEE 8802-11:2018/Amd 1

## Slide 171: IEEE 802c has been published as ISO/IEC/IEEE 8802-A:2015/Amd 2:2019
Drafts sent to SC 6: sent
  802c/D2.1 was liaised for information in Mar 2017 (N16598)
60-day pre-ballot: passed and response sent
  802c 60-day ballot passed on 2 Feb 2018 (N16765)
    Passed 10/0/12 on need for ISO standard
    Passed 9/0/13 on support for submission to FDIS
  China NB and US NB provided comments
    A response was sent in Apr 2018 (N16797)
FDIS ballot: passed & published and response sent
  FDIS ballot passed 9/1/9 on 26 Dec 2018 (N??????)
  China NB voted “no” & provided comments
    A response was sent in Apr 2019 (N16944)
  Published as ISO/IEC/IEEE 8802-A:2015/Amd 2:2019

## Slide 172: IEEE 802.11ah has been published as ISO/IEC/IEEE 8802-11:2018/Amd 2
Drafts sent to SC 6: sent
  802.11ah drafts were liaised for information
    D5.0 in Oct 2015
    D9.0 in Sep 2016
60-day pre-ballot: passed
  802.11ah passed 60-day pre-ballot (N16685) on 20 July 2017
    Need? 10/0/10
    Submission? 9/0/11
FDIS ballot: passed & published
  802.11ah passed FDIS ballot (N16685) on 8 Feb 2019 (N16983)
    Passed 9/1/9
  There was a negative vote and comments from China NB
    Response sent in Mar 2019 (N16906)
  Standard published as ISO/IEC/IEEE 8802-11:2018/Amd 2

## Slide 173: IEEE 802.1CM has been published as ISO/IEC/IEEE 8802-1CM:2019
Drafts sent to SC 6: sent
  D2.2 was liaised in Apr 2018 (WG1N124)
60-day pre-ballot: passed
  802.1CM 60-day ballot passed on 14 Oct 2018 (N16859)
    Passed 7/0/11 on need for ISO standard
    Passed 5/0/13 on support for submission to FDIS
  No comments were submitted
FDIS ballot: passed & published
  802.1CM FDIS ballot passed on 27 Jun 2018
    Passed 10/10/10
    No comments
  Published as ISO/IEC/IEEE 8802-1CM:2019

## Slide 174: IEEE 802.15.6-2012 published as ISO/IEC/IEEE 8802-15-6:2017
Drafts sent to SC 6: sent
  The 802.15.6 standard was supposed to be liaised in Apr 2016 for information but was eventually liaised in late July 2016
60-day pre-ballot: passed & responses sent
  The 60-day ballot passed on 23 Nov 2016
    Need for IS on topic: 9/0/10
    Submission of this proposal as IS: 6/3/10, with “no” from Germany, Japan & UK
  Responses were sent in Feb 2017 (see 15-17-0107-02)
FDIS ballot: passed & published
  Passed on 7 Sep 17 by 12/2/14 (N16711)
    China NB and Japan NB voted “no” with comments
    Response finally sent after July 2019 meeting by e-mail but SC 6 Secretary decided not to publish because so late
  Published as ISO/IEC/IEEE 8802-15-6:2017

## Slide 175: IEEE 802.1AR-Rev is published as ISO/IEC/IEEE 8802-1AR
Drafts sent to SC 6: sent
  D2.0 was liaised in Apr 2018 (WG1N124)
60-day pre-ballot: passed & responses sent
  802.1AR-Rev 60-day ballot passed on 14 Oct 2018 (N16858)
    Passed 8/0/10 on need for ISO standard
    Passed 5/1/12 on support for submission to FDIS
  Response to China NB sent in Jan 2019 (N16912)
FDIS ballot: published
  802.1AR-Rev FDIS ballot passed on 14 Nov 2020
    Passed 10/1/7 (N07167)
    Response to China NB sent in Apr 2020 (N17167)
  Published as ISO/IEC/IEEE 8802-1AR

## Slide 176: IEEE 802.1AC/Cor-1 is published as ISO/IEC/IEEE 8802-1AC:2018/COR 1:2019
Drafts sent to SC 6: sent
  D2.0 was liaised in Apr 2018 (WG1N124)
90-day ballot: published
  802.1AC/Cor1 90-day FDIS ballot passed on 18 Mar 2019 (N16981)
    Passed 6/0/12 on need for ISO standard
    Passed 6/0/12 on approval
  IEEE 802.1AC/Cor 1 is published as ISO/IEC/IEEE 8802-1AC:2018/COR 1:2019

## Slide 177: IEEE 802.1Q-2018 has been published
Drafts sent to SC 6: sent
  802.1Q-REV/D2.0 was liaised for information in Jul 2017 (N16688)
60-day pre-ballot: passed and response sent
  802.1Q-2018 60-day ballot passed on 11 March 2019 (N16985)
    Passed 10/0/8 on need for ISO standard
    Passed 8/1/9 on support for submission to FDIS
  China voted “no” with 1 comment
    A response was sent in Apr 2019 (N16943)
FDIS ballot: passed & response sent
  802.1Q-2018 FDIS ballot passed on 4 May 2020 (N17175)
    Passed 11/1 (China NB)/7
  Response sent in Jun 2020 (N17185)
  IEEE 802.1Q-2018 has been published as ISO/IEC/IEEE 8802-1Q:2020

## Slide 178: IEEE 802.1AE-Rev has been published
Drafts sent to SC 6: sent
  IEEE 802.1AE-Rev D1.1 was liaised in Apr 2018 (WG1N124)
60-day pre-ballot: passed & response sent
  802.1AE-Rev 60-day ballot passed on 11 March 2019 (N17080)
    Passed 10/0/8 on need for ISO standard
    Passed 8/1/9 on support for submission to FDIS
  China voted “no” with 6 comments
    Response was sent in Sept 2019 (N17059)
FDIS ballot: passed & response sent
  802.1AE-Rev FDIS ballot passed on 26 June 2020 (N17207)
    Passed 9/1/8 (China NB voted “no” with 5 comments)
  Response sent in Aug 2020 (N17266)
  IEEE 802.1AE has been published as ISO/IEC/IEEE 8802-1AE:2020

## Slide 179: ISO/IEC/IEEE 8802-11:2018/AMD 3:2020 (802.11aj) has been published
Drafts sent to SC 6: sent
  802.11aj drafts were liaised for information
    D5.0 in Jun 2017
    Published version liaised in July 2018 (N16817)
60-day pre-ballot: passed & response sent
  802.11aj-2018 passed 60-day pre-ballot (N16897) on 10 Feb 2019
    Need? 7/0/12
    Submission? 6/0/13
  China NB voted “yes”/”abstain” but submitted two comments
    Response sent in July 2019 (11-19-1177-03)
FDIS ballot: passed & response sent
  802.11aj-2018 passed FDIS ballot (N17204) on 26 June 2020
    Passed 11/0/7
  China NB voted “yes” but submitted two comments
    Response in 11-20-1024r1 sent in Jul 2020 (N17241)
  Has been published as ISO/IEC/IEEE 8802-11:2018/AMD 3:2020

## Slide 180: ISO/IEC/IEEE 8802-11:2018/AMD 4:2020 (802.11ak) has been published
Drafts sent to SC 6: sent
  802.11ak drafts were liaised for information
    D4.0 in Jun 2017
    Published version liaised in July 2018 (N16817)
60-day pre-ballot: passed & response sent
  802.11ak-2018 passed 60-day pre-ballot (N16898) on 10 Feb 2019
    Need? 7/0/12
    Submission? 5/1/13
  China NB voted “no” and submitted a comment
    Response sent in March 2019 (N16907)
FDIS ballot passed & response sent
  802.11ak-2018 passed FDIS ballot (N17205) on 26 June 2020
    Passed 10/1/7
  China NB voted “no” and submitted one comment
    Response in 11-20-1025r1 sent in Jul 2020 (N17242)
  Has been published as ISO/IEC/IEEE 8802-11:2018/AMD 4:2020

## Slide 181: ISO/IEC/IEEE 8802-11:2018/AMD 5:2020 (802.11aq) has been published
Drafts sent to SC 6: sent
  Published version was liaised in Sept 2018 (N16854)
60-day pre-ballot: passed & response sent
  802.11aq-2018 passed 60-day pre-ballot (N16899) on 10 Feb 2019
    Need? 7/0/12
    Submission? 5/1/13
  China NB voted “no” and submitted a comment
    Response sent in Mar 2019 (N16908)
FDIS ballot passed & response sent
  802.11aq-2018 passed FDIS ballot (N17208) on 26 June 2020
    Passed 10/1/7
  China NB voted “no” and submitted one comment
    Response in 11-20-1026r0 sent in Jul 2020 (N17243)
  Has been published as ISO/IEC/IEEE 8802-11:2018/AMD 5:2020

## Slide 182: IEEE 802.1Xck was published as ISO/IEC/IEEE 8802-1X:2013/AMD2-2020 in Nov 2020
Drafts sent to SC 6: sent
  IEEE 802.1Xck D2.0 was liaised in Apr 2018 (WG1N124)
60-day pre-ballot: passed & response sent
  802.1Xck 60-day ballot passed on 11 March 2019 (N17081)
    Passed 10/0/8 on need for ISO standard
    Passed 8/1/9 on support for submission to FDIS
    China voted “no” with 2 comments; response was sent in Sept 2019 (N17060)
FDIS ballot: passed & response sent
  IEEE 802.1Xck FDIS ballot passed on 26 June 2020 (N17203)
    Passed 9/1/8
    China voted “no” with 1 comment; response sent in Aug 2020 (N17265)
  ISO/IEC/IEEE 8802-1X:2013/AMD2-2020 was published in Nov 2020

## Slide 183: IEEE 802.3-REV was published in Feb 2021
Drafts sent to SC 6: sent
  802.3 D3.0 (802.3cj) was liaised in Feb 2018
60-day pre-ballot: passed & response sent
  802.3-REV 60-day ballot passed on 14 April 2019 (N16917)
    Passed 7/0/11 on need for ISO standard
    Passed 5/1/12 on support for submission to FDIS
    China NB voted “no” with comments; response was sent in June 2019 (N16971)
FDIS ballot: passed & response liaised
  802.3-REV FDIS ballot passed on 22 July 2020 (N17223)
    Passed 10/1/9, with two comments from China NB
  A response to China NB was sent in Nov 2020 (N17388)
  Was published as ISO/IEC/IEEE 8802-3:2021

## Slide 184: IEEE 802.1AE-2018/Cor1-2020 was published in Jun 2021
Drafts sent to SC 6: sent
  802.1AE-2018/Cor1-2020 was liaised in Aug 2020 (N17252)
90-day FDIS: passed & published
  IEEE 802.1AE-2018/Cor1-2020 90-day FDIS ballot (N17321) passed on 13 Jan 2021
    Passed 7/0/10 (N17471)
  Published as ISO/IEC/IEEE 8802-1AE:2020/COR 1:2021 in June 2021

## Slide 185: IEEE 802.1Qcx will be included in IEEE 802.1Q-Rev rather than a separate submission
Drafts sent to SC 6: sent
  802.1Qcx D2.0 was liaised in Jan 2020 (N17095)
60-day pre-ballot: on hold
  (Jul 2020) Paul Congdon writes:
    P802.1Qcx/D2.0 was sent to ISO/IEC JTC1 SC 6 for information in January, however we are considering NOT sending 802.1Qcx-2020 for adoption because it will be included in the IEEE 802.1Q-Revision project that is planning to start WG balloting very soon (and is expected to progress quickly).
  (Sep 2021) Will remove 802.1Qcx from pipeline once IEEE 802.1Q-Revision liaised for information
FDIS ballot: waiting

## Slide 186: IEEE 802.1Qcr will be included in IEEE 802.1Q-Rev rather than a separate submission
Drafts sent to SC 6: sent
  802.1Qcr D2.3 was liaised in Aug 2020 (N17269)
60-day pre-ballot: on hold
  (Nov 2020) May be part of 802.1Q-Rev
  (Sep 2021) Will remove 802.1Qcx from pipeline once IEEE 802.1Q-Revision liaised for information
FDIS ballot: waiting

## Slide 187: IEEE 802.1Qcp-2018 was published as ISO/IEC/IEEE 8802-1Q:2020/AMD 2:2021 in Sep 2021
Drafts sent to SC 6: sent
  D2.6 liaised in Dec 2017 (WG1-N119)
  802.1Qcp was published in Sept 2018
60-day pre-ballot: passed
  802.1Qcp-2018 60-day ballot passed on 16 July 2020 (N17245)
    Passed 8/0/10 on need for ISO standard
    Passed 6/0/12 on support for submission to FDIS
    There were no comments
FDIS ballot: passed & published
  IEEE 802.1Qcp-2018 FDIS ballot passed on 29 Jul 2021
    Passed 8/0/10 (N17612)
  Published as ISO/IEC/IEEE 8802-1Q:2020/AMD 2:2021 in Sep 2021

## Slide 188: IEEE 802.1Qcy-2019 was published as ISO/IEC/IEEE 8802-1Q:2020/AMD 3:2021 in Sep 2021
Drafts sent to SC 6: sent
  D2.1 was liaised in Apr 2018 (WG1N124)
60-day pre-ballot: passed
  802.1Qcy-2019 60-day ballot passed on 16 July 2020 (N17246)
    Passed 8/0/10 on need for ISO standard
    Passed 6/0/12 on support for submission to FDIS
    There were no comments
FDIS ballot: passed & published
  IEEE 802.1Qcy-2019 FDIS ballot passed on 29 Jul 2021
    Passed 8/0/10 (N17553)
  Published as ISO/IEC/IEEE 8802-1Q:2020/AMD3 in Sep 2021

## Slide 189: IEEE 802.1AX-Rev was published as ISO/IEC/IEEE 8802-1AX:2021 in Sep 2021
Drafts sent to SC 6: sent
  802.1AX-Rev D2.0 was liaised in Jul 2019 (N16984)
60-day pre-ballot: passed
  A motion to submit was approved by IEEE 802 EC in Hawaii in Nov 2019
  802.1AX-Rev 60-day ballot passed on 22 August 2020 (N17267)
    Passed 9/0/9 on need for ISO standard
    Passed 7/0/11 on support for submission to FDIS
    There were no comments
FDIS ballot: passed & published
  802.1AX-Rev FDIS ballot passed on 29 Jul 2021
    Passed 8/0/10 (N17552)
  802.1AX was published as ISO/IEC/IEEE 8802-1AX:2021 in Sep 2021

## Slide 190: IEEE 802.1Qcc was published as ISO/IEC/IEEE 8802-1Q:2020/AMD 31:2021
Drafts sent to SC 6: sent
  D2.0 liaised in Dec 2017 (WG1-N119)
60-day pre-ballot: passed & response sent
  IEEE 802.1Qcc 60-day ballot passed on 16 July 2020 (N17244)
    Passed 8/0/10 on need for ISO standard
    Passed 6/1/9 on support for submission to FDIS
    China voted “no” with 2 comments, with response sent Oct 2020 (N17443)
FDIS ballot: passed & published & response sent
  IEEE 802.1Qcc FDIS ballot passed on 8 Sep 2021 (N17603)
    Passed 8/1/10
    China NB voted no with usual security related comments
    802.1 WG sent responses in Jan 2022 (N17662)
  Published as ISO/IEC/IEEE 8802-1Q:2020/AMD 31:2021

## Slide 191: IEEE 802.1AS-Rev published as ISO/IEC/IEEE 8802-1AS:2021
Drafts sent to SC 6: sent
  802.1AS-Rev D8 was liaised in Mar 2019 (N17089 in Jan 2020)
60-day pre-ballot: passed & response sent
  802.1AS-Rev 60-day ballot passed on 22 August 2020 (N17268)
    Passed 9/0/9 on need for ISO standard
    Passed 7/1/10 on support for submission to FDIS
    China voted “no” with one comment; response sent in Oct 2020 (N17442)
FDIS ballot: passed, published & response sent
  802.1AS-Rev FDIS ballot passed on 16 Sept 2021
    Passed 8/1/10, with usual security comment from China NB (N17611)
    802.1 WG sent responses in Jan 2022 (N17663)
  Published as ISO/IEC/IEEE 8802-1AS:2021

## Slide 192: IEEE 802.1CMde published as ISO/IEC/IEEE 8802-1CM:2019/Amd 1:2021
Drafts sent to SC 6: sent
  802.1CMde D2.0 was liaised in Jan 2020 (N17094)
60-day pre-ballot: passed
  802.1CMde 60-day ballot passed on 22 Jan 2021 (N17470)
    Passed 8/0/9 on need for ISO standard
    Passed 7/0/10 on support for submission to FDIS
FDIS ballot: passed, published & response sent
  802.1CMde FDIS ballot passed on 8 Sep 2021 (N17604)
    Passed 8/1/10
    China NB voted no with usual security related comments
    802.1 WG sent responses in Jan 2022 (N17661)
  Published as ISO/IEC/IEEE 8802-1CM:2019/Amd 1:2021

## Slide 193: IEEE 802.3cn-2019 was published as ISO/IEC/IEEE 8802-3:2021/Amd 4:2021
Drafts sent to SC 6: sent
  802.3cn D3.1 was liaised for information in Dec 2019 (N17086)
60-day pre-ballot: passed
  802.3cn-2019 60-day ballot passed on 14 Dec 2020 (N17447)
    Passed 9/0/9 on need for ISO standard
    Passed 9/0/9 on support for submission to FDIS
FDIS ballot: passed, response sent & published
  802.3cn-2019 FDIS ballot passed on 8 Sep 2021 (N17606)
    Passed 9/1/9
    China NB voted no with the usual demand that 802.3 include security
    (27 Nov 2021) multi-ballot response sent (N17645)
  Published as ISO/IEC/IEEE 8802-3:2021/Amd 4:2021

## Slide 194: IEEE 802.3cq-2020 was published as ISO/IEC/IEEE 8802-3:2021/Amd 6:2021
Drafts sent to SC 6: sent
  802.3cq D3.2 was liaised for information in Dec 2019 (N17086)
    D3.1 was approved by EC but D3.2 was available and so was the version liaised
60-day pre-ballot: passed
  802.3cq-2020 60-day ballot passed on 14 Dec 2020 (N17448)
    Passed 9/0/9 on need for ISO standard
    Passed 9/0/9 on support for submission to FDIS
FDIS ballot: passed, response sent & published
  802.3cq-2020 FDIS ballot passed on 8 Sep 2021 (N17607)
    Passed 9/1/9
    China NB voted no with the usual demand that 802.3 include security
    (27 Nov 2021) multi-ballot response sent (N17645)
  Published as ISO/IEC/IEEE 8802-3:2021/Amd 6:2021

## Slide 195: IEEE 802.3cm-2020 was published as ISO/IEC/IEEE 8802-3:2021/Amd 7:2021
Drafts sent to SC 6: sent
  802.3cm D3.1 was liaised for information in Dec 2019 (N17086)
60-day pre-ballot: passed
  802.3cm-2020 60-day ballot passed on 14 Dec 2020 (N17449)
    Passed 9/0/9 on need for ISO standard
    Passed 9/0/9 on support for submission to FDIS
FDIS ballot: passed, response sent & published
  802.3cm-2020 FDIS ballot passed on 8 Sep 2021 (N17608)
    Passed 9/1/9
    China NB voted no with the usual demand that 802.3 include security
    (27 Nov 2021) multi-ballot response sent (N17645)
  Published as ISO/IEC/IEEE 8802-3:2021/Amd 7:2021

## Slide 196: IEEE 802.3ch-2020 is published as ISO/IEC/IEEE 8802-3:2021/Amd 8:2021
Drafts sent to SC 6: sent
  802.3ch D3.0 was liaised for information in Dec 2019 (N17086)
60-day pre-ballot: passed
  802.3ch-2020 60-day ballot passed on 14 Dec 2020 (N17446)
    Passed 9/0/9 on need for ISO standard
    Passed 9/0/9 on support for submission to FDIS
FDIS ballot: passed, response sent & published
  802.3ch-2020 FDIS ballot passed on 8 Sep 2021 (N17605)
    Passed 9/1/9
    China NB voted no with the usual demand that 802.3 include security
    (27 Nov 2021) multi-ballot response sent (N17645)
  Published as ISO/IEC/IEEE 8802-3:2021/Amd 8:2021

## Slide 197: IEEE 802.3.2-2019 was published as ISO/IEC/IEEE 8802-3-2:2021:2021
Drafts sent to SC 6: sent
  802.3.2 D3.0 was liaised for information in Feb 2019 (N16893)
60-day pre-ballot: passed & response sent
  802.3.2-2019 60-day ballot passed on 14 Dec 2020 (N17451)
    Passed 8/1/9 on need for ISO standard
    Passed 8/1/9 on support for submission to FDIS
  China NB voted “no” with two comments
    Response sent in Feb 2021 (N17474)
FDIS ballot: passed, response sent & published
  802.3.2-2019 FDIS ballot passed on 8 Sep 2021 (N17644)
    Passed 8/0/11
    China NB voted yes, but with the usual demand that 802.3 include security
    (27 Nov 2021) multi-ballot response sent (N17645)
  Published as ISO/IEC/IEEE 8802-3-2:2021

## Slide 198: IEEE 802.3cb-2018 is published as ISO/IEC/IEEE 8802-3:2021/Amd 1:2021
Drafts sent to SC 6: sent
  802.3cb D3.0 was liaised in June 2017
60-day pre-ballot: passed & response sent
  802.3cb-2018 60-day ballot passed on 8 April 2019 (N16914)
    Passed 8/0/9 on need for ISO standard
    Passed 6/1/10 on support for submission to FDIS
    China NB voted “no” with comments; response was sent in June 2019 (N16971)
FDIS ballot: passed, published & response sent
  IEEE 802.3cb-2018 FDIS ballot passed on 11 Nov 2021 (N17638)
    Passed 8/1/10
    China NB voted no with the usual demand that 802.3 include security
      (Feb 2022) Responses were sent (N17669)
  Published as ISO/IEC/IEEE 8802-3:2021/Amd 1:2021

## Slide 199: IEEE 802.3bt-2018 is published as ISO/IEC/IEEE 8802-3:2021/Amd 2:2021
Drafts sent to SC 6: sent
  802.3bt D3.2 was liaised in Feb 2018
60-day pre-ballot: passed
  802.3cd-2018 60-day ballot passed on 17 Oct 2020 (N17340)
    Passed 7/0/10 on need for ISO standard
    Passed 6/0/11 on support for submission to FDIS
FDIS ballot: passed, published & response sent
  IEEE 802.3bt-2018 FDIS ballot passed on 11 Nov 2021 (N17639)
    Passed 9/1/9
    China NB voted no with the usual demand that 802.3 include security
      (Feb 2022) Responses were sent (N17669)
  Published as ISO/IEC/IEEE 8802-3:2021/Amd 2:2021

## Slide 200: IEEE 802.3cd-2018 is published as ISO/IEC/IEEE 8802-3:2021/Amd 3:2021
Drafts sent to SC 6: sent
  802.3cd D3.0 was liaised in Feb 2018
60-day pre-ballot: passed
  802.3bt-2018 60-day ballot passed on 17 Oct 2020 (N17339)
    Passed 7/0/10 on need for ISO standard
    Passed 6/0/11 on support for submission to FDIS
FDIS ballot: passed, published & response sent
  IEEE 802.3cd-2018 FDIS ballot passed on 11 Nov 2021 (N17640)
    Passed 9/1/9
    China NB voted no with the usual demand that 802.3 include security
      (Feb 2022) Responses were sent (N17669)
  Published as ISO/IEC/IEEE 8802-3:2021/Amd 3:2021

## Slide 201: IEEE 802.3cg-2019 is published as ISO/IEC/IEEE 8802-3:2021/Amd 5:2021
Drafts sent to SC 6: sent
  802.3cg D3.1 was liaised for information in Jun 2019 (N16973)
60-day pre-ballot: passed
  802.3cg-2019 60-day ballot passed on 14 Dec 2020 (N17444)
    Passed 9/0/9 on need for ISO standard
    Passed 9/0/9 on support for submission to FDIS
FDIS ballot: passed, published & response sent
  IEEE 802.3cg-2019 FDIS ballot passed on 17 Nov 2021 (N17641)
    Passed 10/1/11
    China NB voted no with the usual demand that 802.3 include security
      (Feb 2022) Responses were sent (N17669)
  Published as ISO/IEC/IEEE 8802-3:2021/Amd 5:2021

## Slide 202: IEEE 802.3ca-2020 is published as ISO/IEC/IEEE 8802-3:2021/Amd 9:2021
Drafts sent to SC 6: sent
  802.3ca D3.0 was liaised for information in Dec 2019 (N17086)
60-day pre-ballot: passed
  802.3ca-2020 60-day ballot passed on 14 Dec 2020 (N17445)
    Passed 9/0/9 on need for ISO standard
    Passed 9/0/9 on support for submission to FDIS
FDIS ballot: passed, published & response sent
  802.3ca-2020 FDIS ballot passed on 17 Nov 2021 (N17642)
    Passed 9/1/9
    China NB voted no with the usual demand that 802.3 include security
      (Feb 2022) Responses were sent (N17669)
  Published as ISO/IEC/IEEE 8802-3:2021/Amd 9:2021

## Slide 203: IEEE 802.1X-2020 was published as ISO/IEC/IEEE 8802-1X:2021
Drafts sent to SC 6: sent
  802.1X-2020 was liaised for information in Aug 2020 (N17251)
60-day pre-ballot: passed & response sent
  802.1X-2020 60-day ballot passed on 14 Dec 2020 (N17450)
    Passed 9/0/9 on need for ISO standard
    Passed 8/1/9 on support for submission to FDIS (China NB voted no)
    Response (N17493) was approved in Mar 2021 & sent in Apr 2021
FDIS ballot: passed, published & response sent
  802.1X-2020 FDIS ballot passed on 17 Nov 2021
    Passed 9/1/9, with the usual security comments from China NB (N17643)
    A response was sent in Mar 2022 (N17741)
  Published as ISO/IEC/IEEE 8802-1X:2021

## Slide 204: IEEE 802.1CS has been published
Drafts sent to SC 6: sent
  802.1CS D3.0 was liaised in Aug 2020 (N17269)
60-day pre-ballot: passed
  802.1CS 60-day ballot passed on 31 Jul 2021 (N17554)
    Passed 8/0/9 on need for ISO standard
    Passed 7/0/10 on support for submission to FDIS
FDIS ballot: passed & published
  802.1CS FDIS ballot passed on 4 Jun 2022
    Passed 9/0/10
  Published as ISO/IEC/IEEE 8802-1CS:2022

## Slide 205: IEEE 802.3cr has been published
Drafts sent to SC 6: sent
  IEEE 802.3cr D3.1 was liaised in Oct 2020 (N17346)
60-day pre-ballot: passed
  IEEE 802.3cr 60-day ballot passed on 11 Jun 2021 (N17517)
    Passed 9/0/10 on need for ISO standard
    Passed 8/0/11 on support for submission to FDIS
FDIS ballot: passed & published
  IEEE 802.3cr FDIS ballot passed on 4 Jun 2022
    Passed 9/0/10
  Published as ISO/IEC/IEEE 8802-3:2021/Amd 10:2022

## Slide 206: IEEE 802.3cu has been published
Drafts sent to SC 6: sent
  IEEE 802.3cu D3.0 was liaised in Oct 2020 (N17346)
60-day pre-ballot: passed
  IEEE 802.3cu 60-day ballot passed on 11 Jun 2021 (N17515)
    Passed 9/0/10 on need for ISO standard
    Passed 8/0/11 on support for submission to FDIS
FDIS ballot: passed & published
  IEEE 802.3cu FDIS ballot passed on 4 Jun 2022
    Passed 9/0/10
  Published as ISO/IEC/IEEE 8802-3:2021/Amd 11:2022

## Slide 207: IEEE 802.22-2019 has been published
Drafts sent to SC 6: sent
  D8.0 sent in Nov 2019 (N17064)
60-day pre-ballot: passed & response sent
  IEEE 802.22-2019 passed on 16 Oct 2020 (N17342)
    Passed 6/0/11 on need for ISO standard
    Passed 5/1/11 on support for submission to FDIS
    China NB voted “no” with comments
      Comment resolution was sent in late Dec 2020 (N17405)
FDIS ballot: passed & published & response sent
  IEEE 802.22-2019 FDIS ballot passed on 18 Mar 2022 (N17685)
    Passed 9/1/9
    China NB voted “no” with a repeat of the previous comment
    A proposed response was liaised in Aug 2022 (see 11-22-0806-02) (N17855)
  Published as ISO/IEC/IEEE 8802-22:2022

## Slide 208: Routing Packets in IEEE 802.15.4 Dynamically Changing Wireless Networks IEEE 802.15.10-2017 will not be submitted into the PSDO process
Drafts sent to SC 6: no need
  (Sep 2022) It was suggested that 802.15.10 (and 10a) be submitted into PSDO process – however, it is a recommended practice, which is not covered by PSDO agreement
60-day pre-ballot: no need
FDIS ballot: no need

## Slide 209: IEEE 802.11-2020 FDIS passed, a response liaised & published
Drafts sent to SC 6: sent
  802.11md D3.0 was liaised for information in Jan 2020 (N17082)
60-day pre-ballot: passed & response sent
  802.11-2020 60-day ballot passed on 1 Jun 2021 (N17516)
    Passed 9/0/10 on need for ISO standard
    Passed 8/1/10 on support for submission to FDIS
  The China NB voted “no” with 18 comments
    Response liaised in Aug 2021 (N17600)
FDIS ballot: passed, response sent & published
  802.11-2020 FDIS ballot passed on 23 Jun 2022 (N17748)
    Passed 8/2/8, negative votes from Japan NB & China NB
    Technical responses were liaised (N17853) in Jul 2022
    Japan NB’s IPR related, non tech comments need to be dealt with by ISO staff
  It has been published as ISO/IEC/IEEE 802-11:2022 (July 2022)

## Slide 210: Power over Ethernet IEEE 802.3cv has been published as ISO/IEC/IEEE 8802-3:2021/Amd 12:2022
Drafts sent to SC 6: sent
  IEEE 802.3cv D3.0 was liaised in Jan 2021 (N17453)
60-day pre-ballot: passed & response sent
  IEEE 802.3cv 60-day ballot passed on 9 Oct 2021 (N17627)
    Passed 8/0/11 on need for ISO standard
    Passed 7/1/11 on support for submission to FDIS
    China NB voted no with the usual demand that 802.3 include security
    (27 Nov 2021) multi-ballot response sent (N17645)
FDIS ballot: passed, response sent, published
  802.3cv FDIS ballot passed on 1 Sep 2022 (N17849)
    Passed 10/1/8, negative vote China NB (same security comments)
    Response sent (N17935)
  Published as ISO/IEC/IEEE 8802-3:2021/Amd 12:2022

## Slide 211: 100 Gb/s Operation over DWDM Systems IEEE 802.3ct published as ISO/IEC/IEEE 8802-3:2021/Amd 13:2022
Drafts sent to SC 6: sent
  IEEE 802.3ct D3.1 was liaised in Jan 2021 (N17453)
60-day pre-ballot: passed & response sent
  IEEE 802.3ct 60-day ballot passed on 9 Oct 2021 (N17626)
    Passed 8/0/11 on need for ISO standard
    Passed 7/1/11 on support for submission to FDIS
    China NB voted no with the usual demand that 802.3 include security
    (27 Nov 2021) multi-ballot response sent (N17645)
FDIS ballot: passed, response sent, published
  802.3ct FDIS ballot passed on 2 Sep 2022 (N17844)
    Passed 10/1/8, negative vote China NB (same security comments as 802.3cv/cp, even incorrectly references 802.3cp)
    Response sent (N17935)
  Published as ISO/IEC/IEEE 8802-3:2021/Amd 13:2022

## Slide 212: Bidirectional 10 Gb/s, 25 Gb/s, and 50 Gb/s Optical Access PHYs IEEE 802.3cp published as ISO/IEC/IEEE 8802-3:2021/Amd 14:2022
Drafts sent to SC 6: sent
  IEEE 802.3cp D3.0 was liaised in Feb 2021 (N17475)
60-day pre-ballot: passed & response sent
  IEEE 802.3cp 60-day ballot passed on 9 Oct 2021 (N17629)
    Passed 8/0/11 on need for ISO standard
    Passed 7/1/11 on support for submission to FDIS
    China NB voted no with the usual demand that 802.3 include security
    (27 Nov 2021) multi-ballot response sent (N17645)
FDIS ballot: passed, response sent, published
  802.3cp FDIS ballot passed on 2 Sep 2022 (N17846)
    Passed 10/1/8, negative vote China NB (same security comments as 802.3cv)
    Response sent (N17935)
  Published as ISO/IEC/IEEE 8802-3:2021/Amd 14:2022

## Slide 213: A number of ISO/IEC/IEEE standards are subject to systematic review
Systematic review ballots
  ISO/IEC/IEEE 8802-1AB:2017 SR was confirmed on 2 Dec 2022
    The China NB commented about security of the IS, “This standard shall be used together with IEEE 802.1X and IEEE 802.1AE standards with security defects, it should no longer be valid”
    However, the China NB also commented, “This international standard is being modified and adopted as the national standard of China, and the state of the national standard of China is under approval.” …
    … with the modifications specified as, “China's national standards modify the security mechanism of this international standards”
    IEEE has notified ISO as any national body must seek permission from IEEE to modify an IEEE standard adopted by ISO under the PSDO agreement

## Slide 214: Frame Replication & Elimination for Reliability: Extended Stream Identification Functions IEEE 802.1CBdb passed FDIS ballot & has been published
Drafts sent to SC 6: sent
  802.1CBdb D2.0 was liaised for information on 23 Sep 2021 (N17614)
60-day pre-ballot: passed
  802.1CBdb 60-day ballot passed on 14 Jun 2022 (N17750)
    Passed 8/0/10 on need for ISO standard
    Passed 8/0/10 on support for submission to FDIS
FDIS ballot: passed, waiting for publication
  802.1CBdb FDIS ballot passed on 16 Jan 23 (N17949)
    Passed 9/0/10
    No comments
  Published as ISO/IEC/IEEE 8802-1CB:2019/Amd 2:2023

## Slide 215: Information model, YANG data model, & management information base module IEEE 802.1CBcv passed FDIS ballot & has been published
Drafts sent to SC 6: sent
  802.1CBcv D2.0 was liaised for information on 23 Sep 2021 (N17614)
60-day pre-ballot: passed
  802.1CBcv 60-day ballot passed on 14 Jun 22 (N17749)
    Passed 8/0/10 on need for ISO standard
    Passed 8/0/10 on support for submission to FDIS
FDIS ballot: passed, waiting for publication
  802.1CBcv FDIS ballot passed on 16 Jan 20 (N17950)
    Passed 9/0/10
    No comments
  Published as ISO/IEC/IEEE 8802-1CB:2019/Amd 1:2023

## Slide 216: Audio Video Bridging (AVB) Systems IEEE 802.1BA-Rev passed FDIS ballot in Mar 2023
Drafts sent to SC 6: sent
  802.1BA-Rev D2.0 was liaised for information on 23 Sep 2021 (N17614)
60-day pre-ballot: passed & response sent
  802.1BA 60-day ballot passed on 24 Jun 2022 (N17847)
    Passed 8/0/11 on need for ISO standard
    Passed 7/1/10 on support for submission to FDIS
  China NB voted “no: with usual security related comments
    A response was sent in Jul 2022 (N17852)
FDIS ballot: closed 24 Mar 2023
  One negative from the China NB for the usual reason (see N18054). Response to be recycled after approval during the July plenary.
  Was published as ISO/IEC/IEEE 8802-1BA:2023 in March 2023

## Slide 217: MAC Service Definition: Support for IEEE Std 802.15.3 IEEE 802.1ACct passed FDIS ballot in Mar 2023
Drafts sent to SC 6: sent
  802.1ACct D2.0 was liaised for information on 23 Sep 2021 (N17614)
60-day pre-ballot: passed & response sent
  802.1ACct 60-day ballot passed on 10 Apr 2022 (N17703)
    Passed 8/0/11 on need for ISO standard
    Passed 7/1/11 on support for submission to FDIS
  China NB had usual comments that needed a response
    A response was sent in Jul 2022 (N17856)
FDIS ballot: closed 24 Mar 2023
  Passed with repeated comments from the China NB (see N18055). Repeated response to be sent after approval during July plenary.
  Has been published as ISO/IEC/IEEE 8802-1AC:2018/Amd 1:2023

## Slide 218: The ISO version of one IEEE 802.15 standard completed systematic review
Systematic review
  ISO/IEC/IEEE 8802-15-4:2018 – closed 4 June 2023
    Vote 6/0/0/1/12/0 (Confirm/Revise/Withdraw/Abst1/Abst2/Stabilize) (N18086)

## Slide 219: The ISO version of one IEEE 802.1 standard completed systematic review
Systematic review
  ISO/IEC/IEEE 8802-1AC:2018 – closed 3 September 2023
    Vote 6/0/1/1/11/0 (Confirm/Revise/Withdraw/Abst1/Abst2/Stabilize) (N18109)
    Votes to confirm from: Canada, Japan, South Korea, [Nigeria], Ukraine, United Kingdom, and United States
    The vote to withdraw came from the China National Body (based on reliance on the IEEE 802.11(!) architecture and IEEE 802.1AE)

## Slide 220: MAC Connectivity Discovery: YANG Data Model IEEE 802.1ABcu passed FDIS ballot in June 2023
Drafts sent to SC 6: sent
  802.1ABcu D2.0 was sent for information on 23 Jul 2021 (N17613)
60-day pre-ballot: passed
  802.1ABcu 60-day ballot passed on 22 Jul 2022 (N17845)
    Passed 7/0/12 on need for ISO standard
    Passed 7/0/12 on support for submission to FDIS
FDIS ballot: passed
802.1ABcu 5-month FDIS ballot passed on 21 June 2023 (N18088)
    Passed 10/0/9 without comments
  Has been published as ISO/IEC/IEEE 8802-1AB:2017/Amd 1:2023

## Slide 221: Support for Multi-frame Protocol Data Units IEEE 802.1ABdh passed FDIS ballot in June 2023
Drafts sent to SC 6: sent
  802.1ABdh D2.0 was liaised for information on 23 Sep 2021 (N17614)
60-day pre-ballot: passed
  802.1ABdh 60-day ballot passed on 22 Jul 2022 (N17848)
    Passed 7/0/12 on need for ISO standard
    Passed 7/0/12 on support for submission to FDIS
FDIS ballot: passed 21 June 2023
  802.1ABdh 5-month FDIS ballot passed on 21 June 2023 (N18087)
    Passed 10/0/9 without comments
  Has been published as ISO/IEC/IEEE 8802-1AB:2017/Amd 2:2023

## Slide 222: The ISO versions of two IEEE 802.21 standards completed systematic review
Systematic review
  ISO/IEC/IEEE 8802-21:2018 – closed 3 September 2023
    Vote 6/0/0/1/12/0 (Confirm/Revise/Withdraw/Abst1/Abst2/Stabilize) (N18110)
  ISO/IEC/IEEE 8802-21-1:2018 – closed 3 September 2023
    Vote 6/0/0/1/12/0 (Confirm/Revise/Withdraw/Abst1/Abst2/Stabilize) (N18111)
    In favor were Canada, Japan, South Korea, [Nigeria], Ukraine, United Kingdom, and United States.
    The China National Body voted for withdrawal (owing to reliance on IEEE 802.1X)

## Slide 223: The AG4 convenor sent IEEE 802 a request in relation to MCS issues in Ethernet
  The convenor (Kingston Zhang - kingston_zhang1999@126.com) of ISO/IEC JTC 1/SC 6 AG4 sent the following
    As the convenor of ISO/IEC JTC 1/SC 6 advisory group 4 on MCS Innovation (AG 4), I am writing to ask for your attention to the activities of AG 4 since its foundation on July 1, 2022. The group has held two meetings and a third meeting is scheduled for 15 Feb. 2023. On 4 Oct. 2022, SC 6 Secretariat issued a call for AG 4 membership registration (6N17860), but IEEE has not registered delegate in the group.
    AG 4 is formed based on the constructive discussions between SC 6 and IEEE on WLAN MCS challenges. In the ToR, AG 4 needs to extend the scope of the MCS deficiency analysis to other representative application fields. During the second meeting, LAN (Ethernet) MCS challenge is seen as a significant field for study. If a contribution is received on this subject, I will add it to the agenda of the third meeting. IEEE's participation in the discussion will be very beneficial
  See following pages for context

## Slide 224: The LS sent in response to the HK NB submission WG1 N289 was discussed by SC 6/WG 1 in Feb 2022
  The HK NB uploaded a document (WG1 N289) that
    Asserts High Efficiency wrt 802.11ax is ill defined
    Evaluates 1024QAM in 802.11ax – noting deficiencies
    Evaluates 4096QAM in 802.11be – noting deficiencies
    Expressed concerns about high order QAM in the future
    Proposes SC 6 start a research program on “the challenges of MCS schemes and the ways to continuously improve efficiencies of communication and network systems”
  The 802.11 WG and 802 EC subsequently approved a LS
    See 11-21-1450-06 (WG1 N297 and N17619)
  The LS was discussed at the SC 6/WG 1 meeting in Feb 2022
    It was agreed the labelling issue was minor and/or trivial
    China NB stated they intended to propose a research project on QAM mechanisms
July 2022

## Slide 225: The HK NB proposal an Advisory Group on MCS Innovation has been accepted?
  The HK NB submitted a document in late Mar 2022 proposing an Advisory Group on MCS Innovation
    See N17684
  In July 2022, SC 6 approved the Establishment of a SC 6 Advisory Group on MCS Innovation
    See N17817 for summary
    See N17834 for ToR
  The proposed mission (with a three-year time horizon) is
    The Mission of AG-MCS is to study the challenges of MCS schemes, to explore ways to, continuously improve MCS efficiencies of communication and network systems, and to find new MCS technologies and propose standardization projects for SC 6
  It is suggested that IEEE 802 monitor this activity
July 2022

## Slide 226: Is there any interest for someone to join the AG 4 global directory to monitor the MCS activity
  Previously we agreed to monitor this activity
  Monitoring requires someone to join the AG 4 global directory (via the SC 6 secretary) … and reporting back
  George Zimmerman has attended one session
  Is there any other interest?

## Slide 227: SC 6 concluded voting on the Deterministic wireless industrial network PWI
PWI
  Deterministic wireless industrial network
Scope
  This standard defines the physical layer (PHY) and medium access control (MAC) sublayer specifications of the deterministic wireless industrial network operating in unlicensed band for the discrete manufacturing that guarantees 250 us bounded end-to-end latency and 125 us cycle time and is capable to be integrated to the wired TSN.
Plan
  PHY & MAC by Dec 2024
Ballot
  Closed 27 Jan 2023. Result: 4/3/12

## Slide 228: Resolutions of the JTC 1/SC 6 Plenary in March 2023
  Resolution 6.0.1 Request a report on adoption of IEEE standards
    Asks ISO/CS to report on the status of the following IEEE standards with negative LoAs: IEEE 802.11ai, IEEE 802.11ah, IEEE 802.11af, IEEE 802.11ah, IEEE 802.11-2016 (incorporating IEEE 802.11ae, 802.11aa, 802.11ad, 802.11ac, 802.11af into IEEE 802.11-2012), IEEE 802.11ax, and IEEE 802.11ay. No mention of IEEE 802.11ba.
    Approved

## Slide 229: Resolutions of the JTC 1/SC 6 Plenary in March 2023
  Resolution 6.0.2 Request to consider SC 6's feedback in the revision work of the ISO/IEEE PSDO Agreement
    Ask ISO/CS to consider:
      When submitting standards for fast-tracking via the FDIS process, IEEE should inform ISO whether a standard proposed for adoption has one or more negative LoAs prior to the initiation of balloting. ISO/CS should collaboratively work with IEEE on this issue.
      To prevent confusion among SC 6 members, IEEE standards with one or more negative LoAs should not be initiated in the ISO fast track adoption process
    Approved over objections by the US and UK National Bodies

## Slide 230: US NB's late comments on SC 6 N 17954 for SC 6 Plenary and SC 6/WG 1 Meeting
  US NB submitted N 17994 making the following points:
    SC 6 should not request ISO look at the negative LoAs on published standards.
    SC 6 not request IEEE “propose solutions to such problems to ensure that proposals submitted to SC 6 are in compliance with ISO patent policy.”
    SC 6 not attempt to suspend approval initiations under the PSDO agreement.
  It’s not clear to me whether this input was discussed. It certainly wasn’t accepted based on the previously reported resolutions.

## Slide 231: Resolutions of the JTC 1/SC 6 Plenary in March 2023
  Resolution 6.A.3 Appreciation to Andrew Myles
    SC 6 expresses heartfelt gratitude to Andrew Myles for his fruitful collaboration with SC 6 on behalf of IEEE spanning two decades. His unwavering dedication has significantly contributed to the enhanced cooperation between SC 6 and IEEE.
    Acclaimed

## Slide 232: The 802.3 WG is likely to approve the liaising of multiple docs for information and then ratification
Published
  IEEE Std 802.3-2022
  IEEE Std 802.3dd-2022
On RevCom agenda
  IEEE P802.3cs
  IEEE P802.3db
  IEEE P802.3ck
  IEEE P802.3de
In SA ballot
  IEEE P802.3cx
  IEEE P802.3cz
Seek approval to send IEEE Std 802.3-2022 for preview at the IEEE 802.3 Ethernet WG interim meeting on 15 September and seek EC approval at the 4 October teleconference meeting
Seek approval to send the first 4 (tbc) amendment standards/drafts for preview at the November plenary meeting
Seek approval to send the next 3 to 4 (depending on project status) amendment standards/drafts for preview during the January 2023 (WG) and February 2023 (EC) meetings.

## Slide 233: Power over Data Lines of Single Pair Ethernet IEEE 802.3dd will probably be liaised after IEEE 802.3-2022 has completed PSDO process
Drafts sent to SC 6: waiting
  (Nov 2022) EC approved for liaising for information
    (Jan 2023) Staff suggests liaising held off until IEEE 802.3-2022 has completed PSDO process
      Do we want do wait until ISO version approved?
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 234: Increased-reach Ethernet optical subscriber access (Super-PON) IEEE 802.3cs will probably be liaised after IEEE 802.3-2022 has completed PSDO process
Drafts sent to SC 6: waiting
  (Nov 2022) EC approved for liaising for information
    (Jan 2023) Staff suggests liaising held off until IEEE 802.3-2022 has completed PSDO process
      Do we want do wait until ISO version approved?
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 235: 100 Gb/s, 200 Gb/s, and 400 Gb/s Short Reach Fiber IEEE 802.3db will probably be liaised after IEEE 802.3-2022 has completed PSDO process
Drafts sent to SC 6: waiting
  (Nov 2022) EC approved for liaising for information
    (Jan 2023) Staff suggests liaising held off until IEEE 802.3-2022 has completed PSDO process
      Do we want do wait until ISO version approved?
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 236: 100 Gb/s, 200 Gb/s, and 400 Gb/s Electrical Interfaces IEEE 802.3ck will probably be liaised after IEEE 802.3-2022 has completed PSDO process
Drafts sent to SC 6: waiting
  (Nov 2022) EC approved for liaising for information
    (Jan 2023) Staff suggests liaising held off until IEEE 802.3-2022 has completed PSDO process
      Do we want do wait until ISO version approved?
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 237: Time Synchronization for Point-to-Point Single Pair Ethernet IEEE 802.3de will probably be liaised sometime in 2023
Drafts sent to SC 6: waiting
  (Jan 2023) EC approval for liaising for information likely in about March 2023
    Should liaising be held off until ISO version of IEEE 802.3-2022 approved?
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 238: Improved PTP Timestamping Accuracy IEEE 802.3cx will probably be liaised sometime in 2023
Drafts sent to SC 6: waiting
  (Jan 2023) EC approval for liaising for information likely in about March 2023
    Should liaising be held off until ISO version of IEEE 802.3-2022 approved?
60-day pre-ballot: waiting
FDIS ballot: waiting

## Slide 239: Multi-Gigabit Optical Automotive Ethernet IEEE 802.3cz will probably be liaised sometime in 2023
Drafts sent to SC 6: waiting
  (Jan 2023) EC approval for liaising for information likely in about March 2023
    Should liaising be held off until ISO version of IEEE 802.3-2022 approved?
60-day pre-ballot: waiting
FDIS ballot: waiting