## Slide 1
Task Group BF November 2023 Closing Report
Date: 2023-11-16
Authors:
Name | Affiliation | Address | Phone | Email
Tony Xiao Han | Huawei Technologies Co., Ltd. | F3, Huawei Base, Shenzhen, China |  | Tony.hanxiao@huawei.com

## Slide 2: Abstract
This document is the closing report for Task Group BF for the November 2023 session.

## Slide 3: TGbf (WLAN Sensing)– November 2023
Progress during November 2023 session
  7 slots scheduled for TGbf
  Comment resolution for D2.0 (LB276)
    the Comment resolution for 127 CID are newly approved or marked as “ready for motion”
    100% of all LB272 comments are now resolved or marked as “ready for motion”
    (545 /545, Please refer to the figure)
Goals for the next two months
  Release the Draft 3.0
  TGbf Recirculation LB (D3.0), and assign the comments
  Requested 1 calls per week
Chart: P802.11bf D2.0 CR Status
| Technical | General | Editorial
Received | 257 | 19 | 269
Resolved | 257 | 19 | 269

## Slide 4: TGbf Timeline (To be discuss and Updated)
  PAR approved Sep 2020
  First TG meeting Oct 2020
  Comment Collection (D0.1) Jan 2022Mar 2022
   April 2022
  Initial Letter Ballot (D1.0) Jul 2022 Sep 2022 Nov 2022
   Jan 2023
  Recirculation LB (D2.0) Jan 2023  Mar 2023
   July 2023
  Recirculation LB (D3.0) May 2023  Nov 2023
  Recirculation LB (D4.0) July 2023 à Jan 2024à Mar 2024
  Initial SA Ballot (D4.0) Sep 2023 à Mar 2024à May 2024
  Final 802.11 WG approval July 2024à Jan 2025à Mar 2025
  802 EC approval July 2024à Jan 2025à Mar 2025
  RevCom and SASB approval Sep 2024à Mar 2025à May 2025
Timeline (Comment resolution for D2.0)
July 14, 2023
  802.11 Working group Motion passes：802.11bf (WLAN Sensing) Draft 2.0 and Re-circulation Letter Ballot
Wed July 26, 2023 at 23:59 Eastern Time USA (11:59 PM)
  Initial LB start for D2.0
Sun August 20, 2023 at 23:59 Eastern Time USA (11:59 PM)
  Initial LB end for D2.0
  Assign the comments
Target for Recirculation LB (D3.0) in November Plenary

## Slide 5
Teleconference Times (plan after November Plenary)
  Confirmed:
    Dec 12 (Tuesday) 9：00 - 11:00 ET
    Dec 21 (Thursday) 22：00 - 00:00 ET
    Jan 4 (Thursday) 22：00 - 00:00 ET
    Jan 8 (Monday) 9：00 - 11:00 ET
    Jan 9 (Tuesday) 9：00 - 11:00 ET