## Slide 1: TGbe March Closing Report
Date: 2024-03-14
Authors:

## Slide 2: TGbe (Extremely High Throughput)
TGbe had scheduled 5 sessions during the March plenary
  Two Joint, one MAC/PHY and two MAC ad-hoc sessions
    Discussed comment resolution documents
      All comments in the PHY and Joint tabs are resolved
  Instructed the editor to generate IEEE802.11 TGbe D5.1
    TGbe D5.1 is expected to be available by end of March 2024
Agenda is available in 11-24/0237r10
Motions List is available in 11-23/442r45
Goals for May 2024:
  Complete comment resolution from initial SA ballot
CID Distribution (415)
~5%
~90%
~5%
MAC
JOINT
PHY

## Slide 3: Teleconference Plan
March 27 (Wednesday) – MAC 10:00-12:00 ET
April 03 (Wednesday) – Joint* 10:00-12:00 ET
April 10 (Wednesday) – MAC 10:00-12:00 ET
April 17 (Wednesday) – Joint* 10:00-12:00 ET
April 24 (Wednesday) – MAC 10:00-12:00 ET
May 02 (Wednesday) Holiday
May 08 (Wednesday) – MAC 10:00-12:00 ET
PHY ad-hoc calls, on demand, with 10-day advanced notice (in parallel with MAC)

## Slide 4: TGbe Timeline And Status
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sept 2020
D1.0 WG Comment Collection May 2021
D2.0 WG Letter Ballot May 2022
D3.0 LB Jan 2023
D4.0 LB July 2023
D5.0 Recirculation LB Nov 2023
Initial SA Ballot Jan 2024
Final 802.11 WG approval Sept 2024
802 EC approval Sept 2024
RevCom and SASB approval Dec 2024