## Slide 1: TGbk 320MHz Positioning May Meeting Closing Report
Date: 2024-05-16
Authors:

## Slide 2: Abstract
This document is the TGbk 320MHz Positioning closing report for the IEEE 802.11 May 2024 interim meeting.

## Slide 3: May Meeting Progress and Targets Towards the July Meeting
Work completed during this meeting:
  Reviewed, and approved resolution to 50 Technical and General CIDs, roughly 2/3 of the received T/G comments.
  Reviewed 7 CR submissions and approved 10 motions.
  Conducted vice chairs and secretary re-affirmation vote.
  Initiated Mandatory Draft Review and SA ballot pool formation.
Jonathan Segev, Intel corporation
Chart: LB286 CR Progress
| Overall | Editorial | Technical | General
LB286 | 134 | 53 | 72 | 9
Current completion | 52 | 0 | 45 | 7
  Reviewed and considered progress – no change to timelines.

## Slide 4: May Meeting Progress and Targets Towards the July Meeting
Work expected towards July meeting:
  Complete 80% of LB286 technical and general CR (targeting recirculation out of July).
  Complete 95% of LB286 editorial CR.
  Review feedback from MDR
  Address 70% of feedback collected in the MDR process.
Jonathan Segev, Intel corporation
Chart: LB286 CR Progress
| Overall | Editorial | Technical | General
LB286 | 134 | 53 | 72 | 9
Current completion | 52 | 0 | 45 | 7

## Slide 5: TGbk Projected Timeline (previous)
Q2 2024
Q1 2024
Q3 2023
Q2 2023
Q1 2023
Q4 2023
Q3 2024
Q4 2024
Formation
Framework
Framework completion
05/23
802.11bk amendment text development
Initial WG ballot
Recirc 03/24
11bk D2.0
Initial SA
07/24
Final WG ballot 7/24
11bk D3.0
MDR
MDR start
MDR cmp
D4.0
D5.0
Final SA
11/24
SA Recir.
10/24

## Slide 6: TGbk Projected Timeline (updated)
Q2 2024
Q1 2024
Q3 2023
Q2 2023
Q1 2023
Q4 2023
Q3 2024
Q4 2024
Formation
Framework
Framework completion
05/23
802.11bk amendment text development
Initial WG ballot
Recirc 03/24
11bk D2.0
Initial SA
07/24
Final WG ballot 7/24
11bk D3.0
MDR
MDR start
MDR cmp
D4.0
D5.0
Final SA
11/24
SA Recir.
10/24

## Slide 7: Scheduled TGbk telecons
  June 4th 10:00 am PT/13:00 ET (2hrs)
  June 11th 10:00 am PT/13:00 ET (2hrs)
  June 25th 10:00 am PT/13:00 ET (2hrs) ┼
  July 9th 10:00 am PT/13:00 ET (2hrs)
** - meeting as part of the IEEE week, refer to WG agenda document for details.
┼ - Motion meeting, motions to be made available to chair 15 days in advance and announced to group 10 days in advance.