## Slide 1: TGbn January Closing Report
Date: 2025-01-16
Authors:

## Slide 2: TGbn (Ultra High Reliability)
TGbn had scheduled 11 sessions during the January interim
  Discussed technical submissions covering a variety of topics and proposed draft texts (PDTs)
  Approved over 100 motions that added additional concepts to the TGbn SFD, and spec text to the TGbn D0.1
  Instructed the TGbn Editor to create TGbn D0.1
Agenda is available in 11-24/2074r18,
Motions are available in 11-24/0014r8.
Goals for March 2025:
  Discuss technical submissions
  Resolve comments received from the internal CC
    Comment collection (CC) to start after TGbn D0.1 is published
      The duration of the internal CC expected to be ~3 weeks
    Comment assignment to be performed during telcos
  Continue populating the TGbn SFD & preparing PDTs
  Instruct the TGbn Editor to create TGbn D0.2

## Slide 3: Teleconference Plan
January 27-February 05 (Monday-Wednesday) Holiday
February 06 (Thursday) – MAC/PHY 10:00-12:00 ET
February 10 (Monday) – MAC/PHY 19:00-21:00 ET
February 13 (Thursday) – MAC/PHY 10:00-12:00 ET
February 17 (Monday) Holiday
February 20 (Thursday) – MAC/PHY 10:00-12:00 ET
February 24 (Monday) – MAC/PHY 19:00-21:00 ET
February 27 (Thursday) – Joint (Motions)* 10:00-12:00 ET
March 03-March 07 (Monday-Friday) Holiday
* TGbn joint session during which there can be motions, subject to WG chair approval and with 10-day advanced notice.

## Slide 4: TGbn Timeline And Status
  PAR approved July 2023
  First TG meeting Nov 2023
  D0.1 Jan 2025
  D1.0 Letter Ballot May 2025
  D2.0 LB May 2026
  D3.0 LB Jan 2027
  Initial SA ballot (D4.0) May 2027
  Final 802.11 WG approval Mar 2028
  802 EC approval Mar 2028
  RevCom and SASB approval May 2028