## Slide 1: TGbr – Enhanced Light Communications Proposed Timeline
Date: 2025-05-11
Authors:

## Slide 2: Abstract
This presentation contains the timeline for the successful completion of the IEEE 802.11 Light Communications Amendment.

## Slide 3: Work Plan
Task Group | 2025 | May | Core feature proposals
 |  | Jul | Core feature proposals D0.1 Table of Content
 |  | Sept. | Considerations for PHY and MAC
 |  | Nov. | Review incoming PHY text and MAC contributions Agree D0.1 with initial text
 | 2026 | Jan | PHY text complete for D0.1
 |  | Mar | Agree PHY common mode and optional mode text
 |  | Jun | Agree centre frequency, spectral masks and create D0.2 (all PHY text complete)
 |  | Jul | List MAC feature set
 |  | Sep | Initial text for MAC
 |  | Nov | Collect first MAC contributions
 | 2027 | Jan | Collect MAC text for D0.3
 |  | Mar | Review and resolve comments on D0.3, Send Draft 0.4 to WG for CC
 |  | May | Review and resolve WG comments on D0.4 to create D0.5 for recirculation
 |  | Jul. | Review and resolve comments on D0.5 to create D0.6 for WG Comment Collection
 |  | Sept. | Draft D0.7 review for Draft 1.0 (potential for WG LB)
 |  | Nov. | Create D1.0 and send for Letter Ballot for D1.0

## Slide 4: Work Plan
TG | 2028 | Jan | Review and resolve WG comments on D1.0 and create D2.0 for WG LB
 |  | Mar | Review and resolve WG comments on D2.0 and create D3.0 for WG LB
 |  | April | Recirculation D3.0 WG LB (unchanged)
 |  | May | Submission of D3.0 (unchanged) for SA Ballot
 |  | July | SA Ballot Comment Resolution
 |  | Sept. | SA Ballot Comment Resolution
 |  | Oct. | Submission to RevCom
 |  | Nov. | Final EC Approval
 |  | Dec. | RevCom / SA SB Approval