## Slide 1: On the timeline for TGbr
Date: 2025-05-12
Authors:

## Slide 2: Abstract
This presentation contains the timeline for the successful completion of the IEEE 802.11br Enhanced Light Communications Amendment.

## Slide 3: Timelines for TGbr vs. TGbb
Mar-2025 PAR approved (TGbb: Sept-2018)
Jul-2025 initial SFD
Nov-2025 agree main features (PHY)
Jan-2026 start PDT (PHY)
Jul-2026 complete PHY (D0.1)
Sep-2026 agree main features (MAC)
Nov-2026 start PDT (MAC)
Jan-2027 complete MAC (D0.2), start internal CC
Jul-2027 complete D0.x, start CC in 802.11 WG
Nov-2027 D1.0 for WG letter ballot (TGbb: Jan-2022)
Jan-2028 D2.0 (TGbb: Apr-2022)
Mar-2028 D3.0 (TGbb: Aug-2022)
May-2028 start SA ballot (TGbb: Nov-2022)
Nov-2028 submit to RevCom (TGbb: Mar-2023)
2029 publish