## Slide 1
  Proposed P802.16s Amendment Extension Request to RevCom
Document Number:
  IEEE 802.16-17-0022-00-000s
Date Submitted:
  2017-05-12
Source:
  Roger B. Marks Voice: +1 802 capable
  EthAirNet Associates E-mail: roger@ethair.net
  4040 Montview Blvd
  Denver, CO 80207 USA
  *<http://standards.ieee.org/faqs/affiliationFAQ.html>
Re:
  P802.16s amendment to RevCom
Base Contribution:
  none
Purpose:
  For review by 802.16 Working Group at Session #99
Notice:
  This document does not represent the agreed views of the IEEE 802.16 Working Group or any of its subgroups. It represents only the views of the participants listed in the “Source(s)” field above. It is offered as a basis for discussion. It is not binding on the contributor(s), who reserve(s) the right to add, amend or withdraw material contained herein.
Copyright Policy:
  The contributor is familiar with the IEEE-SA Copyright Policy <http://standards.ieee.org/IPR/copyrightpolicy.html>.
Patent Policy:
  The contributor is familiar with the IEEE-SA Patent Policy and Procedures:
      <http://standards.ieee.org/guides/bylaws/sect6-7.html#6> and <http://standards.ieee.org/guides/opman/sect6.html#6.3>.
  Further information is located at <http://standards.ieee.org/board/pat/pat-material.html> and <http://standards.ieee.org/board/pat >.

## Slide 2: Background: SASB 8.1.2
    Up to three amendments can be approved before the standard shall be revised, unless the base standard has been approved within the past three years. In such a case, multiple amendments may be added until the base standard is three years old. After the three-year period, RevCom shall defer consideration of additional amendments or corrigenda until a revision or a two-year extension request is approved by the IEEE-SA Standards Board.
    If, for any extenuating circumstances, an exception to these rules is required, the Sponsor shall take its request for a two-year extension to RevCom. A project plan outlining the rationale for the request, as well as a schedule for the revision, also shall be submitted. RevCom will review the request and make a recommendation to the IEEE-SA Standards Board.
    During the two-year extension period, Sponsors can submit additional amendments and corrigenda for approval consideration. However, after this period, RevCom shall defer consideration of additional amendments or corrigenda until a revision is approved by the IEEE-SA Standards Board.

## Slide 3: Background: P802.16s
  P802.16s amendment is currently in Sponsor Ballot
    first round closed 12 May
        approval status: X/Y/Z
        XX comments
    This would be the fourth amendment to IEEE Std 802.16-2012
        IEEE Std 802.16p (First Amendment)
        IEEE Std 802.16n (Second Amendment)
        IEEE Std 802.16q (Third Amendment)
  SASB 8.1.2 is applicable.

## Slide 4: Background: 802.16 Revision
  P802.16 Revision Project authorized 2017-02-17
    Initial draft (including rollup of three amendments) completed and reviewed in Working Group Letter Ballot, closing 2017-04-16
    Expectation that P802.16s material will be added during ballot
    Schedule indicates completion in late 2017

## Slide 5: Rationale (Part 1)
  The P802.16s project is the only project underway to amend IEEE 802.16-2012.
  The P802.16 revision project is well underway and is expected to complete in 2017, incorporating the content of P802.16s.
  Although the request is for a two-year extension period, the only need is for a brief window in which to approve P802.16s.
  Allowing the P802.16s project to complete first will allow for that work to be quickly available to the industry and also allow the upcoming revision to provide a new clean version of the standard that will remain unamended for at least a few years.

## Slide 6: Rationale (Part 2)
  The P802.16s Sponsor Ballot has met the approval ratio requirements, and ballot resolution is expected by July 2017.
  Per the SASB Operations Manual (5.4.3.5 “Completion of the standards balloting process and submittal to RevCom”):
    “the IEEE has an obligation to the majority to review and publish the proposed standard quickly”

## Slide 7: Schedule for the Revision (1/2)
Date | Date End | Draft | Ballot or Progress | Action by
2017-02-17 |  |  | PAR Authorization | IEEE-SA SB
2017-03-07 |  | pre-D1.0 | Prepared by Technical Editor | Technical Editor
2017-03-16 |  | D1.0 | agreed by WG for WG Letter Ballot | Maint TG Chair
2017-03-24 | 2017-04-24 | D1.0 | WG LB #41 | Maint TG Chair
2017-05-19 |  |  | Editor's Proposed Dispositions | Technical Editor
2017-05-31 | 2017-06-01 |  | comment resolution, Draft 0.1 (Session #109) | Maint TG Chair
2017-06-16 |  | D1.0 | Prepared by Technical Editor | Technical Editor
2017-06-16 |  |  | D1.1 submitted for Mandatory Editorial Coordination (MEC) | Technical Editor
2017-06-16 | 2017-07-16 |  | Form Sponsor Ballot Group | WG Chair
2017-06-19 | 2017-06-29 | D1.1 | WG LB Recirc #41a | Maint TG Chair
2017-07-06 |  |  | Editor's Proposed Dispositions | Technical Editor
2017-07-11 |  |  | comment resolution, Draft 1.1 | Technical Editor
2017-07-11 | 2017-07-13 |  | comment resolution, Draft 1.0 (Session #110) | Maint TG Chair
2017-07-14 |  |  | EC Conditional Approval for Sponsor Ballot | WG Chair
2017-07-17 |  | D2.0 | Prepared by Technical Editor | Technical Editor
2017-07-17 | 2017-07-27 | D2.0 | WG LB Recirc #41b | Maint TG Chair

## Slide 8: Schedule for the Revision (2/2)
Date | Date End | Draft | Ballot or Progress | Action by
2017-07-28 | 2017-08-28 | D2.0 | Sponsor Ballot | Maint TG Chair
2017-09-04 |  |  | Editor's Proposed Dispositions | Technical Editor
2017-09-12 | 2017-09-14 |  | comment resolution, Draft 2.0 (Session #111) | Maint TG Chair
2017-10-16 |  | D2.1 | Prepared by Technical Editor | Technical Editor
2017-10-16 | 2017-10-26 |  | Sponsor Ballot Recirc A | Maint TG Chair
2017-10-31 |  |  | Editor's Proposed Dispositions | Technical Editor
2017-11-07 | 2017-11-09 |  | comment resolution, Draft 2.1 (Session #112) | Maint TG Chair
2017-11-10 |  |  | EC Conditional Approval for RevCom | WG Chair
2017-11-24 |  | D2.2 | Prepared by Technical Editor | Technical Editor
2017-11-27 | 2017-12-08 | D2.2 | Sponsor Ballot Recirc B | Maint TG Chair
2017-12-11 |  |  | submit D2.2 to RevCom | WG Chair
2017-12-11 | 2018-01-31 |  | Pre-publication preparationa and review by Technical Editor and editorial staff | Technical Editor
2018-01-30 |  |  | approval at RevCom teleconference (approximate date) | RevCom Admin
2018-02-16 |  |  | approval by IEEE-SA ballot (approximate date) | RevCom Admin
2018-02-23 |  |  | publication (approximate date) | Maint TG Chair

## Slide 9: Request
An extension to allow consideration of P802.16s as the fourth amendment to IEEE Std 802.16-2012